## ADNOC
SN | Date | DURATION TIMES | DURATION HRS | DURATION DAYS | Activity | LEVEL 1 | LEVEL 2 | ACTIVITY ID | ACTIVITY NAME
1 | 2026-01-25 | 04:30 Hrs | 25.5 | 1.06 | Vessel released from shipping and sailed to MZP anchorage to berth on 26 Jan 2026 as requested by SCT. | OPERATIONAL | Deck Preparations | A1004 | Deck Preparations (D-ring cutting; marking, steel sets installation) - One 5t forklift and Crane required
2 | 2026-01-26 | 06:00 Hrs | 35.63 | 1.48 | Vessel remained at anchorage as Berth wasn’t secured | MOBILIZATION | SPMT | A1000 | Mobilization of 1st set of SPMT; Asembly + Function Test
3 | 2026-01-27 | 17:38 Hrs | 23.37 | 0.97 | Bushra Berthed at MZP RoRo Berth No. 5 | OPERATIONAL | Deck Preparations | A1004 | Deck Preparations (D-ring cutting; marking, steel sets installation) - One 5t forklift and Crane required
4 | 2026-01-28 | 17:00 Hrs | 65.5 | 2.73 | Grillage, stools installed and welding completed onboard Bushra. | OPERATIONAL | Deck Preparations | A1005 | Deck Preparations (Steel sets installation, welding) - Crane Required for steel sets installation
5 | 2026-01-31 | 10:30 Hrs | 0.5 | 0.02 | Loading Permission received by MZP Harbor Master. | OPERATIONAL | AGI TR Unit 1 | A1070 | RoRo ramp removal; Seafastening AGL TR Unit 1 - Crane required
6 | 2026-01-31 | 11:00 Hrs | 9.6 | 0.4 | Loading TR No. 1 Completed | OPERATIONAL | AGI TR Unit 1 | A1070 | RoRo ramp removal; Seafastening AGL TR Unit 1 - Crane required
7 | 2026-01-31 | 20:36 Hrs | 9.4 | 0.39 | MWS Sail away certificate was received Bushra Cast off MZP | OPERATIONAL | AGI TR Unit 1 | A1070 | RoRo ramp removal; Seafastening AGL TR Unit 1 - Crane required
8 | 2026-02-01 | 06:00 Hrs | 47 | 1.96 | Bushra Dropped anchor at Al Ghallan Anchorage waiting for Berth | OPERATIONAL | AGI TR Unit 1 | A1081 | MWS; MPI; Sail-away - Marine Transportation by LCT to Al Ghallan Island
9 | 2026-02-03 | 05:00 Hrs | 35.1 | 1.46 | MMT team travelled from Mina Port to AGI for TR No. 1 offloading | OPERATIONAL | AGI TR Unit 1 | A1110 | Load-in of AGI TR Unit 1 (including RoRo Ramp Installation); store on Jetty - Crane required
10 | 2026-02-04 | 16:06 Hrs | 4.4 | 0.18 | Bushra Berthed alongside West RoRo Berth No. 3 at AGI | OPERATIONAL | AGI TR Unit 1 | A1140 | AGL TR Unit 1 (TR Bay 4) load on SPMT; lashing; Transportation and JD (steel set to be delivered to bay area by trailer)
11 | 2026-02-04 | 20:30 Hrs | 86.5 | 3.6 | J62 arrived to AGI with Lifting clamps for TR No. 1 offloading | OPERATIONAL | AGI TR Unit 1 | A1121 | LCT Sails back to MZP to collect TR Unit 1
12 | 2026-02-08 | 11:00 Hrs | 3.63 | 0.15 | Tr No. 1 Offloaded at AGI | OPERATIONAL | AGI TR Unit 1 | A1150 | Jacking down of AGI TR Unit 1 (TR Bay 4) on temporary support - Forklift required
13 | 2026-02-08 | 14:38 Hrs | 8.07 | 0.34 | Bushra Sailed from AGI | OPERATIONAL | AGI TR Unit 1 | A1150 | Jacking down of AGI TR Unit 1 (TR Bay 4) on temporary support - Forklift required
14 | 2026-02-08 | 22:42 Hrs |  |  | Bushra dropped anchor at MZP anchorage waiting for berth | OPERATIONAL | AGI TR Unit 1 | A1150 | Jacking down of AGI TR Unit 1 (TR Bay 4) on temporary support - Forklift required

## BUSHRA VODR
NO | START DATE | START TIME | END DATE | END TIME | DURATION TIMES | DURATION HRS | DURATION DAYS | Activity | LEVEL 1 | LEVEL 2 | ACTIVITY ID | ACTIVITY NAME
1 | 2026-01-27 | 0:00 | 2026-01-28 | 9:00 | 33:00 HRS | 33 | 1.38 | SECURED ALONGSIDE MINA ZAYED RORO BERTH /PILOT OFF | OPERATIONAL | Deck Preparations | A1004 | Deck Preparations (D-ring cutting; marking, steel sets installation) - One 5t forklift and Crane required
2 | 2026-01-28 | 0:00 | 2026-01-28 | 10:12 | 10:12 HRS | 10.2 | 0.42 | COMMENCE DECK PREPARATION | OPERATIONAL | Deck Preparations | A1005 | Deck Preparations (Steel sets installation, welding) - Crane Required for steel sets installation
3 | 2026-01-28 | 0:00 | 2026-01-28 | 10:30 | 10:30 HRS | 10.5 | 0.44 | START CUTTING PAD EYE | OPERATIONAL | Deck Preparations | A1005 | Deck Preparations (Steel sets installation, welding) - Crane Required for steel sets installation
4 | 2026-01-28 | 0:00 | 2026-01-28 | 13:00 | 13:00 HRS | 13 | 0.54 | RAMP DOOR LOWERED | OPERATIONAL | Deck Preparations | A1005 | Deck Preparations (Steel sets installation, welding) - Crane Required for steel sets installation
5 | 2026-01-28 | 0:00 | 2026-01-28 | 14:24 | 14:24 HRS | 14.4 | 0.6 | LUNCH BREAK | OPERATIONAL | Deck Preparations | A1005 | Deck Preparations (Steel sets installation, welding) - Crane Required for steel sets installation
6 | 2026-01-28 | 0:00 | 2026-01-28 | 15:00 | 15:00 HRS | 15 | 0.62 | RESUME DECK PREPARATION WORK | OPERATIONAL | Deck Preparations | A1005 | Deck Preparations (Steel sets installation, welding) - Crane Required for steel sets installation
7 | 2026-01-28 | 0:00 | 2026-01-29 | 0:00 | 24:00 HRS | 24 | 1 | STOP DECK PREPARATION WORK | OPERATIONAL | Deck Preparations | A1005 | Deck Preparations (Steel sets installation, welding) - Crane Required for steel sets installation
8 | 2026-01-29 | 0:00 | 2026-01-30 | 0:00 | 24:00 HRS | 24 | 1 | MINA ZAYED PORT | OPERATIONAL | Beam Replacement |  | Beam Replacement
9 | 2026-01-30 | 0:00 | 2026-01-31 | 0:00 | 24:00 HRS | 24 | 1 | MINA ZAYED PORT | OPERATIONAL | AGI TR Unit 1 | A1030 | Loading of AGI TR Unit 1 on SPMT; lashing; Shifting to Mina Zayed Port RoRo Jetty area
10 | 2026-01-31 | 0:00 | 2026-01-31 | 1:45 | 01:45 HRS | 1.75 | 0.07 | MINA ZAYED PORT/ DECK PREPARATION IN PROGRESS | MOBILIZATION | JACKING EQUIPMENT, STEEL BRIDGE | A2010 | Mobilization of Jacking Equipment and Steel bridge (prior LCT's arrival to AGI with TR 1&2!))
11 | 2026-01-31 | 0:00 | 2026-01-31 | 10:30 | 10:30 HRS | 10.5 | 0.44 | COMMENCE PUMPING WATER TRANSFER TO TANKER TRUCK | MOBILIZATION | JACKING EQUIPMENT, STEEL BRIDGE | A2010 | Mobilization of Jacking Equipment and Steel bridge (prior LCT's arrival to AGI with TR 1&2!))
12 | 2026-01-31 | 0:00 | 2026-01-31 | 10:51 | 10:51 HRS | 10.85 | 0.45 | COMMENCE LOADING TRANSFORMER CARGO | OPERATIONAL | AGI TR Unit 1 | A1070 | RoRo ramp removal; Seafastening AGL TR Unit 1 - Crane required
13 | 2026-01-31 | 0:00 | 2026-01-31 | 10:54 | 10:54 HRS | 10.9 | 0.45 | TRANSFORMER IN POSITION | OPERATIONAL | AGI TR Unit 1 | A1070 | RoRo ramp removal; Seafastening AGL TR Unit 1 - Crane required
14 | 2026-01-31 | 0:00 | 2026-01-31 | 13:00 | 13:00 HRS | 13 | 0.54 | COMPLETE TRANSFORMER INSPECTION | OPERATIONAL | AGI TR Unit 1 | A1070 | RoRo ramp removal; Seafastening AGL TR Unit 1 - Crane required
15 | 2026-01-31 | 0:00 | 2026-01-31 | 13:45 | 13:45 HRS | 13.75 | 0.57 | LUNCH BREAK | MOBILIZATION | JACKING EQUIPMENT, STEEL BRIDGE | A2010 | Mobilization of Jacking Equipment and Steel bridge (prior LCT's arrival to AGI with TR 1&2!))
16 | 2026-01-31 | 0:00 | 2026-01-31 | 15:00 | 15:00 HRS | 15 | 0.62 | RESUME CARGO SECURING JOB AND WELDING | MOBILIZATION | JACKING EQUIPMENT, STEEL BRIDGE | A2010 | Mobilization of Jacking Equipment and Steel bridge (prior LCT's arrival to AGI with TR 1&2!))
17 | 2026-01-31 | 0:00 | 2026-01-31 | 16:45 | 16:45 HRS | 16.75 | 0.7 | COMMENCE DISCHARGE PORTABLE GENERATOR WELDING SECURING IN PROGRESS | MOBILIZATION | JACKING EQUIPMENT, STEEL BRIDGE | A2010 | Mobilization of Jacking Equipment and Steel bridge (prior LCT's arrival to AGI with TR 1&2!))
18 | 2026-01-31 | 0:00 | 2026-01-31 | 20:24 | 20:24 HRS | 20.4 | 0.85 | COMPLETED LASHING AND SECURING JOB/NDT COMPLETED | MOBILIZATION | JACKING EQUIPMENT, STEEL BRIDGE | A2010 | Mobilization of Jacking Equipment and Steel bridge (prior LCT's arrival to AGI with TR 1&2!))
19 | 2026-01-31 | 0:00 | 2026-01-31 | 20:30 | 20:30 HRS | 20.5 | 0.85 | PILOT ONBOARD - CASTED OFF MZP | MOBILIZATION | JACKING EQUIPMENT, STEEL BRIDGE | A2010 | Mobilization of Jacking Equipment and Steel bridge (prior LCT's arrival to AGI with TR 1&2!))
20 | 2026-01-31 | 0:00 | 2026-01-31 | 21:00 | 21:00 HRS | 21 | 0.88 | PILOT OFF - MANOUVRE OT AL GHALLAN | MOBILIZATION | JACKING EQUIPMENT, STEEL BRIDGE | A2010 | Mobilization of Jacking Equipment and Steel bridge (prior LCT's arrival to AGI with TR 1&2!))
21 | 2026-01-31 | 0:00 | 2026-02-01 | 6:00 | 30:00 HRS | 30 | 1.25 | CLEAR MINA ZAYED CHANNEL | MOBILIZATION | JACKING EQUIPMENT, STEEL BRIDGE | A2010 | Mobilization of Jacking Equipment and Steel bridge (prior LCT's arrival to AGI with TR 1&2!))
22 | 2026-02-01 | 0:00 | 2026-02-02 | 0:00 | 24:00 HRS | 24 | 1 | DROPPED ANCHOR AT SOUTH ZAKUM AREA WAITING INSTRUCTIONS | OPERATIONAL | AGI TR Unit 1 | A1081 | MWS; MPI; Sail-away - Marine Transportation by LCT to Al Ghallan Island
23 | 2026-02-02 | 0:00 | 2026-02-03 | 0:00 | 24:00 HRS | 24 | 1 | DROPPED ANCHOR AT SOUTH ZAKUM AREA WAITING INSTRUCTIONS | OPERATIONAL | AGI TR Unit 1 | A1100 | Unlashing and cutting; steel sets preparations - Forklift required
24 | 2026-02-03 | 0:00 | 2026-02-04 | 0:00 | 24:00 HRS | 24 | 1 | DROPPED ANCHOR AT SOUTH ZAKUM AREA WAITING INSTRUCTIONS | OPERATIONAL | AGI TR Unit 1 | A1110 | Load-in of AGI TR Unit 1 (including RoRo Ramp Installation); store on Jetty - Crane required
25 | 2026-02-04 | 0:00 | 2026-02-04 | 12:12 | 12:12 HRS | 12.2 | 0.51 | DROPPED ANCHOR AT SOUTH ZAKUM AREA WAITING INSTRUCTIONS | OPERATIONAL | AGI TR Unit 1 | A1140 | AGL TR Unit 1 (TR Bay 4) load on SPMT; lashing; Transportation and JD (steel set to be delivered to bay area by trailer)
26 | 2026-02-04 | 0:00 | 2026-02-04 | 12:18 | 12:18 HRS | 12.3 | 0.51 | START HEAVE UP ANCHOR | OPERATIONAL | AGI TR Unit 1 | A1140 | AGL TR Unit 1 (TR Bay 4) load on SPMT; lashing; Transportation and JD (steel set to be delivered to bay area by trailer)
27 | 2026-02-04 | 0:00 | 2026-02-04 | 13:48 | 13:48 HRS | 13.8 | 0.57 | ANCHOR AWEIGH PROCEED TO AL GHALLAN | OPERATIONAL | AGI TR Unit 1 | A1140 | AGL TR Unit 1 (TR Bay 4) load on SPMT; lashing; Transportation and JD (steel set to be delivered to bay area by trailer)
28 | 2026-02-04 | 0:00 | 2026-02-04 | 14:06 | 14:06 HRS | 14.1 | 0.59 | ENTERED FIELD LIMIT ZAKUM FIELD | OPERATIONAL | AGI TR Unit 1 | A1140 | AGL TR Unit 1 (TR Bay 4) load on SPMT; lashing; Transportation and JD (steel set to be delivered to bay area by trailer)
29 | 2026-02-04 | 0:00 | 2026-02-04 | 15:24 | 15:24 HRS | 15.4 | 0.64 | ENTERED CHANNEL | OPERATIONAL | AGI TR Unit 1 | A1140 | AGL TR Unit 1 (TR Bay 4) load on SPMT; lashing; Transportation and JD (steel set to be delivered to bay area by trailer)
30 | 2026-02-04 | 0:00 | 2026-02-04 | 15:45 | 15:45 HRS | 15.75 | 0.66 | ARRIVED BLANKET AREA | OPERATIONAL | AGI TR Unit 1 | A1140 | AGL TR Unit 1 (TR Bay 4) load on SPMT; lashing; Transportation and JD (steel set to be delivered to bay area by trailer)
31 | 2026-02-04 | 0:00 | 2026-02-04 | 16:06 | 16:06 HRS | 16.1 | 0.67 | PASSING BREAKWATER | OPERATIONAL | AGI TR Unit 1 | A1140 | AGL TR Unit 1 (TR Bay 4) load on SPMT; lashing; Transportation and JD (steel set to be delivered to bay area by trailer)
32 | 2026-02-04 | 0:00 | [5 empty] | SECURED ALONGSIDE AL GHALLAN WEST PORT BERTH 3/WAITING INSTRUCTIONS | OPERATIONAL | AGI TR Unit 1 | A1140 | AGL TR Unit 1 (TR Bay 4) load on SPMT; lashing; Transportation and JD (steel set to be delivered to bay area by trailer)

## WA TIMELINE
NO | START DATE | START TIME | END DATE | END TIME | DURATION TIMES | DURATION HRS | DURATION DAYS | Activity | LEVEL 1 | LEVEL 2 | ACTIVITY ID | ACTIVITY NAME
1 | 2026-01-24 | 10:47 | 2026-01-24 | 11:34 | 00:47 HRS | 0.78 | 0.03 | CHA: MZP load-out readiness 요약(Deck prep 27–28 Jan, Load-out target 29 Jan AM, Tide≥2.00m, 자원 24h 사전요청, tug/TBC, Ramp certificate 필요 가능) | OPERATIONAL | Deck Preparations | A1004 | Deck Preparations (D-ring cutting; marking, steel sets installation) - One 5t forklift and Crane required
2 |  |  | 2026-01-25 | 9:08 |  |  |  | LCT Bushra: Musaffah short stay drop anchor 25/01/2026 0854 hrs | MOBILIZATION | SPMT | A1000 | Mobilization of 1st set of SPMT; Asembly + Function Test
3 | 2026-01-25 | 9:08 | 2026-01-25 | 9:11 | 00:03 HRS | 0.05 | 0 | Capt Igor: Samsung agent가 MZP berth arrange 전까지 anchorage 대기 | OPERATIONAL | Deck Preparations | A1004 | Deck Preparations (D-ring cutting; marking, steel sets installation) - One 5t forklift and Crane required
4 | 2026-01-25 | 9:11 | 2026-01-25 | 9:12 | 00:01 HRS | 0.02 | 0 | 상욱: Noted | MOBILIZATION | SPMT | A1000 | Mobilization of 1st set of SPMT; Asembly + Function Test
5 | 2026-01-25 | 9:12 | 2026-01-25 | 9:35 | 00:23 HRS | 0.38 | 0.02 | LCT Bushra: Noted | MOBILIZATION | SPMT | A1000 | Mobilization of 1st set of SPMT; Asembly + Function Test
6 |  |  | 2026-01-26 | 10:03 |  |  |  | Adnoc Ouda: Bushra MZP 도착 시점 문의(27 Jan?) | MOBILIZATION | SPMT | A1000 | Mobilization of 1st set of SPMT; Asembly + Function Test
7 | 2026-01-26 | 10:03 | 2026-01-26 | 10:12 | 00:09 HRS | 0.15 | 0.01 | CHA: 2026-01-27 08:00 AM | MOBILIZATION | SPMT | A1000 | Mobilization of 1st set of SPMT; Asembly + Function Test
8 | 2026-01-26 | 10:12 | 2026-01-26 | 10:14 | 00:02 HRS | 0.03 | 0 | Adnoc Ouda: Bushra 27 Jan 08:00 도착 준비 지시(berth/pilot/agent) | MOBILIZATION | SPMT | A1000 | Mobilization of 1st set of SPMT; Asembly + Function Test
9 | 2026-01-26 | 10:14 | 2026-01-26 | 10:22 | 00:08 HRS | 0.13 | 0.01 | Yoonus: Ramp certificates ASAP 요청 | MOBILIZATION | SPMT | A1000 | Mobilization of 1st set of SPMT; Asembly + Function Test
10 | 2026-01-26 | 10:22 | 2026-01-26 | 11:06 | 00:44 HRS | 0.73 | 0.03 | Yulia(MAMMOET): 10 forklift + 25t(이상) mobile crane 요청(14t mats 2pcs) | MOBILIZATION | SPMT | A1000 | Mobilization of 1st set of SPMT; Asembly + Function Test
11 | 2026-01-26 | 11:06 | 2026-01-26 | 11:07 | 00:01 HRS | 0.02 | 0 | CHA: NOTED | MOBILIZATION | SPMT | A1000 | Mobilization of 1st set of SPMT; Asembly + Function Test
12 | 2026-01-26 | 11:07 | 2026-01-26 | 11:13 | 00:06 HRS | 0.1 | 0 | Adnoc Ouda: Sent by mail | MOBILIZATION | SPMT | A1000 | Mobilization of 1st set of SPMT; Asembly + Function Test
13 | 2026-01-26 | 11:13 | 2026-01-26 | 14:10 | 02:57 HRS | 2.95 | 0.12 | Yulia: 5 trailers 도착, forklift/crane 제공 시점 문의 | MOBILIZATION | SPMT | A1000 | Mobilization of 1st set of SPMT; Asembly + Function Test
14 | 2026-01-26 | 14:10 | 2026-01-26 | 14:11 | 00:01 HRS | 0.02 | 0 | CHA: I check Ofco team | MOBILIZATION | SPMT | A1000 | Mobilization of 1st set of SPMT; Asembly + Function Test
15 | 2026-01-26 | 14:11 | 2026-01-26 | 14:53 | 00:42 HRS | 0.7 | 0.03 | Yulia: No crane and forklift until now =( | MOBILIZATION | SPMT | A1000 | Mobilization of 1st set of SPMT; Asembly + Function Test
16 | 2026-01-26 | 14:53 | 2026-01-26 | 15:00 | 00:07 HRS | 0.12 | 0.01 | Yoonus: F/L only available now, follow-up 중 | MOBILIZATION | SPMT | A1000 | Mobilization of 1st set of SPMT; Asembly + Function Test
17 | 2026-01-26 | 15:00 | 2026-01-26 | 15:00 | 00:00 HRS | 0 | 0 | Yoonus: F/L will be coming soon | MOBILIZATION | SPMT | A1000 | Mobilization of 1st set of SPMT; Asembly + Function Test
18 | 2026-01-26 | 15:00 | 2026-01-26 | 15:01 | 00:01 HRS | 0.02 | 0 | Yulia: 20t forklift면 crane 불필요(14t mats) | MOBILIZATION | SPMT | A1000 | Mobilization of 1st set of SPMT; Asembly + Function Test
19 | 2026-01-26 | 15:01 | 2026-01-26 | 15:01 | 00:00 HRS | 0 | 0 | Yoonus: this is 15T F/L | MOBILIZATION | SPMT | A1000 | Mobilization of 1st set of SPMT; Asembly + Function Test
20 | 2026-01-26 | 15:01 | 2026-01-26 | 15:49 | 00:48 HRS | 0.8 | 0.03 | Yoonus: meeting scheduled tomorrow with Mina Zayed HM | MOBILIZATION | SPMT | A1000 | Mobilization of 1st set of SPMT; Asembly + Function Test
21 | 2026-01-26 | 15:49 | 2026-01-26 | 15:57 | 00:08 HRS | 0.13 | 0.01 | Yulia: Until now no forklift... | MOBILIZATION | SPMT | A1000 | Mobilization of 1st set of SPMT; Asembly + Function Test
22 | 2026-01-26 | 15:57 | 2026-01-26 | 16:09 | 00:12 HRS | 0.2 | 0.01 | Yulia: 6pm 이후 offload 불가, forklift ASAP | MOBILIZATION | SPMT | A1000 | Mobilization of 1st set of SPMT; Asembly + Function Test
23 | 2026-01-26 | 16:09 | 2026-01-26 | 16:10 | 00:01 HRS | 0.02 | 0 | 상욱: OFCO team..pls.. | MOBILIZATION | SPMT | A1000 | Mobilization of 1st set of SPMT; Asembly + Function Test
24 | 2026-01-26 | 16:10 | 2026-01-26 | 16:13 | 00:03 HRS | 0.05 | 0 | CHA: The operation will start soon | MOBILIZATION | SPMT | A1000 | Mobilization of 1st set of SPMT; Asembly + Function Test
25 | 2026-01-26 | 16:13 | 2026-01-26 | 16:19 | 00:06 HRS | 0.1 | 0 | Yoonus: labour and forklift is there(현장), supervisor 번호 공유 | MOBILIZATION | SPMT | A1000 | Mobilization of 1st set of SPMT; Asembly + Function Test
26 | 2026-01-26 | 16:19 | 2026-01-26 | 17:29 | 01:10 HRS | 1.17 | 0.05 | Yulia: 내일 계획(08:00 SPMT/70t crane/10t FL/점심 후 2x10t FL) | MOBILIZATION | SPMT | A1000 | Mobilization of 1st set of SPMT; Asembly + Function Test
27 | 2026-01-26 | 17:29 | 2026-01-26 | 17:29 | 00:00 HRS | 0 | 0 | Yulia: 1st TR unit ID number 요청 | MOBILIZATION | SPMT | A1000 | Mobilization of 1st set of SPMT; Asembly + Function Test
28 | 2026-01-26 | 17:29 | 2026-01-26 | 17:31 | 00:02 HRS | 0.03 | 0 | CHA: Case no 364332 | MOBILIZATION | SPMT | A1000 | Mobilization of 1st set of SPMT; Asembly + Function Test
29 | 2026-01-26 | 17:31 | 2026-01-26 | 17:32 | 00:01 HRS | 0.02 | 0 | CHA: Yoonus please arrange | MOBILIZATION | SPMT | A1000 | Mobilization of 1st set of SPMT; Asembly + Function Test
30 | 2026-01-26 | 17:32 | 2026-01-26 | 17:33 | 00:01 HRS | 0.02 | 0 | Yoonus: Tomorrow crane/forklift/gang booking request submitted | MOBILIZATION | SPMT | A1000 | Mobilization of 1st set of SPMT; Asembly + Function Test
31 | 2026-01-26 | 17:33 | 2026-01-26 | 17:34 | 00:01 HRS | 0.02 | 0 | Yoonus: RORO jetty approval 대기 | MOBILIZATION | SPMT | A1000 | Mobilization of 1st set of SPMT; Asembly + Function Test
32 | 2026-01-26 | 17:34 | 2026-01-26 | 17:35 | 00:01 HRS | 0.02 | 0 | Yulia: beam replacement 위해 2nd forklift 요청 | MOBILIZATION | SPMT | A1000 | Mobilization of 1st set of SPMT; Asembly + Function Test
33 | 2026-01-26 | 17:35 | 2026-01-26 | 17:49 | 00:14 HRS | 0.23 | 0.01 | Yoonus: GC ops 확인 후 업데이트 예정 | MOBILIZATION | SPMT | A1000 | Mobilization of 1st set of SPMT; Asembly + Function Test
34 |  |  | 2026-01-27 | 7:07 |  |  |  | 상욱: Pls update | OPERATIONAL | Deck Preparations | A1004 | Deck Preparations (D-ring cutting; marking, steel sets installation) - One 5t forklift and Crane required
35 | 2026-01-27 | 7:07 | 2026-01-27 | 7:38 | 00:31 HRS | 0.52 | 0.02 | Yulia: Jetty 5 currently berthed LCT Safeen Kate | OPERATIONAL | Deck Preparations | A1004 | Deck Preparations (D-ring cutting; marking, steel sets installation) - One 5t forklift and Crane required
36 | 2026-01-27 | 7:38 | 2026-01-27 | 7:38 | 00:00 HRS | 0 | 0 | Yulia: SPMT crew & Marine crew arrived, preparing | OPERATIONAL | Deck Preparations | A1004 | Deck Preparations (D-ring cutting; marking, steel sets installation) - One 5t forklift and Crane required
37 | 2026-01-27 | 7:38 | 2026-01-27 | 7:39 | 00:01 HRS | 0.02 | 0 | CHA: Noted | OPERATIONAL | Deck Preparations | A1004 | Deck Preparations (D-ring cutting; marking, steel sets installation) - One 5t forklift and Crane required
38 | 2026-01-27 | 7:39 | 2026-01-27 | 7:39 | 00:00 HRS | 0 | 0 | Yulia: transformer serial number sticker 못 찾음(위치 문의) | OPERATIONAL | Deck Preparations | A1004 | Deck Preparations (D-ring cutting; marking, steel sets installation) - One 5t forklift and Crane required
39 | 2026-01-27 | 7:39 | 2026-01-27 | 7:41 | 00:02 HRS | 0.03 | 0 | CHA: 확인 후 안내(잠시 대기 요청) | OPERATIONAL | Deck Preparations | A1004 | Deck Preparations (D-ring cutting; marking, steel sets installation) - One 5t forklift and Crane required
40 | 2026-01-27 | 7:41 | 2026-01-27 | 7:42 | 00:01 HRS | 0.02 | 0 | Yulia: crane & forklift 8am 도착 맞나? | OPERATIONAL | Deck Preparations | A1004 | Deck Preparations (D-ring cutting; marking, steel sets installation) - One 5t forklift and Crane required
41 | 2026-01-27 | 7:42 | 2026-01-27 | 7:45 | 00:03 HRS | 0.05 | 0 | CHA: S/N 2XBR62542-T Spare | OPERATIONAL | Deck Preparations | A1004 | Deck Preparations (D-ring cutting; marking, steel sets installation) - One 5t forklift and Crane required
42 | 2026-01-27 | 7:45 | 2026-01-27 | 8:33 | 00:48 HRS | 0.8 | 0.03 | Yulia: Crane and forklift arrived on time | OPERATIONAL | Deck Preparations | A1004 | Deck Preparations (D-ring cutting; marking, steel sets installation) - One 5t forklift and Crane required
43 | 2026-01-27 | 8:33 | 2026-01-27 | 8:33 | 00:00 HRS | 0 | 0 | Yulia: Bushra는 jetty 5? other jetty? | OPERATIONAL | Deck Preparations | A1004 | Deck Preparations (D-ring cutting; marking, steel sets installation) - One 5t forklift and Crane required
44 | 2026-01-27 | 8:33 | 2026-01-27 | 8:35 | 00:02 HRS | 0.03 | 0 | 상욱: Jetty #5는 29일 loadout 필요, deck prep는 타 jetty 가능 검토 요청 | OPERATIONAL | Deck Preparations | A1004 | Deck Preparations (D-ring cutting; marking, steel sets installation) - One 5t forklift and Crane required
45 | 2026-01-27 | 8:35 | 2026-01-27 | 12:56 | 04:21 HRS | 4.35 | 0.18 | Yulia: offloading 완료, crane release. SPMT assembly/beam replacement 진행. Bushra status? | OPERATIONAL | Beam Replacement | A1002 | Beam Replacement AGI TR Unit 1 (TR Bay 4) - Two 5t forklifts required
46 | 2026-01-27 | 12:56 | 2026-01-27 | 14:20 | 01:24 HRS | 1.4 | 0.06 | Yulia: 2:30pm beam replacement 시작 예정, 2nd forklift 2:30까지 요청 + LCT ETA 요청 | OPERATIONAL | Beam Replacement | A1002 | Beam Replacement AGI TR Unit 1 (TR Bay 4) - Two 5t forklifts required
47 | 2026-01-27 | 14:20 | 2026-01-27 | 14:26 | 00:06 HRS | 0.1 | 0 | CHA: I check | OPERATIONAL | Deck Preparations | A1004 | Deck Preparations (D-ring cutting; marking, steel sets installation) - One 5t forklift and Crane required
48 | 2026-01-27 | 14:26 | 2026-01-27 | 15:29 | 01:03 HRS | 1.05 | 0.04 | Yoonus: 2nd Forklift not available today | OPERATIONAL | Deck Preparations | A1004 | Deck Preparations (D-ring cutting; marking, steel sets installation) - One 5t forklift and Crane required
49 | 2026-01-27 | 15:29 | 2026-01-27 | 15:31 | 00:02 HRS | 0.03 | 0 | Yoonus: Land PTW pending → 승인 전 SPMT 이동 금지 | OPERATIONAL | Deck Preparations | A1004 | Deck Preparations (D-ring cutting; marking, steel sets installation) - One 5t forklift and Crane required
50 | 2026-01-27 | 15:31 | 2026-01-27 | 15:38 | 00:07 HRS | 0.12 | 0.01 | 상욱: Hot work(deck prep) start 요청(접안/확보 후) | OPERATIONAL | Deck Preparations | A1004 | Deck Preparations (D-ring cutting; marking, steel sets installation) - One 5t forklift and Crane required
51 | 2026-01-27 | 15:38 | 2026-01-27 | 15:39 | 00:01 HRS | 0.02 | 0 | Yulia: laydown area, permission 없이 SPMT 이동 안함 | OPERATIONAL | Deck Preparations | A1004 | Deck Preparations (D-ring cutting; marking, steel sets installation) - One 5t forklift and Crane required
52 | 2026-01-27 | 15:39 | 2026-01-27 | 15:42 | 00:03 HRS | 0.05 | 0 | Yulia: 내일 2 forklifts booking 요청 | OPERATIONAL | Beam Replacement | A1002 | Beam Replacement AGI TR Unit 1 (TR Bay 4) - Two 5t forklifts required
53 | 2026-01-27 | 15:42 | 2026-01-27 | 15:54 | 00:12 HRS | 0.2 | 0.01 | Yoonus: 내일 몇 시? 2 forklifts만? (port advance notice 필요) | OPERATIONAL | Deck Preparations | A1004 | Deck Preparations (D-ring cutting; marking, steel sets installation) - One 5t forklift and Crane required
54 | 2026-01-27 | 15:54 | 2026-01-27 | 16:00 | 00:06 HRS | 0.1 | 0 | Yulia: 8am부터 3시간 2 forklifts + (Marine) forklift+crane+gang 8am 시작 | OPERATIONAL | Deck Preparations | A1004 | Deck Preparations (D-ring cutting; marking, steel sets installation) - One 5t forklift and Crane required
55 | 2026-01-27 | 16:00 | 2026-01-27 | 16:00 | 00:00 HRS | 0 | 0 | Yulia: Bushra Captain 정보—17:00 berth 예상 | OPERATIONAL | Deck Preparations | A1004 | Deck Preparations (D-ring cutting; marking, steel sets installation) - One 5t forklift and Crane required
56 | 2026-01-27 | 16:00 | 2026-01-27 | 16:05 | 00:05 HRS | 0.08 | 0 | Yulia: Marine crew shift 17:00 종료, deck prep 내일 아침 시작 | DEMOBILIZATION | MARINE | A2000 | Demobilization of Marine Equipment and Steelworks
57 | 2026-01-27 | 16:05 | 2026-01-27 | 16:05 | 00:00 HRS | 0 | 0 | Yoonus: port 장비 가용 확인 후 업데이트 | OPERATIONAL | Deck Preparations | A1004 | Deck Preparations (D-ring cutting; marking, steel sets installation) - One 5t forklift and Crane required
58 | 2026-01-27 | 16:05 | 2026-01-27 | 17:59 | 01:54 HRS | 1.9 | 0.08 | Yulia: Bushra berthed roro jetty 17:38 | OPERATIONAL | Deck Preparations | A1004 | Deck Preparations (D-ring cutting; marking, steel sets installation) - One 5t forklift and Crane required
59 | 2026-01-27 | 17:59 | 2026-01-27 | 18:11 | 00:12 HRS | 0.2 | 0.01 | LCT Bushra: ALL FAST SECURED MINA ZAYED RORO BERTH 27.01.2026 1738 HRS | OPERATIONAL | Deck Preparations | A1004 | Deck Preparations (D-ring cutting; marking, steel sets installation) - One 5t forklift and Crane required
60 |  |  | 2026-01-28 | 10:01 |  |  |  | Yoonus: (MZ GC Ops) 작업 완료 후 Delivery Note 작성→AD Customs 제출(출항 전) | OPERATIONAL | Deck Preparations | A1005 | Deck Preparations (Steel sets installation, welding) - Crane Required for steel sets installation
61 | 2026-01-28 | 10:01 | 2026-01-28 | 10:52 | 00:51 HRS | 0.85 | 0.04 | Yulia: crane 3시간 연장 요청 | OPERATIONAL | Deck Preparations | A1005 | Deck Preparations (Steel sets installation, welding) - Crane Required for steel sets installation
62 | 2026-01-28 | 10:52 | 2026-01-28 | 10:56 | 00:04 HRS | 0.07 | 0 | Yulia: forklift 1대 off-hire 가능, 1대는 필요 | OPERATIONAL | Deck Preparations | A1005 | Deck Preparations (Steel sets installation, welding) - Crane Required for steel sets installation
63 | 2026-01-28 | 10:56 | 2026-01-28 | 11:02 | 00:06 HRS | 0.1 | 0 | Yoonus: port 통보 후 가용 업데이트 | OPERATIONAL | Deck Preparations | A1005 | Deck Preparations (Steel sets installation, welding) - Crane Required for steel sets installation
64 | 2026-01-28 | 11:02 | 2026-01-28 | 11:20 | 00:18 HRS | 0.3 | 0.01 | Yulia: 29-01-2026 07:00 crane+1 forklift booking 요청(linkspan) | OPERATIONAL | Deck Preparations | A1005 | Deck Preparations (Steel sets installation, welding) - Crane Required for steel sets installation
65 | 2026-01-28 | 11:20 | 2026-01-28 | 11:40 | 00:20 HRS | 0.33 | 0.01 | Yoonus: crane extension port confirmed | OPERATIONAL | Deck Preparations | A1005 | Deck Preparations (Steel sets installation, welding) - Crane Required for steel sets installation
66 | 2026-01-28 | 11:40 | 2026-01-28 | 13:19 | 01:39 HRS | 1.65 | 0.07 | Yulia: SPMT scope 완료→release, Marine crew 계속 | OPERATIONAL | Deck Preparations | A1005 | Deck Preparations (Steel sets installation, welding) - Crane Required for steel sets installation
67 | 2026-01-28 | 13:19 | 2026-01-28 | 14:19 | 01:00 HRS | 1 | 0.04 | Yoonus: 16t forklift + 40t crane(65t 정비) | OPERATIONAL | Deck Preparations | A1005 | Deck Preparations (Steel sets installation, welding) - Crane Required for steel sets installation
68 | 2026-01-28 | 14:19 | 2026-01-28 | 16:56 | 02:37 HRS | 2.62 | 0.11 | Yulia: 29/30 Jan weather forecast 요청 | OPERATIONAL | Deck Preparations | A1005 | Deck Preparations (Steel sets installation, welding) - Crane Required for steel sets installation
69 | 2026-01-28 | 16:56 | 2026-01-28 | 17:10 | 00:14 HRS | 0.23 | 0.01 | Yulia: AGI berth 3 점유/기상 리스크(최악 2-Feb까지 stay) 공유 | OPERATIONAL | Beam Replacement | A1003 | Beam Replacement AGI TR Unit 2 (TR Bay 3) - Two 5t forklifts required
70 | 2026-01-28 | 17:10 | 2026-01-28 | 17:18 | 00:08 HRS | 0.13 | 0.01 | Haitham: 내일 HM linkspan F2F meeting, 11am, 참석자 SCT/MWS/MMT/OFCO | OPERATIONAL | Deck Preparations | A1005 | Deck Preparations (Steel sets installation, welding) - Crane Required for steel sets installation
71 | 2026-01-28 | 17:18 | 2026-01-28 | 17:20 | 00:02 HRS | 0.03 | 0 | Yulia: tide window 8–10am, 그럼 내일 load-out 안하나? | OPERATIONAL | Deck Preparations | A1005 | Deck Preparations (Steel sets installation, welding) - Crane Required for steel sets installation
72 | 2026-01-28 | 17:20 | 2026-01-28 | 17:22 | 00:02 HRS | 0.03 | 0 | 상욱: Not possible. Linkspan issue.. HM want certificate | OPERATIONAL | Deck Preparations | A1005 | Deck Preparations (Steel sets installation, welding) - Crane Required for steel sets installation
73 | 2026-01-28 | 17:22 | 2026-01-28 | 17:36 | 00:14 HRS | 0.23 | 0.01 | Yulia: crew standby, F2F 참석, office location 요청 | OPERATIONAL | Deck Preparations | A1005 | Deck Preparations (Steel sets installation, welding) - Crane Required for steel sets installation
74 | 2026-01-28 | 17:36 | 2026-01-28 | 17:38 | 00:02 HRS | 0.03 | 0 | OFCO: Land PTW 승인 아직(초기 승인 HM) | OPERATIONAL | Deck Preparations | A1005 | Deck Preparations (Steel sets installation, welding) - Crane Required for steel sets installation
75 | 2026-01-29 | - | 2026-01-29 | 12:29 | - | - | - | Yoonus: 오늘 작업 없음 → crane/forklift/gang release | OPERATIONAL | Beam Replacement |  | Beam Replacement
76 | 2026-01-29 | 12:29 | 2026-01-29 | 12:31 | 00:02 HRS | 0.03 | 0 | 상욱: loadout tom 9–11am, supporting docs ASAP | OPERATIONAL | Beam Replacement |  | Beam Replacement
77 | 2026-01-29 | 12:31 | 2026-01-29 | 13:31 | 01:00 HRS | 1 | 0.04 | OFCO: linkspan certificate mandatory | OPERATIONAL | Beam Replacement |  | Beam Replacement
78 | 2026-01-29 | 13:31 | 2026-01-29 | 15:05 | 01:34 HRS | 1.57 | 0.07 | Yulia: 내일 25t crane+forklift 7am booking 요청 | OPERATIONAL | Beam Replacement |  | Beam Replacement
79 | 2026-01-29 | 15:05 | 2026-01-29 | 15:07 | 00:02 HRS | 0.03 | 0 | Yoonus: booking 진행, port confirmation 회신 예정 | OPERATIONAL | Beam Replacement |  | Beam Replacement
80 | 2026-01-29 | 15:07 | 2026-01-29 | 16:28 | 01:21 HRS | 1.35 | 0.06 | Yulia: Mammoet 팀 내일 7am port 도착 | OPERATIONAL | Beam Replacement |  | Beam Replacement
81 |  |  | 2026-01-30 | 7:26 |  |  |  | Yulia: 준비 시작(steel plates installation), PTW 또는 reschedule 대기 | MOBILIZATION | JACKING EQUIPMENT, STEEL BRIDGE | A2010 | Mobilization of Jacking Equipment and Steel bridge (prior LCT's arrival to AGI with TR 1&2!))
82 | 2026-01-30 | 7:26 | 2026-01-30 | 8:40 | 01:14 HRS | 1.23 | 0.05 | Yulia: steel plates 설치 완료, linkspan ramp adjusted | OPERATIONAL | AGI TR Unit 1 | A1040 | RoRo Ramp Installation - 5t Frokift and Crane required
83 | 2026-01-30 | 8:40 | 2026-01-30 | 8:53 | 00:13 HRS | 0.22 | 0.01 | Yulia: Tide(09:00 1.97m / 10:00 2.05m / 11:00 2.04m) | OPERATIONAL | AGI TR Unit 1 | A1030 | Loading of AGI TR Unit 1 on SPMT; lashing; Shifting to Mina Zayed Port RoRo Jetty area
84 | 2026-01-30 | 8:53 | 2026-01-30 | 10:31 | 01:38 HRS | 1.63 | 0.07 | Adnoc Ouda: welding schedule/Aries witness/MWS scope 질의 시작 | OPERATIONAL | AGI TR Unit 1 | A1030 | Loading of AGI TR Unit 1 on SPMT; lashing; Shifting to Mina Zayed Port RoRo Jetty area
85 | 2026-01-30 | 10:31 | 2026-01-30 | 10:39 | 00:08 HRS | 0.13 | 0.01 | 상욱: Aries analysis done, issue는 PTW/Linkspan | OPERATIONAL | AGI TR Unit 1 | A1030 | Loading of AGI TR Unit 1 on SPMT; lashing; Shifting to Mina Zayed Port RoRo Jetty area
86 | 2026-01-30 | 10:39 | 2026-01-30 | 10:43 | 00:04 HRS | 0.07 | 0 | Adnoc Ouda: FW discharge clearance 업데이트 요청(OFCO) | OPERATIONAL | AGI TR Unit 1 | A1030 | Loading of AGI TR Unit 1 on SPMT; lashing; Shifting to Mina Zayed Port RoRo Jetty area
87 | 2026-01-30 | 10:43 | 2026-01-30 | 11:20 | 00:37 HRS | 0.62 | 0.03 | Yulia: Port Authority가 ops 불가 → linkspan removal 시작 가능 여부 문의 | OPERATIONAL | AGI TR Unit 1 | A1030 | Loading of AGI TR Unit 1 on SPMT; lashing; Shifting to Mina Zayed Port RoRo Jetty area
88 | 2026-01-30 | 11:20 | 2026-01-30 | 11:22 | 00:02 HRS | 0.03 | 0 | Capt Igor: Please share mobile of MWS | OPERATIONAL | AGI TR Unit 1 | A1030 | Loading of AGI TR Unit 1 on SPMT; lashing; Shifting to Mina Zayed Port RoRo Jetty area
89 | 2026-01-30 | 11:22 | 2026-01-30 | 11:23 | 00:01 HRS | 0.02 | 0 | CHA: Linkspan Removal - Hold until 14:00 | OPERATIONAL | AGI TR Unit 1 | A1070 | RoRo ramp removal; Seafastening AGL TR Unit 1 - Crane required
90 | 2026-01-30 | 11:23 | 2026-01-30 | 12:01 | 00:38 HRS | 0.63 | 0.03 | Yoonus: de-ballasting/tanker arrangements 승인 필요, proceed 확인 요청 | OPERATIONAL | AGI TR Unit 1 | A1030 | Loading of AGI TR Unit 1 on SPMT; lashing; Shifting to Mina Zayed Port RoRo Jetty area
91 | 2026-01-30 | 12:01 | 2026-01-30 | 12:01 | 00:00 HRS | 0 | 0 | Shariff: Ok confirmed...pls proceed | OPERATIONAL | AGI TR Unit 1 | A1030 | Loading of AGI TR Unit 1 on SPMT; lashing; Shifting to Mina Zayed Port RoRo Jetty area
92 | 2026-01-30 | 12:01 | 2026-01-30 | 12:12 | 00:11 HRS | 0.18 | 0.01 | LCT Bushra: fresh water transfer 계획/trim 목표 공유 | MOBILIZATION | JACKING EQUIPMENT, STEEL BRIDGE | A2010 | Mobilization of Jacking Equipment and Steel bridge (prior LCT's arrival to AGI with TR 1&2!))
93 | 2026-01-30 | 12:12 | 2026-01-30 | 14:54 | 02:42 HRS | 2.7 | 0.11 | LCT Bushra: FW transfer 후 trim 1m, plan 대비 0.15m 차이 | MOBILIZATION | JACKING EQUIPMENT, STEEL BRIDGE | A2010 | Mobilization of Jacking Equipment and Steel bridge (prior LCT's arrival to AGI with TR 1&2!))
94 | 2026-01-30 | 14:54 | 2026-01-30 | 15:55 | 01:01 HRS | 1.02 | 0.04 | Yoonus: port에 장비/gang release 요청 | OPERATIONAL | AGI TR Unit 1 | A1030 | Loading of AGI TR Unit 1 on SPMT; lashing; Shifting to Mina Zayed Port RoRo Jetty area
95 | 2026-01-30 | 15:55 | 2026-01-30 | 16:00 | 00:05 HRS | 0.08 | 0 | Yulia: load out 승인 시 내일 crane+forklift 필요(11–12pm 이후) | OPERATIONAL | AGI TR Unit 1 | A1060 | Load-out of AGL TR Unit 1; stool down (8am-10am)
96 | 2026-01-30 | 16:00 | 2026-01-30 | 22:10 | 06:10 HRS | 6.17 | 0.26 | Yoonus: HM/HSE/MZ Ops 승인(01st trip load), 출항 전 MWS COA 제출 조건 | OPERATIONAL | AGI TR Unit 1 | A1060 | Load-out of AGL TR Unit 1; stool down (8am-10am)
97 | 2026-01-30 | 22:10 | 2026-01-30 | 22:11 | 00:01 HRS | 0.02 | 0 | Adnoc Ouda: loading 전 MWS confirmation(Aries bow strength arrangement 정합) 필수 | OPERATIONAL | AGI TR Unit 1 | A1030 | Loading of AGI TR Unit 1 on SPMT; lashing; Shifting to Mina Zayed Port RoRo Jetty area
98 | 2026-01-30 | 22:11 | 2026-01-30 | 22:13 | 00:02 HRS | 0.03 | 0 | 상욱: loadout tomorrow morning( tide 9–11 ), MMT standby 7am | OPERATIONAL | AGI TR Unit 1 | A1030 | Loading of AGI TR Unit 1 on SPMT; lashing; Shifting to Mina Zayed Port RoRo Jetty area
99 |  |  | 2026-01-31 | 6:16 |  |  |  | CHA: MWS 08:50 Mina Port 도착 예정 | MOBILIZATION | JACKING EQUIPMENT, STEEL BRIDGE | A2010 | Mobilization of Jacking Equipment and Steel bridge (prior LCT's arrival to AGI with TR 1&2!))
100 | 2026-01-31 | 6:16 | 2026-01-31 | 7:21 | 01:05 HRS | 1.08 | 0.05 | Yulia: Please share PTW | MOBILIZATION | JACKING EQUIPMENT, STEEL BRIDGE | A2010 | Mobilization of Jacking Equipment and Steel bridge (prior LCT's arrival to AGI with TR 1&2!))
101 | 2026-01-31 | 7:21 | 2026-01-31 | 7:32 | 00:11 HRS | 0.18 | 0.01 | Yulia: HM이 MWS COA 기다림, 발급되나? | MOBILIZATION | JACKING EQUIPMENT, STEEL BRIDGE | A2010 | Mobilization of Jacking Equipment and Steel bridge (prior LCT's arrival to AGI with TR 1&2!))
102 | 2026-01-31 | 7:32 | 2026-01-31 | 7:46 | 00:14 HRS | 0.23 | 0.01 | Haitham: MWS before 9am, COA 발급 | MOBILIZATION | JACKING EQUIPMENT, STEEL BRIDGE | A2010 | Mobilization of Jacking Equipment and Steel bridge (prior LCT's arrival to AGI with TR 1&2!))
103 | 2026-01-31 | 7:46 | 2026-01-31 | 9:49 | 02:03 HRS | 2.05 | 0.09 | Yulia: mats 이동 위해 forklift 요청 | MOBILIZATION | JACKING EQUIPMENT, STEEL BRIDGE | A2010 | Mobilization of Jacking Equipment and Steel bridge (prior LCT's arrival to AGI with TR 1&2!))
104 | 2026-01-31 | 9:49 | 2026-01-31 | 9:50 | 00:01 HRS | 0.02 | 0 | Yoonus: noted, MZ GC ops에 요청 | MOBILIZATION | JACKING EQUIPMENT, STEEL BRIDGE | A2010 | Mobilization of Jacking Equipment and Steel bridge (prior LCT's arrival to AGI with TR 1&2!))
105 | 2026-01-31 | 9:50 | 2026-01-31 | 10:25 | 00:35 HRS | 0.58 | 0.02 | Yulia: HM 승인 받아 load out 시작, toolbox talk 완료 | OPERATIONAL | AGI TR Unit 1 | A1070 | RoRo ramp removal; Seafastening AGL TR Unit 1 - Crane required
106 | 2026-01-31 | 10:25 | 2026-01-31 | 10:29 | 00:04 HRS | 0.07 | 0 | Yulia: Load out started | OPERATIONAL | AGI TR Unit 1 | A1070 | RoRo ramp removal; Seafastening AGL TR Unit 1 - Crane required
107 | 2026-01-31 | 10:29 | 2026-01-31 | 10:53 | 00:24 HRS | 0.4 | 0.02 | Yulia: TR Unit 1 on LCT | MOBILIZATION | JACKING EQUIPMENT, STEEL BRIDGE | A2010 | Mobilization of Jacking Equipment and Steel bridge (prior LCT's arrival to AGI with TR 1&2!))
108 | 2026-01-31 | 10:53 | 2026-01-31 | 10:54 | 00:01 HRS | 0.02 | 0 | Yulia: linkspan ramp removal/적재 위해 crane 요청 | OPERATIONAL | AGI TR Unit 1 | A1070 | RoRo ramp removal; Seafastening AGL TR Unit 1 - Crane required
109 | 2026-01-31 | 10:54 | 2026-01-31 | 10:58 | 00:04 HRS | 0.07 | 0 | Yoonus: crane confirmed | OPERATIONAL | AGI TR Unit 1 | A1070 | RoRo ramp removal; Seafastening AGL TR Unit 1 - Crane required
110 | 2026-01-31 | 10:58 | 2026-01-31 | 11:08 | 00:10 HRS | 0.17 | 0.01 | Adnoc Ouda: 1st unit loading 축하 | OPERATIONAL | AGI TR Unit 1 | A1070 | RoRo ramp removal; Seafastening AGL TR Unit 1 - Crane required
111 | 2026-01-31 | 11:08 | 2026-01-31 | 11:09 | 00:01 HRS | 0.02 | 0 | Adnoc Ouda: AGI offloading 전 hing beam 하부 구조/용접 재확인(MWS) | MOBILIZATION | JACKING EQUIPMENT, STEEL BRIDGE | A2010 | Mobilization of Jacking Equipment and Steel bridge (prior LCT's arrival to AGI with TR 1&2!))
112 | 2026-01-31 | 11:09 | 2026-01-31 | 12:29 | 01:20 HRS | 1.33 | 0.06 | LCT Bushra: cargo manifest 요청(계산 위해) | MOBILIZATION | JACKING EQUIPMENT, STEEL BRIDGE | A2010 | Mobilization of Jacking Equipment and Steel bridge (prior LCT's arrival to AGI with TR 1&2!))
113 | 2026-01-31 | 12:29 | 2026-01-31 | 13:12 | 00:43 HRS | 0.72 | 0.03 | Yoonus: (GC Ops) crane after lunch 제공 가능 | OPERATIONAL | AGI TR Unit 1 | A1070 | RoRo ramp removal; Seafastening AGL TR Unit 1 - Crane required
114 | 2026-01-31 | 13:12 | 2026-01-31 | 14:33 | 01:21 HRS | 1.35 | 0.06 | Adnoc Ouda: sailing time/ETA 요청 | MOBILIZATION | JACKING EQUIPMENT, STEEL BRIDGE | A2010 | Mobilization of Jacking Equipment and Steel bridge (prior LCT's arrival to AGI with TR 1&2!))
115 | 2026-01-31 | 14:33 | 2026-01-31 | 14:46 | 00:13 HRS | 0.22 | 0.01 | 상욱: ETA AGI 2-Feb 계획 언급 | MOBILIZATION | JACKING EQUIPMENT, STEEL BRIDGE | A2010 | Mobilization of Jacking Equipment and Steel bridge (prior LCT's arrival to AGI with TR 1&2!))
116 | 2026-01-31 | 14:46 | 2026-01-31 | 15:15 | 00:29 HRS | 0.48 | 0.02 | OFCO: Bushra ETD 요청(다른 landing crafts 대기) | MOBILIZATION | JACKING EQUIPMENT, STEEL BRIDGE | A2010 | Mobilization of Jacking Equipment and Steel bridge (prior LCT's arrival to AGI with TR 1&2!))
117 | 2026-01-31 | 15:15 | 2026-01-31 | 16:38 | 01:23 HRS | 1.38 | 0.06 | Yulia: sea fastening done, inspection ongoing | MOBILIZATION | JACKING EQUIPMENT, STEEL BRIDGE | A2010 | Mobilization of Jacking Equipment and Steel bridge (prior LCT's arrival to AGI with TR 1&2!))
118 | 2026-01-31 | 16:38 | 2026-01-31 | 17:58 | 01:20 HRS | 1.33 | 0.06 | 상욱: manifest/COA 대기, ETD 1-Feb / ETA 2-Feb 추정 | MOBILIZATION | JACKING EQUIPMENT, STEEL BRIDGE | A2010 | Mobilization of Jacking Equipment and Steel bridge (prior LCT's arrival to AGI with TR 1&2!))
119 | 2026-01-31 | 17:58 | 2026-01-31 | 19:18 | 01:20 HRS | 1.33 | 0.06 | LCT Bushra: packing list vs draft/loaded weight match 언급 | MOBILIZATION | JACKING EQUIPMENT, STEEL BRIDGE | A2010 | Mobilization of Jacking Equipment and Steel bridge (prior LCT's arrival to AGI with TR 1&2!))
120 | 2026-01-31 | 19:18 | 2026-01-31 | 19:28 | 00:10 HRS | 0.17 | 0.01 | LCT Bushra: manifest 645t이면 draft 2.9m 예상 vs 실제 2.5m(차이 0.4m) | MOBILIZATION | JACKING EQUIPMENT, STEEL BRIDGE | A2010 | Mobilization of Jacking Equipment and Steel bridge (prior LCT's arrival to AGI with TR 1&2!))
121 | 2026-01-31 | 19:28 | 2026-01-31 | 19:47 | 00:19 HRS | 0.32 | 0.01 | 상욱: revised manifest 공유(Shipping follow-up) | MOBILIZATION | JACKING EQUIPMENT, STEEL BRIDGE | A2010 | Mobilization of Jacking Equipment and Steel bridge (prior LCT's arrival to AGI with TR 1&2!))
122 | 2026-01-31 | 19:47 | 2026-01-31 | 20:52 | 01:05 HRS | 1.08 | 0.05 | Yoonus: Vessel Bushra cast off from Mina Zayed | MOBILIZATION | JACKING EQUIPMENT, STEEL BRIDGE | A2010 | Mobilization of Jacking Equipment and Steel bridge (prior LCT's arrival to AGI with TR 1&2!))
123 | 2026-01-31 | 20:52 | 2026-01-31 | 20:53 | 00:01 HRS | 0.02 | 0 | LCT Bushra: 31/01/2026 2036 cast off, ETA AGI 01/02/2026 0700 | MOBILIZATION | JACKING EQUIPMENT, STEEL BRIDGE | A2010 | Mobilization of Jacking Equipment and Steel bridge (prior LCT's arrival to AGI with TR 1&2!))
124 | 2026-01-31 | 20:53 | 2026-01-31 | 21:18 | 00:25 HRS | 0.42 | 0.02 | Yulia: crew는 CICPA renewal로 3-Feb 이전 이동 불가 | MOBILIZATION | JACKING EQUIPMENT, STEEL BRIDGE | A2010 | Mobilization of Jacking Equipment and Steel bridge (prior LCT's arrival to AGI with TR 1&2!))
125 |  |  | 2026-02-01 | 7:42 |  |  |  | Khemlal: AGI에서는 Linkspan 외 lifting 불가(ALS LOP 범위), forklift ops 불가 | OPERATIONAL | AGI TR Unit 1 | A1081 | MWS; MPI; Sail-away - Marine Transportation by LCT to Al Ghallan Island
126 | 2026-02-01 | 7:42 | 2026-02-01 | 7:49 | 00:07 HRS | 0.12 | 0.01 | Khemlal: ADNOC approved TPC 없으면 lift 불가 | OPERATIONAL | AGI TR Unit 1 | A1081 | MWS; MPI; Sail-away - Marine Transportation by LCT to Al Ghallan Island
127 | 2026-02-01 | 7:49 | 2026-02-01 | 8:01 | 00:12 HRS | 0.2 | 0.01 | LCT Bushra: AGI anchorage 0600, waiting berthing schedule | OPERATIONAL | AGI TR Unit 1 | A1081 | MWS; MPI; Sail-away - Marine Transportation by LCT to Al Ghallan Island
128 |  |  | 2026-02-02 | 9:12 |  |  |  | 상욱: Erwin booking 확인 요청(3-Feb AM) | OPERATIONAL | AGI TR Unit 1 | A1100 | Unlashing and cutting; steel sets preparations - Forklift required
129 | 2026-02-02 | 9:12 | 2026-02-02 | 9:13 | 00:01 HRS | 0.02 | 0 | Yulia: 3rd travel 가능, CICPA pending 공유 예정 | OPERATIONAL | AGI TR Unit 1 | A1100 | Unlashing and cutting; steel sets preparations - Forklift required
130 | 2026-02-02 | 9:13 | 2026-02-02 | 9:15 | 00:02 HRS | 0.03 | 0 | 상욱: Wardeh ETA AGI today | OPERATIONAL | AGI TR Unit 1 | A1100 | Unlashing and cutting; steel sets preparations - Forklift required
131 | 2026-02-02 | 9:15 | 2026-02-02 | 9:16 | 00:01 HRS | 0.02 | 0 | 상욱: JPT62 ETA AGI 3-Feb(부분 적재) | OPERATIONAL | AGI TR Unit 1 | A1100 | Unlashing and cutting; steel sets preparations - Forklift required
132 | 2026-02-02 | 9:16 | 2026-02-02 | 9:56 | 00:40 HRS | 0.67 | 0.03 | PTR 담당: passengers booked 후 PTR 발송 | OPERATIONAL | AGI TR Unit 1 | A1100 | Unlashing and cutting; steel sets preparations - Forklift required
133 | 2026-02-02 | 9:56 | 2026-02-02 | 10:16 | 00:20 HRS | 0.33 | 0.01 | Yulia: Lifting clamps loaded onto LCT JPT62 | OPERATIONAL | AGI TR Unit 1 | A1091 | LCT Arrival; Berthing at AGL RoRo Jetty
134 | 2026-02-02 | 10:16 | 2026-02-02 | 10:17 | 00:01 HRS | 0.02 | 0 | 상욱: ETA MZP 5 or 6, 내일 업데이트 | OPERATIONAL | AGI TR Unit 1 | A1100 | Unlashing and cutting; steel sets preparations - Forklift required
135 | 2026-02-02 | 10:17 | 2026-02-02 | 10:18 | 00:01 HRS | 0.02 | 0 | OFCO: Linkspan certificate very important | OPERATIONAL | AGI TR Unit 1 | A1100 | Unlashing and cutting; steel sets preparations - Forklift required
136 | 2026-02-02 | 10:18 | 2026-02-02 | 10:18 | 00:00 HRS | 0 | 0 | Yulia: 2 beams load test today and tomorrow | OPERATIONAL | AGI TR Unit 1 | A1100 | Unlashing and cutting; steel sets preparations - Forklift required
137 |  |  | 2026-02-04 | 12:22 |  |  |  | 상욱: MUS.0521 | OPERATIONAL | AGI TR Unit 1 | A1140 | AGL TR Unit 1 (TR Bay 4) load on SPMT; lashing; Transportation and JD (steel set to be delivered to bay area by trailer)
138 | 2026-02-04 | 12:22 | 2026-02-04 | 17:35 | 05:13 HRS | 5.22 | 0.22 | Yulia: Wardeh ETA AGI 문의 | OPERATIONAL | AGI TR Unit 1 | A1140 | AGL TR Unit 1 (TR Bay 4) load on SPMT; lashing; Transportation and JD (steel set to be delivered to bay area by trailer)
139 | 2026-02-04 | 17:35 | 2026-02-04 | 17:35 | 00:00 HRS | 0 | 0 | 상욱: Onsite.yesterday | OPERATIONAL | AGI TR Unit 1 | A1140 | AGL TR Unit 1 (TR Bay 4) load on SPMT; lashing; Transportation and JD (steel set to be delivered to bay area by trailer)
140 | 2026-02-04 | 17:35 | 2026-02-04 | 17:36 | 00:01 HRS | 0.02 | 0 | 상욱: JPT62 ETA 20:30 today, onsite tomorrow morning | OPERATIONAL | AGI TR Unit 1 | A1140 | AGL TR Unit 1 (TR Bay 4) load on SPMT; lashing; Transportation and JD (steel set to be delivered to bay area by trailer)
141 | 2026-02-04 | 17:36 | 2026-02-04 | 19:56 | 02:20 HRS | 2.33 | 0.1 | LCT Bushra: AGI West RORO berth 3 alongside 1606 | OPERATIONAL | AGI TR Unit 1 | A1121 | LCT Sails back to MZP to collect TR Unit 1
142 |  |  | 2026-02-05 | 7:59 |  |  |  | LCT Bushra: AGI port meeting onboard 요청(아침) | OPERATIONAL | AGI TR Unit 2 | A2029 | LCT Arrives at MZP; Deck preparations
143 | 2026-02-05 | 7:59 | 2026-02-05 | 8:00 | 00:01 HRS | 0.02 | 0 | Khemlal: Any specific time? | MOBILIZATION | SPMT | A1010 | Mobilization of 2nd set of SPMT; Assembly + Function test
144 | 2026-02-05 | 8:00 | 2026-02-05 | 8:05 | 00:05 HRS | 0.08 | 0 | Khemlal: Electrical/MMT 08:30 참석 | MOBILIZATION | SPMT | A1010 | Mobilization of 2nd set of SPMT; Assembly + Function test
145 | 2026-02-05 | 8:05 | 2026-02-05 | 12:52 | 04:47 HRS | 4.78 | 0.2 | Adnoc Ouda: TR1 offloading 시작/ETD back/2nd TR loading 일정 질의 | OPERATIONAL | AGI TR Unit 2 | A2029 | LCT Arrives at MZP; Deck preparations
146 | 2026-02-05 | 12:52 | 2026-02-05 | 13:07 | 00:15 HRS | 0.25 | 0.01 | 상욱: Loadin plan tomorrow, ETD 6/ETA 7, TR2 loadout 8~9 Feb(계획) | MOBILIZATION | SPMT | A1010 | Mobilization of 2nd set of SPMT; Assembly + Function test
147 | 2026-02-05 | 13:07 | 2026-02-05 | 13:11 | 00:04 HRS | 0.07 | 0 | Yoonus: 다음 TR 문서(Ramp cert/Hotwork/Overwater 등) 미수령 | OPERATIONAL | AGI TR Unit 2 | A2029 | LCT Arrives at MZP; Deck preparations
148 | 2026-02-05 | 13:11 | 2026-02-05 | 13:12 | 00:01 HRS | 0.02 | 0 | Yulia: 날짜만 변경해서 재제출 가능? | MOBILIZATION | SPMT | A1010 | Mobilization of 2nd set of SPMT; Assembly + Function test
149 | 2026-02-05 | 13:12 | 2026-02-05 | 13:13 | 00:01 HRS | 0.02 | 0 | Yoonus: 가능, permit duration(며칠) 필요 | MOBILIZATION | SPMT | A1010 | Mobilization of 2nd set of SPMT; Assembly + Function test
150 | 2026-02-05 | 13:13 | 2026-02-05 | 13:14 | 00:01 HRS | 0.02 | 0 | Yulia: safe side 1 week permit | MOBILIZATION | SPMT | A1010 | Mobilization of 2nd set of SPMT; Assembly + Function test
151 | 2026-02-05 | 13:14 | 2026-02-05 | 13:14 | 00:00 HRS | 0 | 0 | Yulia: linkspan certificate 제출 예정(Inspector 공유 대기) | MOBILIZATION | SPMT | A1010 | Mobilization of 2nd set of SPMT; Assembly + Function test
152 | 2026-02-05 | 13:14 | 2026-02-05 | 16:47 | 03:33 HRS | 3.55 | 0.15 | Yoonus: pre-ops meeting scheduled(06-Feb 15:00) | MOBILIZATION | SPMT | A1010 | Mobilization of 2nd set of SPMT; Assembly + Function test
153 | 2026-02-05 | 16:47 | 2026-02-05 | 16:59 | 00:12 HRS | 0.2 | 0.01 | Yoonus: updated MOS/RA + tide window 요청 | MOBILIZATION | SPMT | A1010 | Mobilization of 2nd set of SPMT; Assembly + Function test
154 | 2026-02-05 | 16:59 | 2026-02-05 | 17:32 | 00:33 HRS | 0.55 | 0.02 | Yulia: 내일 아침 MOS/RA 전달 예정 | MOBILIZATION | SPMT | A1010 | Mobilization of 2nd set of SPMT; Assembly + Function test
155 | 2026-02-05 | 17:32 | 2026-02-05 | 17:33 | 00:01 HRS | 0.02 | 0 | Yulia: ADNOC office Fri–Sun off, approval 지연 우려 | MOBILIZATION | SPMT | A1010 | Mobilization of 2nd set of SPMT; Assembly + Function test
156 |  |  | 2026-02-06 | 9:00 |  |  |  | 상욱: Pls send email.. | OPERATIONAL | AGI TR Unit 2 | A2030 | Loading of AGI TR Unit 2 on SPMT; lashing; Shifting to Mina Zayed Port RoRo Jetty area
157 | 2026-02-06 | 9:00 | 2026-02-06 | 9:07 | 00:07 HRS | 0.12 | 0.01 | Yulia: done | OPERATIONAL | AGI TR Unit 2 | A2030 | Loading of AGI TR Unit 2 on SPMT; lashing; Shifting to Mina Zayed Port RoRo Jetty area
158 | 2026-02-06 | 9:07 | 2026-02-06 | 9:37 | 00:30 HRS | 0.5 | 0.02 | LCT Bushra: offloading plan today? high tide 15:00–16:00 | OPERATIONAL | AGI TR Unit 2 | A2030 | Loading of AGI TR Unit 2 on SPMT; lashing; Shifting to Mina Zayed Port RoRo Jetty area
159 | 2026-02-06 | 9:37 | 2026-02-06 | 10:29 | 00:52 HRS | 0.87 | 0.04 | Yoonus: 2nd TR cargo manifest forward 요청 | OPERATIONAL | AGI TR Unit 2 | A2030 | Loading of AGI TR Unit 2 on SPMT; lashing; Shifting to Mina Zayed Port RoRo Jetty area
160 | 2026-02-06 | 10:29 | 2026-02-06 | 14:44 | 04:15 HRS | 4.25 | 0.18 | Yoonus: 2nd TR BOE copy 요청 | OPERATIONAL | AGI TR Unit 1 | A1181 | SPMT shifting back to Port
161 | 2026-02-06 | 14:44 | 2026-02-06 | 14:46 | 00:02 HRS | 0.03 | 0 | Yoonus: Bushra updated ETA MZP? | OPERATIONAL | AGI TR Unit 2 | A2030 | Loading of AGI TR Unit 2 on SPMT; lashing; Shifting to Mina Zayed Port RoRo Jetty area
162 | 2026-02-06 | 14:46 | 2026-02-06 | 14:52 | 00:06 HRS | 0.1 | 0 | 상욱: tentative ETA 8 or 9 Feb | OPERATIONAL | AGI TR Unit 2 | A2030 | Loading of AGI TR Unit 2 on SPMT; lashing; Shifting to Mina Zayed Port RoRo Jetty area
163 | 2026-02-06 | 14:52 | 2026-02-06 | 14:52 | 00:00 HRS | 0 | 0 | LCT Bushra: TR2 ramp door damage risk 언급(step 4&5) | OPERATIONAL | AGI TR Unit 2 | A2040 | RoRo Ramp Installation - 5t Frokift and Crane required
164 | 2026-02-06 | 14:52 | 2026-02-06 | 14:54 | 00:02 HRS | 0.03 | 0 | Yulia: Engineer Sayeed Ahmed와 논의 요청(+971 58 680 5307) | OPERATIONAL | AGI TR Unit 2 | A2030 | Loading of AGI TR Unit 2 on SPMT; lashing; Shifting to Mina Zayed Port RoRo Jetty area
165 | 2026-02-06 | 14:54 | 2026-02-06 | 14:59 | 00:05 HRS | 0.08 | 0 | LCT Bushra: Ok will try to contact | OPERATIONAL | AGI TR Unit 2 | A2030 | Loading of AGI TR Unit 2 on SPMT; lashing; Shifting to Mina Zayed Port RoRo Jetty area
166 | 2026-02-06 | 14:59 | 2026-02-06 | 15:32 | 00:33 HRS | 0.55 | 0.02 | Yoonus: meeting rescheduled to 09-Feb 11:00 | OPERATIONAL | AGI TR Unit 2 | A2030 | Loading of AGI TR Unit 2 on SPMT; lashing; Shifting to Mina Zayed Port RoRo Jetty area
167 |  |  | 2026-02-07 | 8:47 |  |  |  | 상욱: AGI 1st TR loading commenced. MZP 2nd loadout plan 10-Feb | OPERATIONAL | AGI TR Unit 2 | A2060 | RoRo ramp removal; Seafastening AGL TR Unit 2 - Crane required
168 |  |  | 2026-02-08 | 11:00 |  |  |  | 상욱: AGI 1st TR offloading completed. cast off around 2pm | OPERATIONAL | AGI TR Unit 1 | A1150 | Jacking down of AGI TR Unit 1 (TR Bay 4) on temporary support - Forklift required
169 | 2026-02-08 | 11:00 | 2026-02-08 | 11:04 | 00:04 HRS | 0.07 | 0 | 상욱: TR2 loadout plan(MZP) 09-Feb FRA/PTW, 10-Feb loadout/sea fastening/MWS | OPERATIONAL | AGI TR Unit 2 | A2070 | MWS; MPI; Sail-away - Marine Transportation by LCT to Al Ghallan Island
170 | 2026-02-08 | 11:04 | 2026-02-08 | 12:46 | 01:42 HRS | 1.7 | 0.07 | Shariff: ETD 1600 today, ETA MZP 0300 09-Feb | OPERATIONAL | AGI TR Unit 1 | A1150 | Jacking down of AGI TR Unit 1 (TR Bay 4) on temporary support - Forklift required
171 | 2026-02-08 | 12:46 | 2026-02-08 | 12:49 | 00:03 HRS | 0.05 | 0 | 상욱: Berth request 09–11 Feb pls | OPERATIONAL | AGI TR Unit 1 | A1150 | Jacking down of AGI TR Unit 1 (TR Bay 4) on temporary support - Forklift required
172 | 2026-02-08 | 12:49 | 2026-02-08 | 13:38 | 00:49 HRS | 0.82 | 0.03 | +971 56 898 7173: AGI transformer offloading completed, FRA 승인 기반 운송 예정 | OPERATIONAL | AGI TR Unit 1 | A1150 | Jacking down of AGI TR Unit 1 (TR Bay 4) on temporary support - Forklift required
173 | 2026-02-08 | 13:38 | 2026-02-08 | 15:05 | 01:27 HRS | 1.45 | 0.06 | 상욱: ATD 1500, ETA MZP 0100 | OPERATIONAL | AGI TR Unit 1 | A1150 | Jacking down of AGI TR Unit 1 (TR Bay 4) on temporary support - Forklift required
174 | 2026-02-08 | 15:05 | 2026-02-08 | 16:17 | 01:12 HRS | 1.2 | 0.05 | Yulia: 내일 90t crane+forklift+gang booking 요청(11am/2pm) | OPERATIONAL | AGI TR Unit 1 | A1150 | Jacking down of AGI TR Unit 1 (TR Bay 4) on temporary support - Forklift required
175 | 2026-02-08 | 16:17 | 2026-02-08 | 16:25 | 00:08 HRS | 0.13 | 0.01 | Yoonus: 투입 구역(yard/berth5) + forklift capacity 확인 요청 | OPERATIONAL | AGI TR Unit 1 | A1150 | Jacking down of AGI TR Unit 1 (TR Bay 4) on temporary support - Forklift required
176 | 2026-02-08 | 16:25 | 2026-02-08 | 16:29 | 00:04 HRS | 0.07 | 0 | Yoonus: yard or berth #5? | OPERATIONAL | AGI TR Unit 1 | A1150 | Jacking down of AGI TR Unit 1 (TR Bay 4) on temporary support - Forklift required
177 | 2026-02-08 | 16:29 | 2026-02-08 | 16:41 | 00:12 HRS | 0.2 | 0.01 | Yulia: SPMT는 laydown, marine eq는 상황 따라 berth5/laydown, 10t forklift 충분 | OPERATIONAL | AGI TR Unit 1 | A1150 | Jacking down of AGI TR Unit 1 (TR Bay 4) on temporary support - Forklift required
178 | 2026-02-08 | 16:41 | 2026-02-08 | 17:32 | 00:51 HRS | 0.85 | 0.04 | Yoonus: MZP Berth #5 내일 저녁 가용 | OPERATIONAL | AGI TR Unit 1 | A1150 | Jacking down of AGI TR Unit 1 (TR Bay 4) on temporary support - Forklift required
179 | 2026-02-08 | 17:32 | 2026-02-08 | 18:36 | 01:04 HRS | 1.07 | 0.04 | LCT Bushra: Bushra plan? other berth or drop anchor? (provision/water 부족) | OPERATIONAL | AGI TR Unit 2 | A2070 | MWS; MPI; Sail-away - Marine Transportation by LCT to Al Ghallan Island
180 | 2026-02-08 | 18:36 | 2026-02-08 | 18:38 | 00:02 HRS | 0.03 | 0 | LCT Bushra: CAST OFF AGI 1438, ETA MZP 09-Feb 0100 | OPERATIONAL | AGI TR Unit 2 | A2070 | MWS; MPI; Sail-away - Marine Transportation by LCT to Al Ghallan Island
181 | 2026-02-08 | 18:38 | 2026-02-08 | 18:42 | 00:04 HRS | 0.07 | 0 | 상욱: ETA 0100, provision/drinking water 위해 가능한 jetty 문의 | OPERATIONAL | AGI TR Unit 1 | A1150 | Jacking down of AGI TR Unit 1 (TR Bay 4) on temporary support - Forklift required
182 | 2026-02-08 | 18:42 | 2026-02-08 | 20:28 | 01:46 HRS | 1.77 | 0.07 | Yoonus: 대안 jetty 없음, port authorities와 follow-up | OPERATIONAL | AGI TR Unit 1 | A1150 | Jacking down of AGI TR Unit 1 (TR Bay 4) on temporary support - Forklift required
183 | 2026-02-08 | 20:28 | 2026-02-08 | 23:09 | 02:41 HRS | 2.68 | 0.11 | LCT Bushra: drop anchor at MZP anchorage 2242hrs | OPERATIONAL | AGI TR Unit 2 | A2070 | MWS; MPI; Sail-away - Marine Transportation by LCT to Al Ghallan Island

## WA EVENT
NO | START DATE | START TIME | END DATE | END TIME | DURATION TIMES | DURATION HRS | DURATION DAYS | Activity | LEVEL 1 | LEVEL 2 | ACTIVITY ID | ACTIVITY NAME
1 | - | - | - | - | - | - | - | MZP Load-out readiness 합의 요약(Deck prep 27–28 Jan, Load-out target 29 Jan AM, Tide≥2.00m, 자원 24h 사전요청, tug/TBC, Ramp certificate 필요 가능)
2 | 2026-01-24 | 11:34 | 2026-01-25 | 8:54 | 21:20 HRS | 21.33 | 0.89 | LCT Bushra Musaffah short stay drop anchor | MOBILIZATION | SPMT | A1000 | Mobilization of 1st set of SPMT; Asembly + Function Test
3 | 2026-01-25 | 8:54 | 2026-01-25 | 9:11 | 00:17 HRS | 0.28 | 0.01 | Capt Igor: Samsung agent가 MZP berth arrange 전까지 anchorage 대기 | OPERATIONAL | Deck Preparations | A1004 | Deck Preparations (D-ring cutting; marking, steel sets installation) - One 5t forklift and Crane required
4 | 2026-01-25 | 9:11 | 2026-01-26 | 10:03 | 24:52 HRS | 24.87 | 1.04 | ADNOC Ouda: Bushra MZP 도착 시점 문의(27 Jan?) | MOBILIZATION | SPMT | A1000 | Mobilization of 1st set of SPMT; Asembly + Function Test
5 | 2026-01-26 | 10:03 | 2026-01-26 | 10:12 | 00:09 HRS | 0.15 | 0.01 | CHA: Bushra MZP 도착 목표 2026-01-27 08:00 | MOBILIZATION | SPMT | A1000 | Mobilization of 1st set of SPMT; Asembly + Function Test
6 | 2026-01-26 | 10:12 | 2026-01-26 | 10:14 | 00:02 HRS | 0.03 | 0 | ADNOC Ouda: Bushra 27 Jan 08:00 도착 준비 지시(berth/pilot/agent) | MOBILIZATION | SPMT | A1000 | Mobilization of 1st set of SPMT; Asembly + Function Test
7 | 2026-01-26 | 10:14 | 2026-01-26 | 10:22 | 00:08 HRS | 0.13 | 0.01 | Yoonus: Ramp certificates ASAP 요청 | MOBILIZATION | SPMT | A1000 | Mobilization of 1st set of SPMT; Asembly + Function Test
8 | 2026-01-26 | 10:22 | 2026-01-26 | 16:19 | 05:57 HRS | 5.95 | 0.25 | Yoonus: labour+forklift 현장 투입(감독 번호 공유) — Mammoet 장비 offload 지원 | MOBILIZATION | SPMT | A1000 | Mobilization of 1st set of SPMT; Asembly + Function Test
9 | 2026-01-26 | 16:19 | 2026-01-26 | 17:33 | 01:14 HRS | 1.23 | 0.05 | Yoonus: 27-Jan 장비/갱 booking request 제출(크레인/포크리프트/갱) | MOBILIZATION | SPMT | A1000 | Mobilization of 1st set of SPMT; Asembly + Function Test
10 | 2026-01-26 | 17:33 | 2026-01-26 | 17:34 | 00:01 HRS | 0.02 | 0 | Yoonus: RORO jetty approval 대기 | MOBILIZATION | SPMT | A1000 | Mobilization of 1st set of SPMT; Asembly + Function Test
11 | 2026-01-26 | 17:34 | 2026-01-27 | 15:31 | 21:57 HRS | 21.95 | 0.91 | Yoonus: Land PTW 승인 pending — SPMT yard→jetty 이동 금지 | MOBILIZATION | SPMT | A1000 | Mobilization of 1st set of SPMT; Asembly + Function Test
12 | 2026-01-27 | 15:31 | 2026-01-27 | 17:38 | 02:07 HRS | 2.12 | 0.09 | LCT Bushra: MZP RORO Berth 접안(ALL FAST SECURED 1738) | OPERATIONAL | Deck Preparations | A1004 | Deck Preparations (D-ring cutting; marking, steel sets installation) - One 5t forklift and Crane required
13 | 2026-01-27 | 17:38 | 2026-01-28 | 10:01 | 16:23 HRS | 16.38 | 0.68 | Yoonus: Ops 완료 후 Delivery Note 작성→AD Customs 제출(출항 전) 지시 | OPERATIONAL | Deck Preparations | A1004 | Deck Preparations (D-ring cutting; marking, steel sets installation) - One 5t forklift and Crane required
14 | 2026-01-28 | 10:01 | 2026-01-28 | 17:22 | 07:21 HRS | 7.35 | 0.31 | 상욱: Linkspan issue로 HM이 certificate 요구 → 내일 load-out 불가(“Not possible”) | OPERATIONAL | Deck Preparations | A1005 | Deck Preparations (Steel sets installation, welding) - Crane Required for steel sets installation
15 | 2026-01-28 | 17:22 | 2026-01-29 | 13:31 | 20:09 HRS | 20.15 | 0.84 | OFCO: linkspan certificate mandatory 통보 | OPERATIONAL | Deck Preparations | A1005 | Deck Preparations (Steel sets installation, welding) - Crane Required for steel sets installation
16 | 2026-01-29 | 13:31 | 2026-01-30 | 8:53 | 19:22 HRS | 19.37 | 0.81 | Yulia: Tide 정보 공유(09:00 1.97m / 10:00 2.05m / 11:00 2.04m) | OPERATIONAL | Beam Replacement |  | Beam Replacement
17 | 2026-01-30 | 8:53 | 2026-01-30 | 22:10 | 13:17 HRS | 13.28 | 0.55 | Yoonus: HM/HSE/MZ Ops 승인(01st trip load), 출항 전 MWS COA 제출 조건 | OPERATIONAL | AGI TR Unit 1 | A1060 | Load-out of AGL TR Unit 1; stool down (8am-10am)
18 | 2026-01-30 | 22:10 | 2026-01-31 | 6:16 | 08:06 HRS | 8.1 | 0.34 | CHA: MWS 08:50 도착 예정 공지 | OPERATIONAL | AGI TR Unit 1 | A1030 | Loading of AGI TR Unit 1 on SPMT; lashing; Shifting to Mina Zayed Port RoRo Jetty area
19 | 2026-01-31 | 6:16 | 2026-01-31 | 10:25 | 04:09 HRS | 4.15 | 0.17 | Yulia: HM 승인 받아 load-out start 가능(PTW/Toolbox talk 완료) | OPERATIONAL | AGI TR Unit 1 | A1070 | RoRo ramp removal; Seafastening AGL TR Unit 1 - Crane required
20 | 2026-01-31 | 10:25 | 2026-01-31 | 10:53 | 00:28 HRS | 0.47 | 0.02 | Yulia: TR Unit 1 on LCT (load-out 완료) | OPERATIONAL | AGI TR Unit 1 | A1070 | RoRo ramp removal; Seafastening AGL TR Unit 1 - Crane required
21 | 2026-01-31 | 10:53 | 2026-01-31 | 20:53 | 10:00 HRS | 10 | 0.42 | LCT Bushra: 2036 cast off MZP, ETA AGI 01-Feb 07:00 | MOBILIZATION | JACKING EQUIPMENT, STEEL BRIDGE | A2010 | Mobilization of Jacking Equipment and Steel bridge (prior LCT's arrival to AGI with TR 1&2!))
22 | 2026-01-31 | 20:53 | 2026-02-01 | 6:00 | 09:07 HRS | 9.12 | 0.38 | LCT Bushra: AGI anchorage drop anchor 0600, waiting berthing schedule | MOBILIZATION | JACKING EQUIPMENT, STEEL BRIDGE | A2010 | Mobilization of Jacking Equipment and Steel bridge (prior LCT's arrival to AGI with TR 1&2!))
23 | 2026-02-01 | 6:00 | 2026-02-04 | 16:06 | 82:06 HRS | 82.1 | 3.42 | LCT Bushra: AGI West RORO Berth 3 alongside 1606 | OPERATIONAL | AGI TR Unit 1 | A1081 | MWS; MPI; Sail-away - Marine Transportation by LCT to Al Ghallan Island
24 | 2026-02-04 | 16:06 | 2026-02-08 | 14:38 | 94:32 HRS | 94.53 | 3.94 | LCT Bushra: cast off AGI 1438, ETA MZP 09-Feb 01:00 | OPERATIONAL | AGI TR Unit 1 | A1121 | LCT Sails back to MZP to collect TR Unit 1
25 | 2026-02-08 | 14:38 | 2026-02-08 | 22:42 | 08:04 HRS | 8.07 | 0.34 | LCT Bushra: MZP anchorage drop anchor 2242 | OPERATIONAL | AGI TR Unit 2 | A2070 | MWS; MPI; Sail-away - Marine Transportation by LCT to Al Ghallan Island