## 0_README
AGI Delay Analysis / SSOT v1.1 — Excel Extension v3.0 Template
Timezone (LT): Asia/Dubai
DateTime format: YYYY-MM-DD HH:MM (LT); if UTC needed, use separate *_UTC columns.
Principle: Event → Segment → Window → Cause → Evidence traceability.
CORE sheets: 8~13, ADV sheets: 14~18 (optional).

## 1_SSOT_INPUTS
Param | Value | Unit | Notes | Source
-- Recommended Params (fill blanks) --
TZ | Asia/Dubai | LT |  | User
WIND_MAX_KT |  | kt | Gate threshold
WAVE_MAX_FT |  | ft | Gate threshold
VIS_MIN_M |  | m | Gate threshold
AGI_OPS_ASSUME_DAYS | 2.00 | days | Use only if S4 missing | Assumption
EVID_W_OFFICIAL | 3.00 |  |  | SSOT
EVID_W_AIS | 2.00 |  |  | SSOT
EVID_W_CHAT | 1.00 |  |  | SSOT

## 8_EVENT_MAP
EventKey | EventName | SegmentID | SegmentName | TR | Planned_TS | Actual_TS | EvidenceID_Primary

## 9_SEGMENT_DELTA_TR1-TR3
TR | SegmentID | Plan_Start | Plan_End | Actual_Start | Actual_End | Plan_Dur_h | Actual_Dur_h | ΔDur_h | Driver_Top1 | EvidenceID_Top

## 10_EVIDENCE_LOG
EvidenceID | TR | TS_LT | WindowID | CauseCode | SourceType | SourceName | LocationRef | Excerpt | Weight | Reliability | LinkOrFile | Notes

## 11_CAUSE_TAXONOMY
CauseCode | Category6M | ShortDesc | TypicalGate | DefaultLikelihood | Notes
WX_FOG | Environment | Dense fog / low visibility | VIS_MIN_M | 0.20
WX_WIND | Environment | Strong wind / gust | WIND_MAX_KT | 0.20
WX_WAVE | Environment | High wave / sea state | WAVE_MAX_FT | 0.15
BERTH_OCCUPIED | Method | Berth occupied / allocation |  | 0.15
PILOT_DELAY | Man | Pilot delay |  | 0.10
DOC_PTW | Method | PTW / permit delay |  | 0.10
DOC_MWS | Method | Survey/MWS delay |  | 0.05
EQUIP_LINKSPAN | Machine | Linkspan constraint |  | 0.05
EQUIP_SPMT | Machine | SPMT constraint |  | 0.05
SAFETY_STOP | Method | Safety stop / hold point |  | 0.05

## 12_GATE_EVAL
GateID | GateValue | EventTS | METAR_Wind_kt | METAR_Gust_kt | METAR_Vis_m | NCM_Wind_kt | NCM_Wave_ft | Verdict | EvidenceID

## 13_WINDOWS_ANALYSIS
WindowID | TR | Start_LT | End_LT | ΔDelay_h | TopCause1 | TopCause2 | EvidenceIDs | MethodTag

## 14_5WHY_TR2_TR3
TR | Symptom | Why1 | Why2 | Why3 | Why4 | Why5 | RootCause | Countermeasure | EvidenceIDs

## 15_FISHBONE_6M
TR | Effect | Man | Machine | Method | Material | Measurement | Environment | EvidenceIDs

## 16_BUTFOR_SCENARIOS
ScenarioID | TR | RemoveCauseCode | Recalc_ETD | Recalc_JD | ΔFinish_days | MethodRef | Notes

## 17_QSRA_INPUTS
SegmentID | DistType | P50_h | P80_h | P90_h | Min_h | Max_h | SeasonalityFactor

## 18_QSRA_OUTPUT
TR | Finish_P50 | Finish_P80 | Finish_P90 | Buffer_for_P80_days