## _LISTS (hidden)
Lists for Data Validation (do not edit)
SourceType | OFFICIAL | AIS | CHAT | DOC | OTHER
Reliability | HIGH | MED | LOW
Verdict | OK | LIMIT | FAIL | VERIFY
DistType | NORM | TRI | LOGN | EMPIRICAL
Category6M | Man | Machine | Method | Material | Measurement | Environment

## 0_README
AGI TR Delay Analysis Template v3.0 (Blank) — SSOT + Evidence QA + Forensic + QSRA
How to use
1) Fill YELLOW cells only. 2) Use LT(UTC+4). 3) Every claim links EvidenceID. 4) Use Segment+Windows+GateEval.
Key references
AACEI 29R-03; SCL Protocol; ASQ Fishbone; PSNet 5-Whys caution; NOAA METAR decode key.
Version | v3.0
Generated | 2026-02-18 00:32

## 1_SSOT_INPUTS
SSOT Inputs (fill yellow)
Param | Value | Unit | Notes | Source | Owner | Required(Y/N) | Default
TZ | Asia/Dubai |  | Timezone | SSOT | SCT | Y | Asia/Dubai
TR3_ETD_LT |  | LT | User fixed ETD | Ops | SCT | Y | 2026-02-19 03:00
WIND_MAX_KT | 15 | kt | Stop if > | HM/HSE | Port | Y | 15.00
WAVE_MAX_FT |  | ft | Stop if > (if used) | NCM | Marine | N
VIS_MIN_M |  | m | Stop if < (fog) | METAR | Marine | N
AGI_OPS_ASSUME_DAYS | 2 | days | Assumption if missing actual | Origin | SCT | Y | 2.00
EVID_W_OFFICIAL | 3 |  | Evidence weight | Rule | SCT | Y | 3
EVID_W_AIS | 2 |  | Evidence weight | Rule | SCT | Y | 2
EVID_W_CHAT | 1 |  | Evidence weight | Rule | SCT | Y | 1
FORECAST_SAMPLES_N | 5000 |  | MonteCarlo samples | Rule | SCT | N | 5000

## 2_ACTUAL_MILESTONES
Actual Milestones (TR1-TR7)
TR | EventKey | EventName | TS_LT | TS_UTC | Location | SourceType | EvidenceID | Notes

## 3_ORIGINAL_PLAN
Original Plan
TR | EventKey | Planned_TS | Planned_Duration_h | Baseline_Source | Notes

## 4_DELAY_ANALYSIS_TR1-TR3
Delay Analysis (TR1-TR3)
TR | Milestone | Planned_TS | Actual_TS | ΔDays | ΔHours | PrimaryCause | EvidenceID | Remarks

## 9_SEGMENT_DELTA_TR1-TR3
Segment Delta TR1-TR3
TR | SegmentID | Plan_Start | Plan_End | Actual_Start | Actual_End | Plan_Dur_h | Actual_Dur_h | ΔDur_h | Driver_Top1 | EvidenceID_Top

## 10_EVIDENCE_LOG
Evidence Log
EvidenceID | TR | TS_LT | WindowID | CauseCode | SourceType | SourceName | LocationRef | Excerpt | Weight | Reliability | LinkOrFile | Notes

## 12_GATE_EVAL
Gate Eval
GateID | GateValue | EventTS | METAR_Wind_kt | METAR_Gust_kt | METAR_Vis_m | NCM_Wind_kt | NCM_Wave_ft | Verdict | EvidenceID