## 00_README
AGI TR1~TR7 Schedule / Delay Analysis (WA 기반) - v2
SSOT (Single Source of Truth)
- Baseline 일정: agi tr origin schedule.json (Origin Plan) + agi tr final schedule_backup_20260128.json (Final Plan)
- Actual 증빙: WhatsApp export (‎AGI.TR Operation님과의 WhatsApp 대화.txt) 내 타임스탬프/선장 리포트
핵심 가정(요약)
- TR3 MZP 출항(ETD): 2026-02-19 03:00 (User instruction)
- AGI 작업기간(Load-in 포함): 2.00 days (Origin 일정 가정)
- TR4~TR7: TR1~TR3 실적 평균치 기반으로 MZP Turn(접안~출항) + Return-to-Secure(AGI 출항~MZP 접안) 반영
주의
- 본 파일의 일부 날짜/시간은 WhatsApp 메시지 기반이며, 항만/선박 트래킹 사이트 공식 로그와 100% 일치하지 않을 수 있음
- TR4~TR7는 '평균치 기반 Forecast'로, 실제 기상/선석/통관/작업준비 상태에 따라 변동 가능

## 01_Assumptions
Parameter | Value | Notes
TR3_ETD_MZP (assumed) | 2026-02-19 03:00 | User instruction
AGI_ops_days (Load-in 포함) | 2 | Origin schedule assumption
Sail_time_avg_days (MZP->AGI) | 0.40417 | Avg of TR1~TR2 actual (from Events sheet)
Return_to_secure_avg_days (AGI CastOff -> next MZP Secured) | 2.6118 | Avg of TR1~TR2 (from Events sheet)
MZP_turn_avg_days (MZP Secured -> ETD) | 2.7954 | Avg of TR1~TR3 (from Events sheet)

## 02_TR1-3_Events
Trip | MZP_ETA | MZP_Secured | MZP_ETD | AGI_ETA_or_Anchor | AGI_Secured | AGI_CastOff_Return | Next_MZP_Secured | MZP_Wait_days | MZP_Turn_days | Sail_MZP_to_AGI_hr | Return_to_Secure_days | MZP_Total_Turn_incl_Wait_days
TR1 |  | 2026-01-27 17:38 | 2026-01-31 20:36 | 2026-02-01 06:00 | 2026-02-04 16:06 | 2026-02-08 14:38 | 2026-02-09 21:18 |  | 4.1236 | 9.4 | 1.2778
TR2 | 2026-02-09 01:00 | 2026-02-09 21:18 | 2026-02-12 15:00 | 2026-02-13 01:00 |  | 2026-02-13 15:42 | 2026-02-17 14:24 | 0.84583 | 2.7375 | 10 | 3.9458 | 3.5833
TR3 | 2026-02-14 02:00 | 2026-01-27 17:38: 2026-02-17 14:24; 2026-01-31 20:36: 2026-02-19 03:00 | 3.5167 | 1.525 |  |  | 5.0417

## 03_TR1-3_Evidence
Trip | Datetime | Sender | Message
TR1 | 2026-01-27 15:31 | 𝓨𝓸𝓸𝓷𝓾𝓼 𝓚𝓸𝓵𝓲𝓴𝓴𝓪𝓻𝓪 | *_kindly note that land PTW approval (for 01st Trip - TR) is still pending, hence do not move SPMT from the yard to the jetty area until we receive Land PTW approval _*
TR1 | 2026-01-28 11:20 | Yulia MAMMOET | Please, for tomorrow, 29-01-2026, book a crane and 1 forklift. Starting 07:00am It will be required for linkspan installation.
TR1 | 2026-01-28 17:18 | Haitham | @⁨Yulia MAMMOET⁩ tomorrow we will be have F2F meeting with HM regarding link span issue: Pls attend we will coordinate at morning Attendees: SCT MWS MMT OFCO
TR1 | 2026-01-28 17:22 | 상욱 | Not possible. Linkspan issue..HM want any certificate..confirmation
TR1 | 2026-01-28 17:36 | 상욱 | @⁨Yulia MAMMOET⁩ Linkspan. Pls check..if manufactuer have COC.(Certificate of Conformity).
TR1 | 2026-01-28 17:38 | OFCO DAS GOpal | Please note As advised earlier , The Land PTW ro carry out the operation including shifting if the cafgo from the yard has not been approved yet as the initial approvar is HM.
TR1 | 2026-01-29 13:31 | OFCO DAS GOpal | Dear all We received a phone call now from Mr Ahmed Khasim whom we met from operations, according to his manager linkspan certifiacate is mandatory
TR1 | 2026-01-30 08:40 | Yulia MAMMOET | Steel plates installed. Linskspan ramp adjusted.
TR1 | 2026-01-30 10:35 | 상욱 | Waiting for PTW.. only issue Linkspan.as per request byHM.
TR1 | 2026-01-30 11:20 | Yulia MAMMOET | Mr. Cha, @⁨CHA⁩ Since Port Authority doesn’t allow to commence operation, please, confirm that we can start removal of linkspan
TR1 | 2026-01-30 11:22 | 상욱 | Yulia...you should check another solution on Linkspan . Why push ? SCT will try to resolve issue to TPI. rental base.etc.
TR1 | 2026-01-30 11:23 | CHA | Please Linkspan Removal - Hold until 14:00
TR1 | 2026-01-30 12:01 | 𝓨𝓸𝓸𝓷𝓾𝓼 𝓚𝓸𝓵𝓲𝓴𝓴𝓪𝓻𝓪 | @⁨상욱⁩ , De-ballasting all are subject to approval of port authority, we will request AD port waste service team to arrange tanker for collection. please confirm to proceed for tanker arrangements
TR1 | 2026-01-30 16:04 | Yulia MAMMOET | Yes, tomorrow we come anyway at 7am Either for load out, or for ramp removal… I hope we receive exceptional approval 26/1/30 PM 5:01 - ‎상욱님이 Arvin님을 추가했습니다
TR1 | 2026-01-30 16:04 | 상욱 | If get PTW..we can start to loadout tom.🙏 Today..if no avtivity..pls release them..
TR1 | 2026-01-30 22:10 | 𝓨𝓸𝓸𝓷𝓾𝓼 𝓚𝓸𝓵𝓲𝓴𝓴𝓪𝓻𝓪 | Dear All, we received approval from HM / HSE / MZ Ops (After a long discussion) to load cargo (for 01st trip only) onto the vessel. kindly arrange your loading plan tomorrow *kindly note that we must submit COA from approved MWS team prior sailing vessel from port*
TR1 | 2026-01-31 07:21 | Yulia MAMMOET | Good morning Please share PTW
TR1 | 2026-01-31 07:49 | Yulia MAMMOET | Thank you! SPMT crew is ready to shift Tranformer to jetty area. If you already have land transportation PTW, please, share with us and we will bring it to jetty.
TR1 | 2026-01-31 10:01 | +971 50 680 3593 | Please refer to link for MS 8061 Load in&out Rev.B : OE&PC Approved Rev.C : Re-submitted to ADNOC for approval https://studio.creativefabrica.com/transfer/390gU3Cu3PsHmueJ9LVOeFolWxD?accessCode=390gpoMgEL4b8ipjiOwU35yBuXM&utm_source=amazon-ses&utm_medium=email&utm_campaign=studio-transfer-completed-en-v1 8062 : Jack down skidding Rev.B : OE&PC Approved Rev.D : Re-submitted to ADNOV for approval https://studio.creativefabrica.com/transfer/390gdOigVXYDFir2CKAOs84vo77?accessCode=390gs88tFttTxd9V0Xl3bm4nsJa&utm_source=amazon-ses&utm_medium=email&utm_campaign=studio-transfer-completed-en-v1
TR1 | 2026-01-31 10:25 | Yulia MAMMOET | We received approval from Harbor Master to start load out. Tools box talk done.
TR1 | 2026-01-31 10:54 | Yulia MAMMOET | @⁨𝓨𝓸𝓸𝓷𝓾𝓼 𝓚𝓸𝓵𝓲𝓴𝓴𝓪𝓻𝓪⁩ hi! May we, please, have a crane with us now. For removal of the linkspan ramp and loading it on LCT
TR1 | 2026-01-31 12:29 | LCT Bushra | Good day @⁨Haitham⁩ @⁨Yulia MAMMOET⁩ Pls advised for cargo manifest including the material on board. We need to finalize the calculation. Thank you.
TR1 | 2026-01-31 14:34 | Adnoc Ouda | @⁨Haitham⁩ Appreciate if you can send manifest, Sail away certificate by mail to the team in AGI to be ready for offloading upon arrival and please keep us in the loop to support as may be needed
TR1 | 2026-01-31 17:58 | 상욱 | Waiting Manifest. COA.. I think ETD 1.FEB / ETA 2.FEB.
TR1 | 2026-01-31 19:28 | LCT Bushra | from the latest manifest, the total weight loaded to Bush is 645 tons, in this condition, vessel draught will reach 2,9 mtrs. meanwhile, the actual draught is 2,5 mtr. diff 0,4 mtr by the draught.
TR1 | 2026-01-31 19:47 | 상욱 | @⁨LCT Bushra⁩ I shared..revised manifest. Shipping team will fu.
TR1 | 2026-02-01 07:47 | Khemlal-SCT Logistics | for link Span - will use choker hitch method using a spreader beam and webbing slings, and the same was submitted LOP, has been submitted and is currently awaiting approval from AOF SPA.
TR1 | 2026-02-01 14:05 | 상욱 | @⁨Yulia MAMMOET⁩ Pls prepare 2nd TR operation.- SPMT.LINKSPAN.ETC 26/2/2 AM 1:45 - ‎~ Alex님과의 보안 코드가 변경되었습니다. 더 알아보려면 탭하세요. 26/2/2 AM 6:50 - ‎+971 56 177 0485님과의 보안 코드가 변경되었습니다. 더 알아보려면 탭하세요. 26/2/2 AM 8:58 - ‎~ Alex님과의 보안 코드가 변경되었습니다. 더 알아보려면 탭하세요.
TR2 | 2026-02-09 11:21 | 상욱 | 2nd TR..Loadout plan. -09. Feb..Bushra.securing berth.night -10. Feb..Linkspan arrangement. -11. Feb..2nd TR.Loadout..MWS. -12. Feb..ETA AGI am.Linkspan arrangement -13. Feb..Loadin. -14. Feb..ETA MZP..am <This message was edited>
TR2 | 2026-02-09 16:28 | Yulia MAMMOET | Dear @⁨𝓨𝓸𝓸𝓷𝓾𝓼 𝓚𝓸𝓵𝓲𝓴𝓴𝓪𝓻𝓪⁩ @⁨+971 56 501 4341⁩ good afternoon! Kindly ask you to book for MMT Crew AUX equipment as per below request: 10.02 Please, provide below by 7am: Mafi trailer (for shifting of equipment from laydown area to jetty) 16t forklift (for loading/offloading of equipment) crane (for installation of linkspan) 11.02 Please, provide below by 7am: Crane (for loading of linkspan on LCT) Mafi trailer (for bringing 6m mats to laydown area) Please, provide by 4pm forklift (to shift welding machines from jetty to laydown area) Thank you!
TR2 | 2026-02-10 13:01 | Yulia MAMMOET | Dear All, good afternoon! We are observing quite high waves at the moment. The crew is raising concerns regarding linkspan beam installation. In the afternoon I will let you know if we install beams today or tomorrow morning. The whole installation takes less than 30 minutes. So while we will be shifting Transformers from laydown area to Jetty, Marine crew will install the beams. Welding is almost done. Will be completed today.
TR2 | 2026-02-10 13:01 | Yulia MAMMOET | Tomorrow’s tide window is 7-8am
TR2 | 2026-02-10 14:28 | Yulia MAMMOET | Dears, Linkspan beams will be installed tomorrow morning. Today swell is too high and LCT is moving a lot. As I informed earlier, it won’t take more than 30 minutes
TR2 | 2026-02-10 17:32 | Yulia MAMMOET | Mammoet crew to report to MZP by 06:45am Tide window tomorrow: 06:00am tide is 1.80m 07:00am tide is 1.85m 08:00am tide is 1.82m Marine crew to install linkspan beams (07:00-07:30) SPMT crew to shift transformer to jetty area (07:00-07:30) Crane is arranged. It will be provided at 07:00am Load out start at 07:30am Subject to weather conditions.
TR2 | 2026-02-11 07:09 | Yulia MAMMOET | Dears, Port Supervisor stoped all operations due to dense fog. We can’t use crane now to install the linkspan beams. 26/2/11 AM 7:10 - ‎Yulia MAMMOET님이 Mammoet님을 추가했습니다
TR2 | 2026-02-11 07:18 | Mammoet | Gents, Due to heavy fog all mina activities have stopped,
TR2 | 2026-02-11 07:21 | Mammoet | Please note we won't be able to loadout 2nd TR today before 8pm, as per tide chart 1.8m will drop after 8am,
TR2 | 2026-02-11 08:09 | Yulia MAMMOET | Dears, good morning Please, share weather forecast for tomorrow, including, if fog is expected or not
TR2 | 2026-02-11 08:56 | Yulia MAMMOET | Dear Team, As per concerns from LCT Master, linkspan beams will not be installed today. Crane is released. Mammoet crew will be released as per confirmation from SCT Team (phone call with Mr. Jeong)
TR2 | 2026-02-11 19:16 | 상욱 | Dear all. Tom..will try again.. Tide ok till 10.am ...
TR2 | 2026-02-12 07:01 | Yulia MAMMOET | Dears, good morning. Weather is clear. We will start shifting of TR Unit to jetty and installation of linden beams. Once beams are installed, we will proceed with load out
TR2 | 2026-02-12 10:42 | 상욱 | @⁨Yulia MAMMOET⁩ Pls check. old linkspan..exit plan ?
TR2 | 2026-02-12 12:11 | 상욱 | AGI plan. 13 Feb. Linkspan arrangment 14.Feb..offloading and Cast off (Jetty #3.securing confirmed)
TR2 | 2026-02-12 13:16 | Shariff | MZP..3rd TR operation Initial Plan as per current weather forecast. 15.Feb..ETA MZP 16.Feb..stay (FRA) 17.Feb..Linkspan arrangement. 18.Feb..Loadout and Castoff.
TR3 | 2026-02-15 08:37 | Nanda kumar | In 3 to 4 hrs. An operational vessel is already at the berth. <This message was edited>
TR3 | 2026-02-15 12:09 | LCT Bushra | Call the vts and informed berth still occupied by comarco Palma. Pls advised..
TR3 | 2026-02-15 14:48 | Offco Support Log | 4 more units remain to be offloaded from the Comarco Palma vessel. We have informed our client to expedite the operations.
TR3 | 2026-02-15 14:53 | LCT Bushra | Well noted sir.. Went comarco Palma cast off, I call vts
TR3 | 2026-02-15 19:34 | LCT Bushra | Good evening @⁨𝓨𝓸𝓸𝓷𝓾𝓼 𝓚𝓸𝓵𝓲𝓴𝓴𝓪𝓻𝓪⁩ @⁨OFCO Sathyan⁩ Pls advise berthing schedule for Bushra, We called VtS and informed that berthing for Bushra not approved yet.
TR3 | 2026-02-15 19:45 | Offco Support Log | @⁨LCT Bushra⁩, berth#5 already approved in Maqta System. Comarco Palma vessel is just casted off. You may call VTS once again after 15 mins
TR3 | 2026-02-16 01:11 | Offco Support Log | @⁨LCT Bushra⁩, we understand from VTS that pilot unable to board onto launch due to bad weather.
TR3 | 2026-02-16 01:12 | Offco Support Log | According to VTS, pilot will monitor the weather and he will bring you in if weather is favourable.
TR3 | 2026-02-16 01:14 | LCT Bushra | here is the weather forecast.
TR3 | 2026-02-16 01:28 | LCT Bushra | According the weather forecast the weather will higher swell. suggestion better vessel back to anchorage and drop anchor to avoid heavy rolling. please advice..
TR3 | 2026-02-16 01:43 | LCT Bushra | it is not safe for vessel steaming close to buoy Z19 waiting for pilot due to heavy rolling and pitching, vessel slowly heading back to anchorage location. @⁨Offco Support Log⁩ please advise for vessel approval to drop anchor in Mina Zayed anchorage area.
TR3 | 2026-02-16 06:38 | LCT Bushra | Capt @⁨Capt Igor⁩ @⁨Adnoc Ouda⁩ @⁨CHA⁩ Vessels pitching moderately with 25-28 knots wind and 5-6 wave high. Need quick response for this matter.
TR3 | 2026-02-16 06:42 | LCT Bushra | Noted sir, still waiting for information from the agent, and proceeding slow to the anchorage area.
TR3 | 2026-02-16 07:00 | LCT Bushra | Mr @⁨Offco Support Log⁩ @⁨OFCO DAS GOpal⁩ @⁨OFCO Sathyan⁩ @@⁨Nanda kumar⁩ Just calling Zayed VTS, asking submit a new drop anchor request at Mina Zayed anchorage. Until now the weather not save for us to keep slowly sailing.
TR3 | 2026-02-16 07:21 | 상욱 | Plan.change. 17..pm hrs..berthing 18..Loadout.
TR3 | 2026-02-16 08:18 | LCT Bushra | Good morning, LCT Bushra 16/02/2025 0806hrs drop anchor at MZ anchorage. Strong wind & rough sea. Thank you
TR3 | 2026-02-16 18:03 | Yulia MAMMOET | Dears, Please, confirm LCT Bushra’s berthing.
TR3 | 2026-02-16 18:16 | CHA | As of now, the berthing is not yet confirmed. It will depend on the weather conditions.
TR3 | 2026-02-16 19:34 | Yulia MAMMOET | Dear Team, since it is still unknown what time LCT Bushra will berth, please, be informed, that all operations with 3rd TR Unit will be scheduled for 18th of February. 1. Offloading of LCT (linkspan, transport beams) 2. ⁠Beam replacement for TR 3 3. ⁠Linkspan installation Load out subject to preparations progress and weather conditions.
TR3 | 2026-02-16 19:35 | Yulia MAMMOET | Tide window on 18.02.2026: 13:00-14:00
TR3 | 2026-02-17 14:20 | 상욱 | Bushra. secured berth. FW fu..pls

## 04_TR1-3_BaselineVsActual
Trip | Milestone | Origin_Plan | Final_Plan | Actual_or_Forecast | Var_vs_Origin_days | Var_vs_Final_days
TR1 | AGI_CastOff_Return | 2026-02-06 | 2026-02-04 | 2026-02-08 14:38 | 2.6097 | 4.6097
TR1 | LoadIn | 2026-02-05 | 2026-02-03 | 2026-02-07 08:47 | 2.366 | 4.366
TR1 | SailAway | 2026-02-03 | 2026-02-01 | 2026-01-31 20:36 | -2.1417 | -0.14167
TR2 | AGI_CastOff_Return | 2026-02-13 | 2026-02-11 | 2026-02-13 15:42 | 0.65417 | 2.6542
TR2 | LoadIn | 2026-02-12 | 2026-02-10 | 2026-02-13 14:30 | 1.6042 | 3.6042
TR2 | SailAway | 2026-02-10 | 2026-02-08 | 2026-02-12 15:00 | 2.625 | 4.625
TR3 | AGI_CastOff_Return | 2026-02-20 | 2026-02-20 | 2026-02-21 12:42 | 1.5292 | 1.5292
TR3 | SailAway | 2026-02-17 | 2026-02-19 | 2026-02-19 03:00 | 2.125 | 0.125

## 05_TR4-TR7_Reschedule
Unit | MZP_Secured | MZP_ETD | AGI_ETA | AGI_CastOff_Return | Next_MZP_Secured | Assumed_LoadIn_Start | Turning_Start | Turning_Finish | Jacking_Down | Orig_SailAway | Orig_LoadIn | Orig_Jacking | Var_SailAway_vs_Orig_days | Var_Jacking_vs_Orig_days
4 | 2026-02-24 03:23 | 2026-02-26 22:28 | 2026-02-27 08:10 | 2026-03-01 08:10 | 2026-03-03 22:51 | 2026-02-28 | 2026-03-02 | 2026-03-04 | 2026-03-05 | 2026-02-24 | 2026-02-26 | 2026-03-03 | 2.9363 | 2
5 | 2026-03-03 22:51 | 2026-03-06 17:57 | 2026-03-07 03:39 | 2026-03-09 03:39 | 2026-03-11 18:20 | 2026-03-08 | 2026-03-10 | 2026-03-12 | 2026-03-13 | 2026-03-03 | 2026-03-05 | 2026-03-10 | 3.7477 | 3
6 | 2026-03-11 18:20 | 2026-03-14 13:25 | 2026-03-14 23:07 | 2026-03-16 23:07 | 2026-03-19 13:48 | 2026-03-16 | 2026-03-18 | 2026-03-20 | 2026-03-21 | 2026-03-11 | 2026-03-12 | 2026-03-17 | 3.559 | 4
7 | 2026-03-19 13:48 | 2026-03-22 08:53 | 2026-03-22 18:35 | 2026-03-24 18:35 |  | 2026-03-24 | 2026-03-26 | 2026-03-28 | 2026-03-29 | 2026-03-17 | 2026-03-19 | 2026-03-24 | 5.3704 | 5
Formulas:
MZP_Secured = [Next_MZP_Secured, row above]
MZP_ETD = [MZP_Secured] + '01_Assumptions'!$B6
AGI_ETA = [MZP_ETD] + '01_Assumptions'!$B4
AGI_CastOff_Return = [AGI_ETA] + '01_Assumptions'!$B3
Next_MZP_Secured = [AGI_CastOff_Return] + '01_Assumptions'!$B5
Assumed_LoadIn_Start = INT([MZP_ETD]+2)
Turning_Start = [Assumed_LoadIn_Start]+2
Turning_Finish = [Assumed_LoadIn_Start]+4
Jacking_Down = [Assumed_LoadIn_Start]+5

## 06_TR1-TR7_Summary
Unit | Orig_SailAway | Actual_or_Forecast_SailAway | Var_SailAway_days | Orig_Jacking | Actual_or_Forecast_Jacking | Var_Jacking_days | Buffer_to_OrigFinish_days
1 | 2026-02-03 | 2026-01-31 20:36 | -2.1417 | 2026-02-10 | 2026-02-12 | 2 | 40
2 | 2026-02-10 | 2026-02-12 15:00 | 2.625 | 2026-02-17 | 2026-02-18 | 1 | 34
3 | 2026-02-17 | 2026-02-19 03:00 | 2.125 | 2026-02-24 | 2026-02-26 | 2 | 26
4 | 2026-02-24 | 2026-02-26 22:28 | 2.9363 | 2026-03-03 | 2026-03-05 | 2 | 19
5 | 2026-03-03 | 2026-03-06 17:57 | 3.7477 | 2026-03-10 | 2026-03-13 | 3 | 11
6 | 2026-03-11 | 2026-03-14 13:25 | 3.559 | 2026-03-17 | 2026-03-21 | 4 | 3
7 | 2026-03-17 | 2026-03-22 08:53 | 5.3704 | 2026-03-24 | 2026-03-29 | 5 | -5

## 07_Float
Metric | Value | Notes
Origin Project Finish (Unit7 Jacking) | 2026-03-24 | From Origin schedule
Forecast Project Finish (Unit7 Jacking) | 2026-03-29 | From Reschedule (avg-based)
Project Float (days) = Origin - Forecast | -5 | Positive=buffer, Negative=delay