## All Activities
No | Type | TR Unit | Date | Activity ID | Activity Name | Duration | Start Date | End Date | Level 1 | Level 2
1 | Mobilization | Mobilization | 2026-01-26 | A1000 | Mobilization of 1st set of SPMT; Asembly + Function Test | 1 | 2026-01-26 | 2026-01-26 | MOBILIZATION | SPMT
2 | Mobilization | Mobilization | 2026-01-26 | A1001 | Mobilization of Marine Equipment and Steelworks | 0.5 | 2026-01-26 | 2026-01-26 | MOBILIZATION | MARINE
3 | Demobilization | Demobilization | 2026-01-28 | A2000 | Demobilization of Marine Equipment and Steelworks | 1 | 2026-01-28 | 2026-01-28 | DEMOBILIZATION | MARINE
4 | Mobilization | Mobilization | 2026-02-01 | A2010 | Mobilization of Jacking Equipment and Steel bridge (prior LCT's arrival to AGI with TR 1&2!)) | 1 | 2026-02-01 | 2026-02-02 | MOBILIZATION | JACKING EQUIPMENT, STEEL BRIDGE
5 | Mobilization | Mobilization | 2026-02-07 | A1010 | Mobilization of 2nd set of SPMT; Assembly + Function test | 1 | 2026-02-07 | 2026-02-07 | MOBILIZATION | SPMT
6 | Demobilization | Demobilization | 2026-03-18 | A1980 | Demobilization of 2nd set of SPMT | 1 | 2026-03-18 | 2026-03-18 | DEMOBILIZATION | SPMT
7 | Demobilization | Demobilization | 2026-03-22 | A1990 | Demobilization of 1st set of SPMT | 1 | 2026-03-22 | 2026-03-23 | DEMOBILIZATION | SPMT
8 | Demobilization | Demobilization | 2026-03-25 | A2020 | Demobilization of Jacking Equipment and Steel bridge | 1 | 2026-03-25 | 2026-03-25 | DEMOBILIZATION | JACKING EQUIPMENT, STEEL BRIDGE
9 | TR Unit 1 | TR Unit 1 | 2026-01-28 | A1002 | Beam Replacement AGI TR Unit 1 (TR Bay 4) - Two 5t forklifts required | 1 | 2026-01-28 | 2026-01-28 | OPERATIONAL | Beam Replacement
10 | TR Unit 1 | TR Unit 1 | 2026-01-28 | A1004 | Deck Preparations (D-ring cutting; marking, steel sets installation) - One 5t forklift and Crane required | 1 | 2026-01-28 | 2026-01-28 | OPERATIONAL | Deck Preparations
11 | TR Unit 1 | TR Unit 1 | 2026-01-29 | A1005 | Deck Preparations (Steel sets installation, welding) - Crane Required for steel sets installation | 1 | 2026-01-29 | 2026-01-29 | OPERATIONAL | Deck Preparations
12 | TR Unit 1 | TR Unit 1 | 2026-01-31 | A1030 | Loading of AGI TR Unit 1 on SPMT; lashing; Shifting to Mina Zayed Port RoRo Jetty area | 0.3 | 2026-01-31 | 2026-01-31 | OPERATIONAL | AGI TR Unit 1
13 | TR Unit 1 | TR Unit 1 | 2026-01-31 | A1040 | RoRo Ramp Installation - 5t Frokift and Crane required | 0.3 | 2026-01-31 | 2026-01-31 | OPERATIONAL | AGI TR Unit 1
14 | TR Unit 1 | TR Unit 1 | 2026-01-31 | A1060 | Load-out of AGL TR Unit 1; stool down (8am-10am) | 0.2 | 2026-01-31 | 2026-01-31 | OPERATIONAL | AGI TR Unit 1
15 | TR Unit 1 | TR Unit 1 | 2026-01-31 | A1070 | RoRo ramp removal; Seafastening AGL TR Unit 1 - Crane required | 1.5 | 2026-01-31 | 2026-02-02 | OPERATIONAL | AGI TR Unit 1
16 | TR Unit 1 | TR Unit 1 | 2026-02-03 | A1081 | MWS; MPI; Sail-away - Marine Transportation by LCT to Al Ghallan Island | 1 | 2026-02-03 | 2026-02-03 | OPERATIONAL | AGI TR Unit 1
17 | TR Unit 1 | TR Unit 1 | 2026-02-04 | A1090 | MMT Crew Mob to AGI; Site Induction; Meeting with Client | 0.5 | 2026-02-04 | 2026-02-04 | OPERATIONAL | AGI TR Unit 1
18 | TR Unit 1 | TR Unit 1 | 2026-02-04 | A1091 | LCT Arrival; Berthing at AGL RoRo Jetty | 0.5 | 2026-02-04 | 2026-02-04 | OPERATIONAL | AGI TR Unit 1
19 | TR Unit 1 | TR Unit 1 | 2026-02-04 | A1100 | Unlashing and cutting; steel sets preparations - Forklift required | 0.5 | 2026-02-04 | 2026-02-04 | OPERATIONAL | AGI TR Unit 1
20 | TR Unit 1 | TR Unit 1 | 2026-02-05 | A1110 | Load-in of AGI TR Unit 1 (including RoRo Ramp Installation); store on Jetty - Crane required | 1 | 2026-02-05 | 2026-02-05 | OPERATIONAL | AGI TR Unit 1
21 | TR Unit 1 | TR Unit 1 | 2026-02-06 | A1121 | LCT Sails back to MZP to collect TR Unit 1 | 1 | 2026-02-06 | 2026-02-06 | OPERATIONAL | AGI TR Unit 1
22 | TR Unit 1 | TR Unit 1 | 2026-02-06 | A1122 | Steel bridge Installation - Crane required | 0.3 | 2026-02-06 | 2026-02-06 | OPERATIONAL | AGI TR Unit 1
23 | TR Unit 1 | TR Unit 1 | 2026-02-06 | A1140 | AGL TR Unit 1 (TR Bay 4) load on SPMT; lashing; Transportation and JD (steel set to be delivered to bay area by trailer) | 0.7 | 2026-02-06 | 2026-02-06 | OPERATIONAL | AGI TR Unit 1
24 | TR Unit 1 | TR Unit 1 | 2026-02-07 | A1141 | Turning of AGI TR Unit 1 (TR Bay 4) - 10t Forklift required | 3 | 2026-02-07 | 2026-02-09 | OPERATIONAL | AGI TR Unit 1
25 | TR Unit 1 | TR Unit 1 | 2026-02-08 | A1181 | SPMT shifting back to Port | 0.5 | 2026-02-08 | 2026-02-08 | OPERATIONAL | AGI TR Unit 1
26 | TR Unit 1 | TR Unit 1 | 2026-02-10 | A1150 | Jacking down of AGI TR Unit 1 (TR Bay 4) on temporary support - Forklift required | 1 | 2026-02-10 | 2026-02-10 | OPERATIONAL | AGI TR Unit 1
27 | TR Unit 2 | TR Unit 2 | 2026-01-29 | A1003 | Beam Replacement AGI TR Unit 2 (TR Bay 3) - Two 5t forklifts required | 1 | 2026-01-29 | 2026-01-29 | OPERATIONAL | Beam Replacement
28 | TR Unit 2 | TR Unit 2 | 2026-02-07 | A2029 | LCT Arrives at MZP; Deck preparations | 1 | 2026-02-07 | 2026-02-07 | OPERATIONAL | AGI TR Unit 2
29 | TR Unit 2 | TR Unit 2 | 2026-02-08 | A2030 | Loading of AGI TR Unit 2 on SPMT; lashing; Shifting to Mina Zayed Port RoRo Jetty area | 0.3 | 2026-02-08 | 2026-02-08 | OPERATIONAL | AGI TR Unit 2
30 | TR Unit 2 | TR Unit 2 | 2026-02-08 | A2040 | RoRo Ramp Installation - 5t Frokift and Crane required | 0.3 | 2026-02-08 | 2026-02-08 | OPERATIONAL | AGI TR Unit 2
31 | TR Unit 2 | TR Unit 2 | 2026-02-08 | A2050 | Load-out of AGL TR Unit 2; stool down | 0.2 | 2026-02-08 | 2026-02-08 | OPERATIONAL | AGI TR Unit 2
32 | TR Unit 2 | TR Unit 2 | 2026-02-08 | A2060 | RoRo ramp removal; Seafastening AGL TR Unit 2 - Crane required | 1.5 | 2026-02-08 | 2026-02-09 | OPERATIONAL | AGI TR Unit 2
33 | TR Unit 2 | TR Unit 2 | 2026-02-10 | A2070 | MWS; MPI; Sail-away - Marine Transportation by LCT to Al Ghallan Island | 1 | 2026-02-10 | 2026-02-10 | OPERATIONAL | AGI TR Unit 2
34 | TR Unit 2 | TR Unit 2 | 2026-02-11 | A2090 | LCT Arrival; Berthing at AGL RoRo Jetty | 0.5 | 2026-02-11 | 2026-02-11 | OPERATIONAL | AGI TR Unit 2
35 | TR Unit 2 | TR Unit 2 | 2026-02-11 | A2100 | Unlashing and cutting; steel sets preparations - Forklift required | 0.5 | 2026-02-11 | 2026-02-11 | OPERATIONAL | AGI TR Unit 2
36 | TR Unit 2 | TR Unit 2 | 2026-02-12 | A2110 | Load-in of AGI TR Unit 2 (including RoRo Ramp Installation); store on Jetty - Crane required | 1 | 2026-02-12 | 2026-02-12 | OPERATIONAL | AGI TR Unit 2
37 | TR Unit 2 | TR Unit 2 | 2026-02-13 | A2120 | LCT Sails back to MZP to collect TR Unit 3 (SPMT to bring back 2pcs of 7.45m transport beam) | 1 | 2026-02-13 | 2026-02-13 | OPERATIONAL | AGI TR Unit 2
38 | TR Unit 2 | TR Unit 2 | 2026-02-13 | A2130 | Steel bridge Installation - Crane required | 0.3 | 2026-02-13 | 2026-02-13 | OPERATIONAL | AGI TR Unit 2
39 | TR Unit 2 | TR Unit 2 | 2026-02-13 | A2140 | AGL TR Unit 2 (TR Bay 3) load on SPMT; lashing; Transportation and JD (steel set to be delivered to bay area by trailer) | 0.7 | 2026-02-13 | 2026-02-13 | OPERATIONAL | AGI TR Unit 2
40 | TR Unit 2 | TR Unit 2 | 2026-02-14 | A2150 | Turning of AGI TR Unit 2 (TR Bay 3) - 10t Forklift required | 3 | 2026-02-14 | 2026-02-16 | OPERATIONAL | AGI TR Unit 2
41 | TR Unit 2 | TR Unit 2 | 2026-02-15 | A2170 | SPMT shifting back to Port | 0.5 | 2026-02-15 | 2026-02-15 | OPERATIONAL | AGI TR Unit 2
42 | TR Unit 2 | TR Unit 2 | 2026-02-17 | A2160 | Jacking down of AGI TR Unit 2 (TR Bay 3) on temporary support - Forklift required | 1 | 2026-02-17 | 2026-02-17 | OPERATIONAL | AGI TR Unit 2
43 | TR Unit 3 | TR Unit 3 | 2026-02-14 | A1013 | Beam Replacement AGI TR Unit 3 (TR Bay 2) - Two 5t forklifts required | 1 | 2026-02-14 | 2026-02-14 | OPERATIONAL | Beam Replacement
44 | TR Unit 3 | TR Unit 3 | 2026-02-14 | A2180 | LCT Arrives at MZP; Deck preparations; Beam replacement | 1 | 2026-02-14 | 2026-02-14 | OPERATIONAL | AGI TR Unit 3
45 | TR Unit 3 | TR Unit 3 | 2026-02-15 | A2190 | Loading of AGI TR Unit 3 on SPMT; lashing; Shifting to Mina Zayed Port RoRo Jetty area | 0.3 | 2026-02-15 | 2026-02-15 | OPERATIONAL | AGI TR Unit 3
46 | TR Unit 3 | TR Unit 3 | 2026-02-15 | A2200 | RoRo Ramp Installation - 5t Frokift and Crane required | 0.3 | 2026-02-15 | 2026-02-15 | OPERATIONAL | AGI TR Unit 3
47 | TR Unit 3 | TR Unit 3 | 2026-02-15 | A2210 | Load-out of AGL TR Unit 3; stool down | 0.2 | 2026-02-15 | 2026-02-15 | OPERATIONAL | AGI TR Unit 3
48 | TR Unit 3 | TR Unit 3 | 2026-02-15 | A2220 | RoRo ramp removal; Seafastening AGL TR Unit 3 - Crane required | 1.5 | 2026-02-15 | 2026-02-16 | OPERATIONAL | AGI TR Unit 3
49 | TR Unit 3 | TR Unit 3 | 2026-02-17 | A2230 | MWS; MPI; Sail-away - Marine Transportation by LCT to Al Ghallan Island | 1 | 2026-02-17 | 2026-02-17 | OPERATIONAL | AGI TR Unit 3
50 | TR Unit 3 | TR Unit 3 | 2026-02-18 | A2250 | LCT Arrival; Berthing at AGL RoRo Jetty | 0.5 | 2026-02-18 | 2026-02-18 | OPERATIONAL | AGI TR Unit 3
51 | TR Unit 3 | TR Unit 3 | 2026-02-18 | A2260 | Unlashing and cutting; steel sets preparations - Forklift required | 0.5 | 2026-02-18 | 2026-02-18 | OPERATIONAL | AGI TR Unit 3
52 | TR Unit 3 | TR Unit 3 | 2026-02-19 | A2270 | Load-in of AGI TR Unit 3 (including RoRo Ramp Installation); store on Jetty - Crane required | 1 | 2026-02-19 | 2026-02-19 | OPERATIONAL | AGI TR Unit 3
53 | TR Unit 3 | TR Unit 3 | 2026-02-20 | A2280 | LCT Sails back to MZP to collect TR Unit 4 | 1 | 2026-02-20 | 2026-02-20 | OPERATIONAL | AGI TR Unit 3
54 | TR Unit 3 | TR Unit 3 | 2026-02-20 | A2290 | Steel bridge Installation - Crane required | 0.3 | 2026-02-20 | 2026-02-20 | OPERATIONAL | AGI TR Unit 3
55 | TR Unit 3 | TR Unit 3 | 2026-02-20 | A2300 | AGL TR Unit 3 (TR Bay 2) load on SPMT; lashing; Transportation and JD (steel set to be delivered to bay area by trailer) | 0.7 | 2026-02-20 | 2026-02-20 | OPERATIONAL | AGI TR Unit 3
56 | TR Unit 3 | TR Unit 3 | 2026-02-21 | A2310 | Turning of AGI TR Unit 3 (TR Bay 2) - 10t Forklift required | 3 | 2026-02-21 | 2026-02-23 | OPERATIONAL | AGI TR Unit 3
57 | TR Unit 3 | TR Unit 3 | 2026-02-22 | A2330 | SPMT shifting back to Port | 0.5 | 2026-02-22 | 2026-02-22 | OPERATIONAL | AGI TR Unit 3
58 | TR Unit 3 | TR Unit 3 | 2026-02-24 | A2320 | Jacking down of AGI TR Unit 3 (TR Bay 2) on temporary support - Forklift required | 1 | 2026-02-24 | 2026-02-24 | OPERATIONAL | AGI TR Unit 3
59 | TR Unit 4 | TR Unit 4 | 2026-02-21 | A1023 | Beam Replacement AGI TR Unit 4 (TR Bay 1) - Two 5t forklifts required | 1 | 2026-02-21 | 2026-02-21 | OPERATIONAL | Beam Replacement
60 | TR Unit 4 | TR Unit 4 | 2026-02-21 | A2340 | LCT Arrives at MZP; Deck preparations; Beam replacement | 1 | 2026-02-21 | 2026-02-21 | OPERATIONAL | AGI TR Unit 4
61 | TR Unit 4 | TR Unit 4 | 2026-02-22 | A2350 | Loading of AGI TR Unit 4 on SPMT; lashing; Shifting to Mina Zayed Port RoRo Jetty area | 0.3 | 2026-02-22 | 2026-02-22 | OPERATIONAL | AGI TR Unit 4
62 | TR Unit 4 | TR Unit 4 | 2026-02-22 | A2360 | RoRo Ramp Installation - 5t Frokift and Crane required | 0.3 | 2026-02-22 | 2026-02-22 | OPERATIONAL | AGI TR Unit 4
63 | TR Unit 4 | TR Unit 4 | 2026-02-22 | A2370 | Load-out of AGL TR Unit 4; stool down | 0.2 | 2026-02-22 | 2026-02-22 | OPERATIONAL | AGI TR Unit 4
64 | TR Unit 4 | TR Unit 4 | 2026-02-22 | A2380 | RoRo ramp removal; Seafastening AGL TR Unit 4 - Crane required | 1.5 | 2026-02-22 | 2026-02-23 | OPERATIONAL | AGI TR Unit 4
65 | TR Unit 4 | TR Unit 4 | 2026-02-24 | A2390 | MWS; MPI; Sail-away - Marine Transportation by LCT to Al Ghallan Island | 1 | 2026-02-24 | 2026-02-24 | OPERATIONAL | AGI TR Unit 4
66 | TR Unit 4 | TR Unit 4 | 2026-02-25 | A2410 | LCT Arrival; Berthing at AGL RoRo Jetty | 0.5 | 2026-02-25 | 2026-02-25 | OPERATIONAL | AGI TR Unit 4
67 | TR Unit 4 | TR Unit 4 | 2026-02-25 | A2420 | Unlashing and cutting; steel sets preparations - Forklift required | 0.5 | 2026-02-25 | 2026-02-25 | OPERATIONAL | AGI TR Unit 4
68 | TR Unit 4 | TR Unit 4 | 2026-02-26 | A2430 | Load-in of AGI TR Unit 4 (including RoRo Ramp Installation); store on Jetty - Crane required | 1 | 2026-02-26 | 2026-02-26 | OPERATIONAL | AGI TR Unit 4
69 | TR Unit 4 | TR Unit 4 | 2026-02-27 | A2440 | LCT Sails back to MZP to collect TR Unit 5 | 1 | 2026-02-27 | 2026-02-27 | OPERATIONAL | AGI TR Unit 4
70 | TR Unit 4 | TR Unit 4 | 2026-02-27 | A2450 | Steel bridge Installation - Crane required | 0.3 | 2026-02-27 | 2026-02-27 | OPERATIONAL | AGI TR Unit 4
71 | TR Unit 4 | TR Unit 4 | 2026-02-27 | A2460 | AGL TR Unit 4 (TR Bay 1) load on SPMT; lashing; Transportation and JD (steel set to be delivered to bay area by trailer) | 0.7 | 2026-02-27 | 2026-02-27 | OPERATIONAL | AGI TR Unit 4
72 | TR Unit 4 | TR Unit 4 | 2026-02-28 | A2470 | Turning of AGI TR Unit 4 (TR Bay 1) - 10t Forklift required | 3 | 2026-02-28 | 2026-03-02 | OPERATIONAL | AGI TR Unit 4
73 | TR Unit 4 | TR Unit 4 | 2026-03-01 | A2490 | SPMT shifting back to Port | 0.5 | 2026-03-01 | 2026-03-01 | OPERATIONAL | AGI TR Unit 4
74 | TR Unit 4 | TR Unit 4 | 2026-03-03 | A2480 | Jacking down of AGI TR Unit 4 (TR Bay 1) on temporary support - Forklift required | 1 | 2026-03-03 | 2026-03-03 | OPERATIONAL | AGI TR Unit 4
75 | TR Unit 5 | TR Unit 5 | 2026-02-28 | A1033 | Beam Replacement AGI TR Unit 5 (TR Bay 5) - Two 5t forklifts required | 1 | 2026-02-28 | 2026-02-28 | OPERATIONAL | Beam Replacement
76 | TR Unit 5 | TR Unit 5 | 2026-02-28 | A2500 | LCT Arrives at MZP; Deck preparations; Beam replacement | 1 | 2026-02-28 | 2026-02-28 | OPERATIONAL | AGI TR Unit 5
77 | TR Unit 5 | TR Unit 5 | 2026-03-01 | A2510 | Loading of AGI TR Unit 5 on SPMT; lashing; Shifting to Mina Zayed Port RoRo Jetty area | 0.3 | 2026-03-01 | 2026-03-01 | OPERATIONAL | AGI TR Unit 5
78 | TR Unit 5 | TR Unit 5 | 2026-03-01 | A2520 | RoRo Ramp Installation - 5t Frokift and Crane required | 0.3 | 2026-03-01 | 2026-03-01 | OPERATIONAL | AGI TR Unit 5
79 | TR Unit 5 | TR Unit 5 | 2026-03-01 | A2530 | Load-out of AGL TR Unit 5; stool down | 0.2 | 2026-03-01 | 2026-03-01 | OPERATIONAL | AGI TR Unit 5
80 | TR Unit 5 | TR Unit 5 | 2026-03-01 | A2540 | RoRo ramp removal; Seafastening AGL TR Unit 5 - Crane required | 1.5 | 2026-03-01 | 2026-03-02 | OPERATIONAL | AGI TR Unit 5
81 | TR Unit 5 | TR Unit 5 | 2026-03-03 | A2550 | MWS; MPI; Sail-away - Marine Transportation by LCT to Al Ghallan Island | 1 | 2026-03-03 | 2026-03-03 | OPERATIONAL | AGI TR Unit 5
82 | TR Unit 5 | TR Unit 5 | 2026-03-04 | A2560 | LCT Arrival; Berthing at AGL RoRo Jetty | 0.5 | 2026-03-04 | 2026-03-04 | OPERATIONAL | AGI TR Unit 5
83 | TR Unit 5 | TR Unit 5 | 2026-03-04 | A2570 | Unlashing and cutting; steel sets preparations - Forklift required | 0.5 | 2026-03-04 | 2026-03-04 | OPERATIONAL | AGI TR Unit 5
84 | TR Unit 5 | TR Unit 5 | 2026-03-05 | A2580 | Load-in of AGI TR Unit 5 (including RoRo Ramp Installation); store on Jetty - Crane required | 1 | 2026-03-05 | 2026-03-05 | OPERATIONAL | AGI TR Unit 5
85 | TR Unit 5 | TR Unit 5 | 2026-03-06 | A2590 | LCT Sails back to MZP to collect TR Unit 6 | 1 | 2026-03-06 | 2026-03-06 | OPERATIONAL | AGI TR Unit 5
86 | TR Unit 5 | TR Unit 5 | 2026-03-06 | A2600 | Steel bridge Installation - Crane required | 0.3 | 2026-03-06 | 2026-03-06 | OPERATIONAL | AGI TR Unit 5
87 | TR Unit 5 | TR Unit 5 | 2026-03-06 | A2610 | AGL TR Unit 5 (TR Bay 5) load on SPMT; lashing; Transportation and JD (steel set to be delivered to bay area by trailer) | 0.7 | 2026-03-06 | 2026-03-06 | OPERATIONAL | AGI TR Unit 5
88 | TR Unit 5 | TR Unit 5 | 2026-03-07 | A2620 | Turning of AGI TR Unit 5 (TR Bay 5) - 10t Forklift required | 3 | 2026-03-07 | 2026-03-09 | OPERATIONAL | AGI TR Unit 5
89 | TR Unit 5 | TR Unit 5 | 2026-03-08 | A2640 | SPMT shifting back to Port | 0.5 | 2026-03-08 | 2026-03-08 | OPERATIONAL | AGI TR Unit 5
90 | TR Unit 5 | TR Unit 5 | 2026-03-10 | A2630 | Jacking down of AGI TR Unit 5 (TR Bay 5) on temporary support - Forklift required | 1 | 2026-03-10 | 2026-03-10 | OPERATIONAL | AGI TR Unit 5
91 | TR Unit 6 | TR Unit 6 | 2026-03-07 | A1043 | Beam Replacement AGI TR Unit 6 (TR Bay 6) - Two 5t forklifts required | 1 | 2026-03-07 | 2026-03-07 | OPERATIONAL | Beam Replacement
92 | TR Unit 6 | TR Unit 6 | 2026-03-07 | A2650 | LCT Arrives at MZP; Deck preparations; Beam replacement | 1 | 2026-03-07 | 2026-03-07 | OPERATIONAL | AGI TR Unit 6
93 | TR Unit 6 | TR Unit 6 | 2026-03-08 | A2660 | Loading of AGI TR Unit 6 on SPMT; lashing; Shifting to Mina Zayed Port RoRo Jetty area | 0.3 | 2026-03-08 | 2026-03-08 | OPERATIONAL | AGI TR Unit 6
94 | TR Unit 6 | TR Unit 6 | 2026-03-08 | A2670 | RoRo Ramp Installation - 5t Frokift and Crane required | 0.3 | 2026-03-08 | 2026-03-08 | OPERATIONAL | AGI TR Unit 6
95 | TR Unit 6 | TR Unit 6 | 2026-03-08 | A2680 | Load-out of AGL TR Unit 6; stool down | 0.2 | 2026-03-08 | 2026-03-08 | OPERATIONAL | AGI TR Unit 6
96 | TR Unit 6 | TR Unit 6 | 2026-03-08 | A2690 | RoRo ramp removal; Seafastening AGL TR Unit 6 - Crane required | 1.5 | 2026-03-08 | 2026-03-09 | OPERATIONAL | AGI TR Unit 6
97 | TR Unit 6 | TR Unit 6 | 2026-03-10 | A2700 | MWS; MPI; Sail-away - Marine Transportation by LCT to Al Ghallan Island | 1 | 2026-03-10 | 2026-03-10 | OPERATIONAL | AGI TR Unit 6
98 | TR Unit 6 | TR Unit 6 | 2026-03-11 | A2710 | LCT Arrival; Berthing at AGL RoRo Jetty | 0.5 | 2026-03-11 | 2026-03-11 | OPERATIONAL | AGI TR Unit 6
99 | TR Unit 6 | TR Unit 6 | 2026-03-11 | A2720 | Unlashing and cutting; steel sets preparations - Forklift required | 0.5 | 2026-03-11 | 2026-03-11 | OPERATIONAL | AGI TR Unit 6
100 | TR Unit 6 | TR Unit 6 | 2026-03-12 | A2730 | Load-in of AGI TR Unit 6 (including RoRo Ramp Installation); store on Jetty - Crane required | 1 | 2026-03-12 | 2026-03-12 | OPERATIONAL | AGI TR Unit 6
101 | TR Unit 6 | TR Unit 6 | 2026-03-13 | A2740 | LCT Sails back to MZP to collect TR Unit 7 | 1 | 2026-03-13 | 2026-03-13 | OPERATIONAL | AGI TR Unit 6
102 | TR Unit 6 | TR Unit 6 | 2026-03-13 | A2750 | Steel bridge Installation - Crane required | 0.3 | 2026-03-13 | 2026-03-13 | OPERATIONAL | AGI TR Unit 6
103 | TR Unit 6 | TR Unit 6 | 2026-03-13 | A2760 | AGL TR Unit 6 (TR Bay 6) load on SPMT; lashing; Transportation and JD (steel set to be delivered to bay area by trailer) | 0.7 | 2026-03-13 | 2026-03-13 | OPERATIONAL | AGI TR Unit 6
104 | TR Unit 6 | TR Unit 6 | 2026-03-14 | A2770 | Turning of AGI TR Unit 6 (TR Bay 6) - 10t Forklift required | 3 | 2026-03-14 | 2026-03-16 | OPERATIONAL | AGI TR Unit 6
105 | TR Unit 6 | TR Unit 6 | 2026-03-15 | A2790 | SPMT shifting back to Port | 0.5 | 2026-03-15 | 2026-03-15 | OPERATIONAL | AGI TR Unit 6
106 | TR Unit 6 | TR Unit 6 | 2026-03-17 | A2780 | Jacking down of AGI TR Unit 6 (TR Bay 6) on temporary support - Forklift required | 1 | 2026-03-17 | 2026-03-17 | OPERATIONAL | AGI TR Unit 6
107 | TR Unit 7 | TR Unit 1 | 2026-03-14 | A1053 | Beam Replacement AGI TR Unit 7 (TR Bay 7) - Two 5t forklifts required | 1 | 2026-03-14 | 2026-03-14 | OPERATIONAL | Beam Replacement
108 | TR Unit 7 | TR Unit 7 | 2026-03-14 | A2800 | LCT Arrives at MZP; Deck preparations; Beam replacement | 1 | 2026-03-14 | 2026-03-14 | OPERATIONAL | AGI TR Unit 7
109 | TR Unit 7 | TR Unit 7 | 2026-03-15 | A2810 | Loading of AGI TR Unit 7 on SPMT; lashing; Shifting to Mina Zayed Port RoRo Jetty area | 0.3 | 2026-03-15 | 2026-03-15 | OPERATIONAL | AGI TR Unit 7
110 | TR Unit 7 | TR Unit 7 | 2026-03-15 | A2820 | RoRo Ramp Installation - 5t Frokift and Crane required | 0.3 | 2026-03-15 | 2026-03-15 | OPERATIONAL | AGI TR Unit 7
111 | TR Unit 7 | TR Unit 7 | 2026-03-15 | A2830 | Load-out of AGL TR Unit 7; stool down | 0.2 | 2026-03-15 | 2026-03-15 | OPERATIONAL | AGI TR Unit 7
112 | TR Unit 7 | TR Unit 7 | 2026-03-15 | A2840 | RoRo ramp removal; Seafastening AGL TR Unit 7 - Crane required | 1.5 | 2026-03-15 | 2026-03-16 | OPERATIONAL | AGI TR Unit 7
113 | TR Unit 7 | TR Unit 7 | 2026-03-17 | A2850 | MWS; MPI; Sail-away - Marine Transportation by LCT to Al Ghallan Island | 1 | 2026-03-17 | 2026-03-17 | OPERATIONAL | AGI TR Unit 7
114 | TR Unit 7 | TR Unit 7 | 2026-03-18 | A2860 | LCT Arrival; Berthing at AGL RoRo Jetty | 0.5 | 2026-03-18 | 2026-03-18 | OPERATIONAL | AGI TR Unit 7
115 | TR Unit 7 | TR Unit 7 | 2026-03-18 | A2870 | Unlashing and cutting; steel sets preparations - Forklift required | 0.5 | 2026-03-18 | 2026-03-18 | OPERATIONAL | AGI TR Unit 7
116 | TR Unit 7 | TR Unit 7 | 2026-03-19 | A2880 | Load-in of AGI TR Unit 7 (including RoRo Ramp Installation); store on Jetty - Crane required | 1 | 2026-03-19 | 2026-03-19 | OPERATIONAL | AGI TR Unit 7
117 | TR Unit 7 | TR Unit 7 | 2026-03-20 | A2900 | Steel bridge Installation - Crane required | 0.3 | 2026-03-20 | 2026-03-20 | OPERATIONAL | AGI TR Unit 7
118 | TR Unit 7 | TR Unit 7 | 2026-03-20 | A2910 | AGL TR Unit 7 (TR Bay 7) load on SPMT; lashing; Transportation and JD (steel set to be delivered to bay area by trailer) | 0.7 | 2026-03-20 | 2026-03-20 | OPERATIONAL | AGI TR Unit 7
119 | TR Unit 7 | TR Unit 7 | 2026-03-21 | A2920 | Turning of AGI TR Unit 7 (TR Bay 7) - 10t Forklift required | 3 | 2026-03-21 | 2026-03-23 | OPERATIONAL | AGI TR Unit 7
120 | TR Unit 7 | TR Unit 7 | 2026-03-22 | A2940 | SPMT shifting back to Port | 0.5 | 2026-03-22 | 2026-03-22 | OPERATIONAL | AGI TR Unit 7
121 | TR Unit 7 | TR Unit 7 | 2026-03-24 | A2930 | Jacking down of AGI TR Unit 7 (TR Bay 7) on temporary support - Forklift required | 1 | 2026-03-24 | 2026-03-24 | OPERATIONAL | AGI TR Unit 7

## Sheet1
No | Type | TR Unit | Date | Activity ID | Activity Name | Duration | Start Date | End Date | Level 1 | Level 2
1 | Mobilization | Mobilization | 2026-01-26 | A1000 | Mobilization of 1st set of SPMT; Asembly + Function Test | 1 | 2026-01-26 | 2026-01-26 | MOBILIZATION | SPMT
2 | Mobilization | Mobilization | 2026-01-26 | A1001 | Mobilization of Marine Equipment and Steelworks | 0.5 | 2026-01-26 | 2026-01-26 | MOBILIZATION | MARINE
3 | Demobilization | Demobilization | 2026-01-28 | A2000 | Demobilization of Marine Equipment and Steelworks | 1 | 2026-01-28 | 2026-01-28 | DEMOBILIZATION | MARINE
4 | Mobilization | Mobilization | 2026-02-01 | A2010 | Mobilization of Jacking Equipment and Steel bridge (prior LCT's arrival to AGI with TR 1&2!)) | 1 | 2026-02-01 | 2026-02-02 | MOBILIZATION | JACKING EQUIPMENT, STEEL BRIDGE
5 | Mobilization | Mobilization | 2026-02-07 | A1010 | Mobilization of 2nd set of SPMT; Assembly + Function test | 1 | 2026-02-07 | 2026-02-07 | MOBILIZATION | SPMT
6 | Demobilization | Demobilization | 2026-03-18 | A1980 | Demobilization of 2nd set of SPMT | 1 | 2026-03-18 | 2026-03-18 | DEMOBILIZATION | SPMT
7 | Demobilization | Demobilization | 2026-03-22 | A1990 | Demobilization of 1st set of SPMT | 1 | 2026-03-22 | 2026-03-23 | DEMOBILIZATION | SPMT
8 | Demobilization | Demobilization | 2026-03-25 | A2020 | Demobilization of Jacking Equipment and Steel bridge | 1 | 2026-03-25 | 2026-03-25 | DEMOBILIZATION | JACKING EQUIPMENT, STEEL BRIDGE
9 | TR Unit 1 | TR Unit 1 | 2026-01-28 | A1002 | Beam Replacement AGI TR Unit 1 (TR Bay 4) - Two 5t forklifts required | 1 | 2026-01-28 | 2026-01-28 | OPERATIONAL | Beam Replacement
10 | TR Unit 1 | TR Unit 1 | 2026-01-28 | A1004 | Deck Preparations (D-ring cutting; marking, steel sets installation) - One 5t forklift and Crane required | 1 | 2026-01-28 | 2026-01-28 | OPERATIONAL | Deck Preparations
11 | TR Unit 1 | TR Unit 1 | 2026-01-29 | A1005 | Deck Preparations (Steel sets installation, welding) - Crane Required for steel sets installation | 1 | 2026-01-29 | 2026-01-29 | OPERATIONAL | Deck Preparations
12 | TR Unit 1 | TR Unit 1 | 2026-01-31 | A1030 | Loading of AGI TR Unit 1 on SPMT; lashing; Shifting to Mina Zayed Port RoRo Jetty area | 0.3 | 2026-01-31 | 2026-01-31 | OPERATIONAL | AGI TR Unit 1
13 | TR Unit 1 | TR Unit 1 | 2026-01-31 | A1040 | RoRo Ramp Installation - 5t Frokift and Crane required | 0.3 | 2026-01-31 | 2026-01-31 | OPERATIONAL | AGI TR Unit 1
14 | TR Unit 1 | TR Unit 1 | 2026-01-31 | A1060 | Load-out of AGL TR Unit 1; stool down (8am-10am) | 0.2 | 2026-01-31 | 2026-01-31 | OPERATIONAL | AGI TR Unit 1
15 | TR Unit 1 | TR Unit 1 | 2026-01-31 | A1070 | RoRo ramp removal; Seafastening AGL TR Unit 1 - Crane required | 1.5 | 2026-01-31 | 2026-02-02 | OPERATIONAL | AGI TR Unit 1
16 | TR Unit 1 | TR Unit 1 | 2026-02-03 | A1081 | MWS; MPI; Sail-away - Marine Transportation by LCT to Al Ghallan Island | 1 | 2026-02-03 | 2026-02-03 | OPERATIONAL | AGI TR Unit 1
17 | TR Unit 1 | TR Unit 1 | 2026-02-04 | A1090 | MMT Crew Mob to AGI; Site Induction; Meeting with Client | 0.5 | 2026-02-04 | 2026-02-04 | OPERATIONAL | AGI TR Unit 1
18 | TR Unit 1 | TR Unit 1 | 2026-02-04 | A1091 | LCT Arrival; Berthing at AGL RoRo Jetty | 0.5 | 2026-02-04 | 2026-02-04 | OPERATIONAL | AGI TR Unit 1
19 | TR Unit 1 | TR Unit 1 | 2026-02-04 | A1100 | Unlashing and cutting; steel sets preparations - Forklift required | 0.5 | 2026-02-04 | 2026-02-04 | OPERATIONAL | AGI TR Unit 1
20 | TR Unit 1 | TR Unit 1 | 2026-02-05 | A1110 | Load-in of AGI TR Unit 1 (including RoRo Ramp Installation); store on Jetty - Crane required | 1 | 2026-02-05 | 2026-02-05 | OPERATIONAL | AGI TR Unit 1
21 | TR Unit 1 | TR Unit 1 | 2026-02-06 | A1121 | LCT Sails back to MZP to collect TR Unit 1 | 1 | 2026-02-06 | 2026-02-06 | OPERATIONAL | AGI TR Unit 1
22 | TR Unit 1 | TR Unit 1 | 2026-02-06 | A1122 | Steel bridge Installation - Crane required | 0.3 | 2026-02-06 | 2026-02-06 | OPERATIONAL | AGI TR Unit 1
23 | TR Unit 1 | TR Unit 1 | 2026-02-06 | A1140 | AGL TR Unit 1 (TR Bay 4) load on SPMT; lashing; Transportation and JD (steel set to be delivered to bay area by trailer) | 0.7 | 2026-02-06 | 2026-02-06 | OPERATIONAL | AGI TR Unit 1
24 | TR Unit 1 | TR Unit 1 | 2026-02-07 | A1141 | Turning of AGI TR Unit 1 (TR Bay 4) - 10t Forklift required | 3 | 2026-02-07 | 2026-02-09 | OPERATIONAL | AGI TR Unit 1
25 | TR Unit 1 | TR Unit 1 | 2026-02-08 | A1181 | SPMT shifting back to Port | 0.5 | 2026-02-08 | 2026-02-08 | OPERATIONAL | AGI TR Unit 1
26 | TR Unit 1 | TR Unit 1 | 2026-02-10 | A1150 | Jacking down of AGI TR Unit 1 (TR Bay 4) on temporary support - Forklift required | 1 | 2026-02-10 | 2026-02-10 | OPERATIONAL | AGI TR Unit 1
27 | TR Unit 2 | TR Unit 2 | 2026-01-29 | A1003 | Beam Replacement AGI TR Unit 2 (TR Bay 3) - Two 5t forklifts required | 1 | 2026-01-29 | 2026-01-29 | OPERATIONAL | Beam Replacement
28 | TR Unit 2 | TR Unit 2 | 2026-02-07 | A2029 | LCT Arrives at MZP; Deck preparations | 1 | 2026-02-07 | 2026-02-07 | OPERATIONAL | AGI TR Unit 2
29 | TR Unit 2 | TR Unit 2 | 2026-02-08 | A2030 | Loading of AGI TR Unit 2 on SPMT; lashing; Shifting to Mina Zayed Port RoRo Jetty area | 0.3 | 2026-02-08 | 2026-02-08 | OPERATIONAL | AGI TR Unit 2
30 | TR Unit 2 | TR Unit 2 | 2026-02-08 | A2040 | RoRo Ramp Installation - 5t Frokift and Crane required | 0.3 | 2026-02-08 | 2026-02-08 | OPERATIONAL | AGI TR Unit 2
31 | TR Unit 2 | TR Unit 2 | 2026-02-08 | A2050 | Load-out of AGL TR Unit 2; stool down | 0.2 | 2026-02-08 | 2026-02-08 | OPERATIONAL | AGI TR Unit 2
32 | TR Unit 2 | TR Unit 2 | 2026-02-08 | A2060 | RoRo ramp removal; Seafastening AGL TR Unit 2 - Crane required | 1.5 | 2026-02-08 | 2026-02-09 | OPERATIONAL | AGI TR Unit 2
33 | TR Unit 2 | TR Unit 2 | 2026-02-10 | A2070 | MWS; MPI; Sail-away - Marine Transportation by LCT to Al Ghallan Island | 1 | 2026-02-10 | 2026-02-10 | OPERATIONAL | AGI TR Unit 2
34 | TR Unit 2 | TR Unit 2 | 2026-02-11 | A2090 | LCT Arrival; Berthing at AGL RoRo Jetty | 0.5 | 2026-02-11 | 2026-02-11 | OPERATIONAL | AGI TR Unit 2
35 | TR Unit 2 | TR Unit 2 | 2026-02-11 | A2100 | Unlashing and cutting; steel sets preparations - Forklift required | 0.5 | 2026-02-11 | 2026-02-11 | OPERATIONAL | AGI TR Unit 2
36 | TR Unit 2 | TR Unit 2 | 2026-02-12 | A2110 | Load-in of AGI TR Unit 2 (including RoRo Ramp Installation); store on Jetty - Crane required | 1 | 2026-02-12 | 2026-02-12 | OPERATIONAL | AGI TR Unit 2
37 | TR Unit 2 | TR Unit 2 | 2026-02-13 | A2120 | LCT Sails back to MZP to collect TR Unit 3 (SPMT to bring back 2pcs of 7.45m transport beam) | 1 | 2026-02-13 | 2026-02-13 | OPERATIONAL | AGI TR Unit 2
38 | TR Unit 2 | TR Unit 2 | 2026-02-13 | A2130 | Steel bridge Installation - Crane required | 0.3 | 2026-02-13 | 2026-02-13 | OPERATIONAL | AGI TR Unit 2
39 | TR Unit 2 | TR Unit 2 | 2026-02-13 | A2140 | AGL TR Unit 2 (TR Bay 3) load on SPMT; lashing; Transportation and JD (steel set to be delivered to bay area by trailer) | 0.7 | 2026-02-13 | 2026-02-13 | OPERATIONAL | AGI TR Unit 2
40 | TR Unit 2 | TR Unit 2 | 2026-02-14 | A2150 | Turning of AGI TR Unit 2 (TR Bay 3) - 10t Forklift required | 3 | 2026-02-14 | 2026-02-16 | OPERATIONAL | AGI TR Unit 2
41 | TR Unit 2 | TR Unit 2 | 2026-02-15 | A2170 | SPMT shifting back to Port | 0.5 | 2026-02-15 | 2026-02-15 | OPERATIONAL | AGI TR Unit 2
42 | TR Unit 2 | TR Unit 2 | 2026-02-17 | A2160 | Jacking down of AGI TR Unit 2 (TR Bay 3) on temporary support - Forklift required | 1 | 2026-02-17 | 2026-02-17 | OPERATIONAL | AGI TR Unit 2
43 | TR Unit 3 | TR Unit 3 | 2026-02-14 | A1013 | Beam Replacement AGI TR Unit 3 (TR Bay 2) - Two 5t forklifts required | 1 | 2026-02-14 | 2026-02-14 | OPERATIONAL | Beam Replacement
44 | TR Unit 3 | TR Unit 3 | 2026-02-14 | A2180 | LCT Arrives at MZP; Deck preparations; Beam replacement | 1 | 2026-02-14 | 2026-02-14 | OPERATIONAL | AGI TR Unit 3
45 | TR Unit 3 | TR Unit 3 | 2026-02-15 | A2190 | Loading of AGI TR Unit 3 on SPMT; lashing; Shifting to Mina Zayed Port RoRo Jetty area | 0.3 | 2026-02-15 | 2026-02-15 | OPERATIONAL | AGI TR Unit 3
46 | TR Unit 3 | TR Unit 3 | 2026-02-15 | A2200 | RoRo Ramp Installation - 5t Frokift and Crane required | 0.3 | 2026-02-15 | 2026-02-15 | OPERATIONAL | AGI TR Unit 3
47 | TR Unit 3 | TR Unit 3 | 2026-02-15 | A2210 | Load-out of AGL TR Unit 3; stool down | 0.2 | 2026-02-15 | 2026-02-15 | OPERATIONAL | AGI TR Unit 3
48 | TR Unit 3 | TR Unit 3 | 2026-02-15 | A2220 | RoRo ramp removal; Seafastening AGL TR Unit 3 - Crane required | 1.5 | 2026-02-15 | 2026-02-16 | OPERATIONAL | AGI TR Unit 3
49 | TR Unit 3 | TR Unit 3 | 2026-02-17 | A2230 | MWS; MPI; Sail-away - Marine Transportation by LCT to Al Ghallan Island | 1 | 2026-02-17 | 2026-02-17 | OPERATIONAL | AGI TR Unit 3
50 | TR Unit 3 | TR Unit 3 | 2026-02-18 | A2250 | LCT Arrival; Berthing at AGL RoRo Jetty | 0.5 | 2026-02-18 | 2026-02-18 | OPERATIONAL | AGI TR Unit 3
51 | TR Unit 3 | TR Unit 3 | 2026-02-18 | A2260 | Unlashing and cutting; steel sets preparations - Forklift required | 0.5 | 2026-02-18 | 2026-02-18 | OPERATIONAL | AGI TR Unit 3
52 | TR Unit 3 | TR Unit 3 | 2026-02-19 | A2270 | Load-in of AGI TR Unit 3 (including RoRo Ramp Installation); store on Jetty - Crane required | 1 | 2026-02-19 | 2026-02-19 | OPERATIONAL | AGI TR Unit 3
53 | TR Unit 3 | TR Unit 3 | 2026-02-20 | A2280 | LCT Sails back to MZP to collect TR Unit 4 | 1 | 2026-02-20 | 2026-02-20 | OPERATIONAL | AGI TR Unit 3
54 | TR Unit 3 | TR Unit 3 | 2026-02-20 | A2290 | Steel bridge Installation - Crane required | 0.3 | 2026-02-20 | 2026-02-20 | OPERATIONAL | AGI TR Unit 3
55 | TR Unit 3 | TR Unit 3 | 2026-02-20 | A2300 | AGL TR Unit 3 (TR Bay 2) load on SPMT; lashing; Transportation and JD (steel set to be delivered to bay area by trailer) | 0.7 | 2026-02-20 | 2026-02-20 | OPERATIONAL | AGI TR Unit 3
56 | TR Unit 3 | TR Unit 3 | 2026-02-21 | A2310 | Turning of AGI TR Unit 3 (TR Bay 2) - 10t Forklift required | 3 | 2026-02-21 | 2026-02-23 | OPERATIONAL | AGI TR Unit 3
57 | TR Unit 3 | TR Unit 3 | 2026-02-22 | A2330 | SPMT shifting back to Port | 0.5 | 2026-02-22 | 2026-02-22 | OPERATIONAL | AGI TR Unit 3
58 | TR Unit 3 | TR Unit 3 | 2026-02-24 | A2320 | Jacking down of AGI TR Unit 3 (TR Bay 2) on temporary support - Forklift required | 1 | 2026-02-24 | 2026-02-24 | OPERATIONAL | AGI TR Unit 3
59 | TR Unit 4 | TR Unit 4 | 2026-02-21 | A1023 | Beam Replacement AGI TR Unit 4 (TR Bay 1) - Two 5t forklifts required | 1 | 2026-02-21 | 2026-02-21 | OPERATIONAL | Beam Replacement
60 | TR Unit 4 | TR Unit 4 | 2026-02-21 | A2340 | LCT Arrives at MZP; Deck preparations; Beam replacement | 1 | 2026-02-21 | 2026-02-21 | OPERATIONAL | AGI TR Unit 4
61 | TR Unit 4 | TR Unit 4 | 2026-02-22 | A2350 | Loading of AGI TR Unit 4 on SPMT; lashing; Shifting to Mina Zayed Port RoRo Jetty area | 0.3 | 2026-02-22 | 2026-02-22 | OPERATIONAL | AGI TR Unit 4
62 | TR Unit 4 | TR Unit 4 | 2026-02-22 | A2360 | RoRo Ramp Installation - 5t Frokift and Crane required | 0.3 | 2026-02-22 | 2026-02-22 | OPERATIONAL | AGI TR Unit 4
63 | TR Unit 4 | TR Unit 4 | 2026-02-22 | A2370 | Load-out of AGL TR Unit 4; stool down | 0.2 | 2026-02-22 | 2026-02-22 | OPERATIONAL | AGI TR Unit 4
64 | TR Unit 4 | TR Unit 4 | 2026-02-22 | A2380 | RoRo ramp removal; Seafastening AGL TR Unit 4 - Crane required | 1.5 | 2026-02-22 | 2026-02-23 | OPERATIONAL | AGI TR Unit 4
65 | TR Unit 4 | TR Unit 4 | 2026-02-24 | A2390 | MWS; MPI; Sail-away - Marine Transportation by LCT to Al Ghallan Island | 1 | 2026-02-24 | 2026-02-24 | OPERATIONAL | AGI TR Unit 4
66 | TR Unit 4 | TR Unit 4 | 2026-02-25 | A2410 | LCT Arrival; Berthing at AGL RoRo Jetty | 0.5 | 2026-02-25 | 2026-02-25 | OPERATIONAL | AGI TR Unit 4
67 | TR Unit 4 | TR Unit 4 | 2026-02-25 | A2420 | Unlashing and cutting; steel sets preparations - Forklift required | 0.5 | 2026-02-25 | 2026-02-25 | OPERATIONAL | AGI TR Unit 4
68 | TR Unit 4 | TR Unit 4 | 2026-02-26 | A2430 | Load-in of AGI TR Unit 4 (including RoRo Ramp Installation); store on Jetty - Crane required | 1 | 2026-02-26 | 2026-02-26 | OPERATIONAL | AGI TR Unit 4
69 | TR Unit 4 | TR Unit 4 | 2026-02-27 | A2440 | LCT Sails back to MZP to collect TR Unit 5 | 1 | 2026-02-27 | 2026-02-27 | OPERATIONAL | AGI TR Unit 4
70 | TR Unit 4 | TR Unit 4 | 2026-02-27 | A2450 | Steel bridge Installation - Crane required | 0.3 | 2026-02-27 | 2026-02-27 | OPERATIONAL | AGI TR Unit 4
71 | TR Unit 4 | TR Unit 4 | 2026-02-27 | A2460 | AGL TR Unit 4 (TR Bay 1) load on SPMT; lashing; Transportation and JD (steel set to be delivered to bay area by trailer) | 0.7 | 2026-02-27 | 2026-02-27 | OPERATIONAL | AGI TR Unit 4
72 | TR Unit 4 | TR Unit 4 | 2026-02-28 | A2470 | Turning of AGI TR Unit 4 (TR Bay 1) - 10t Forklift required | 3 | 2026-02-28 | 2026-03-02 | OPERATIONAL | AGI TR Unit 4
73 | TR Unit 4 | TR Unit 4 | 2026-03-01 | A2490 | SPMT shifting back to Port | 0.5 | 2026-03-01 | 2026-03-01 | OPERATIONAL | AGI TR Unit 4
74 | TR Unit 4 | TR Unit 4 | 2026-03-03 | A2480 | Jacking down of AGI TR Unit 4 (TR Bay 1) on temporary support - Forklift required | 1 | 2026-03-03 | 2026-03-03 | OPERATIONAL | AGI TR Unit 4
75 | TR Unit 5 | TR Unit 5 | 2026-02-28 | A1033 | Beam Replacement AGI TR Unit 5 (TR Bay 5) - Two 5t forklifts required | 1 | 2026-02-28 | 2026-02-28 | OPERATIONAL | Beam Replacement
76 | TR Unit 5 | TR Unit 5 | 2026-02-28 | A2500 | LCT Arrives at MZP; Deck preparations; Beam replacement | 1 | 2026-02-28 | 2026-02-28 | OPERATIONAL | AGI TR Unit 5
77 | TR Unit 5 | TR Unit 5 | 2026-03-01 | A2510 | Loading of AGI TR Unit 5 on SPMT; lashing; Shifting to Mina Zayed Port RoRo Jetty area | 0.3 | 2026-03-01 | 2026-03-01 | OPERATIONAL | AGI TR Unit 5
78 | TR Unit 5 | TR Unit 5 | 2026-03-01 | A2520 | RoRo Ramp Installation - 5t Frokift and Crane required | 0.3 | 2026-03-01 | 2026-03-01 | OPERATIONAL | AGI TR Unit 5
79 | TR Unit 5 | TR Unit 5 | 2026-03-01 | A2530 | Load-out of AGL TR Unit 5; stool down | 0.2 | 2026-03-01 | 2026-03-01 | OPERATIONAL | AGI TR Unit 5
80 | TR Unit 5 | TR Unit 5 | 2026-03-01 | A2540 | RoRo ramp removal; Seafastening AGL TR Unit 5 - Crane required | 1.5 | 2026-03-01 | 2026-03-02 | OPERATIONAL | AGI TR Unit 5
81 | TR Unit 5 | TR Unit 5 | 2026-03-03 | A2550 | MWS; MPI; Sail-away - Marine Transportation by LCT to Al Ghallan Island | 1 | 2026-03-03 | 2026-03-03 | OPERATIONAL | AGI TR Unit 5
82 | TR Unit 5 | TR Unit 5 | 2026-03-04 | A2560 | LCT Arrival; Berthing at AGL RoRo Jetty | 0.5 | 2026-03-04 | 2026-03-04 | OPERATIONAL | AGI TR Unit 5
83 | TR Unit 5 | TR Unit 5 | 2026-03-04 | A2570 | Unlashing and cutting; steel sets preparations - Forklift required | 0.5 | 2026-03-04 | 2026-03-04 | OPERATIONAL | AGI TR Unit 5
84 | TR Unit 5 | TR Unit 5 | 2026-03-05 | A2580 | Load-in of AGI TR Unit 5 (including RoRo Ramp Installation); store on Jetty - Crane required | 1 | 2026-03-05 | 2026-03-05 | OPERATIONAL | AGI TR Unit 5
85 | TR Unit 5 | TR Unit 5 | 2026-03-06 | A2590 | LCT Sails back to MZP to collect TR Unit 6 | 1 | 2026-03-06 | 2026-03-06 | OPERATIONAL | AGI TR Unit 5
86 | TR Unit 5 | TR Unit 5 | 2026-03-06 | A2600 | Steel bridge Installation - Crane required | 0.3 | 2026-03-06 | 2026-03-06 | OPERATIONAL | AGI TR Unit 5
87 | TR Unit 5 | TR Unit 5 | 2026-03-06 | A2610 | AGL TR Unit 5 (TR Bay 5) load on SPMT; lashing; Transportation and JD (steel set to be delivered to bay area by trailer) | 0.7 | 2026-03-06 | 2026-03-06 | OPERATIONAL | AGI TR Unit 5
88 | TR Unit 5 | TR Unit 5 | 2026-03-07 | A2620 | Turning of AGI TR Unit 5 (TR Bay 5) - 10t Forklift required | 3 | 2026-03-07 | 2026-03-09 | OPERATIONAL | AGI TR Unit 5
89 | TR Unit 5 | TR Unit 5 | 2026-03-08 | A2640 | SPMT shifting back to Port | 0.5 | 2026-03-08 | 2026-03-08 | OPERATIONAL | AGI TR Unit 5
90 | TR Unit 5 | TR Unit 5 | 2026-03-10 | A2630 | Jacking down of AGI TR Unit 5 (TR Bay 5) on temporary support - Forklift required | 1 | 2026-03-10 | 2026-03-10 | OPERATIONAL | AGI TR Unit 5
91 | TR Unit 6 | TR Unit 6 | 2026-03-07 | A1043 | Beam Replacement AGI TR Unit 6 (TR Bay 6) - Two 5t forklifts required | 1 | 2026-03-07 | 2026-03-07 | OPERATIONAL | Beam Replacement
92 | TR Unit 6 | TR Unit 6 | 2026-03-07 | A2650 | LCT Arrives at MZP; Deck preparations; Beam replacement | 1 | 2026-03-07 | 2026-03-07 | OPERATIONAL | AGI TR Unit 6
93 | TR Unit 6 | TR Unit 6 | 2026-03-08 | A2660 | Loading of AGI TR Unit 6 on SPMT; lashing; Shifting to Mina Zayed Port RoRo Jetty area | 0.3 | 2026-03-08 | 2026-03-08 | OPERATIONAL | AGI TR Unit 6
94 | TR Unit 6 | TR Unit 6 | 2026-03-08 | A2670 | RoRo Ramp Installation - 5t Frokift and Crane required | 0.3 | 2026-03-08 | 2026-03-08 | OPERATIONAL | AGI TR Unit 6
95 | TR Unit 6 | TR Unit 6 | 2026-03-08 | A2680 | Load-out of AGL TR Unit 6; stool down | 0.2 | 2026-03-08 | 2026-03-08 | OPERATIONAL | AGI TR Unit 6
96 | TR Unit 6 | TR Unit 6 | 2026-03-08 | A2690 | RoRo ramp removal; Seafastening AGL TR Unit 6 - Crane required | 1.5 | 2026-03-08 | 2026-03-09 | OPERATIONAL | AGI TR Unit 6
97 | TR Unit 6 | TR Unit 6 | 2026-03-10 | A2700 | MWS; MPI; Sail-away - Marine Transportation by LCT to Al Ghallan Island | 1 | 2026-03-10 | 2026-03-10 | OPERATIONAL | AGI TR Unit 6
98 | TR Unit 6 | TR Unit 6 | 2026-03-11 | A2710 | LCT Arrival; Berthing at AGL RoRo Jetty | 0.5 | 2026-03-11 | 2026-03-11 | OPERATIONAL | AGI TR Unit 6
99 | TR Unit 6 | TR Unit 6 | 2026-03-11 | A2720 | Unlashing and cutting; steel sets preparations - Forklift required | 0.5 | 2026-03-11 | 2026-03-11 | OPERATIONAL | AGI TR Unit 6
100 | TR Unit 6 | TR Unit 6 | 2026-03-12 | A2730 | Load-in of AGI TR Unit 6 (including RoRo Ramp Installation); store on Jetty - Crane required | 1 | 2026-03-12 | 2026-03-12 | OPERATIONAL | AGI TR Unit 6
101 | TR Unit 6 | TR Unit 6 | 2026-03-13 | A2740 | LCT Sails back to MZP to collect TR Unit 7 | 1 | 2026-03-13 | 2026-03-13 | OPERATIONAL | AGI TR Unit 6
102 | TR Unit 6 | TR Unit 6 | 2026-03-13 | A2750 | Steel bridge Installation - Crane required | 0.3 | 2026-03-13 | 2026-03-13 | OPERATIONAL | AGI TR Unit 6
103 | TR Unit 6 | TR Unit 6 | 2026-03-13 | A2760 | AGL TR Unit 6 (TR Bay 6) load on SPMT; lashing; Transportation and JD (steel set to be delivered to bay area by trailer) | 0.7 | 2026-03-13 | 2026-03-13 | OPERATIONAL | AGI TR Unit 6
104 | TR Unit 6 | TR Unit 6 | 2026-03-14 | A2770 | Turning of AGI TR Unit 6 (TR Bay 6) - 10t Forklift required | 3 | 2026-03-14 | 2026-03-16 | OPERATIONAL | AGI TR Unit 6
105 | TR Unit 6 | TR Unit 6 | 2026-03-15 | A2790 | SPMT shifting back to Port | 0.5 | 2026-03-15 | 2026-03-15 | OPERATIONAL | AGI TR Unit 6
106 | TR Unit 6 | TR Unit 6 | 2026-03-17 | A2780 | Jacking down of AGI TR Unit 6 (TR Bay 6) on temporary support - Forklift required | 1 | 2026-03-17 | 2026-03-17 | OPERATIONAL | AGI TR Unit 6
107 | TR Unit 7 | TR Unit 1 | 2026-03-14 | A1053 | Beam Replacement AGI TR Unit 7 (TR Bay 7) - Two 5t forklifts required | 1 | 2026-03-14 | 2026-03-14 | OPERATIONAL | Beam Replacement
108 | TR Unit 7 | TR Unit 7 | 2026-03-14 | A2800 | LCT Arrives at MZP; Deck preparations; Beam replacement | 1 | 2026-03-14 | 2026-03-14 | OPERATIONAL | AGI TR Unit 7
109 | TR Unit 7 | TR Unit 7 | 2026-03-15 | A2810 | Loading of AGI TR Unit 7 on SPMT; lashing; Shifting to Mina Zayed Port RoRo Jetty area | 0.3 | 2026-03-15 | 2026-03-15 | OPERATIONAL | AGI TR Unit 7
110 | TR Unit 7 | TR Unit 7 | 2026-03-15 | A2820 | RoRo Ramp Installation - 5t Frokift and Crane required | 0.3 | 2026-03-15 | 2026-03-15 | OPERATIONAL | AGI TR Unit 7
111 | TR Unit 7 | TR Unit 7 | 2026-03-15 | A2830 | Load-out of AGL TR Unit 7; stool down | 0.2 | 2026-03-15 | 2026-03-15 | OPERATIONAL | AGI TR Unit 7
112 | TR Unit 7 | TR Unit 7 | 2026-03-15 | A2840 | RoRo ramp removal; Seafastening AGL TR Unit 7 - Crane required | 1.5 | 2026-03-15 | 2026-03-16 | OPERATIONAL | AGI TR Unit 7
113 | TR Unit 7 | TR Unit 7 | 2026-03-17 | A2850 | MWS; MPI; Sail-away - Marine Transportation by LCT to Al Ghallan Island | 1 | 2026-03-17 | 2026-03-17 | OPERATIONAL | AGI TR Unit 7
114 | TR Unit 7 | TR Unit 7 | 2026-03-18 | A2860 | LCT Arrival; Berthing at AGL RoRo Jetty | 0.5 | 2026-03-18 | 2026-03-18 | OPERATIONAL | AGI TR Unit 7
115 | TR Unit 7 | TR Unit 7 | 2026-03-18 | A2870 | Unlashing and cutting; steel sets preparations - Forklift required | 0.5 | 2026-03-18 | 2026-03-18 | OPERATIONAL | AGI TR Unit 7
116 | TR Unit 7 | TR Unit 7 | 2026-03-19 | A2880 | Load-in of AGI TR Unit 7 (including RoRo Ramp Installation); store on Jetty - Crane required | 1 | 2026-03-19 | 2026-03-19 | OPERATIONAL | AGI TR Unit 7
117 | TR Unit 7 | TR Unit 7 | 2026-03-20 | A2900 | Steel bridge Installation - Crane required | 0.3 | 2026-03-20 | 2026-03-20 | OPERATIONAL | AGI TR Unit 7
118 | TR Unit 7 | TR Unit 7 | 2026-03-20 | A2910 | AGL TR Unit 7 (TR Bay 7) load on SPMT; lashing; Transportation and JD (steel set to be delivered to bay area by trailer) | 0.7 | 2026-03-20 | 2026-03-20 | OPERATIONAL | AGI TR Unit 7
119 | TR Unit 7 | TR Unit 7 | 2026-03-21 | A2920 | Turning of AGI TR Unit 7 (TR Bay 7) - 10t Forklift required | 3 | 2026-03-21 | 2026-03-23 | OPERATIONAL | AGI TR Unit 7
120 | TR Unit 7 | TR Unit 7 | 2026-03-22 | A2940 | SPMT shifting back to Port | 0.5 | 2026-03-22 | 2026-03-22 | OPERATIONAL | AGI TR Unit 7
121 | TR Unit 7 | TR Unit 7 | 2026-03-24 | A2930 | Jacking down of AGI TR Unit 7 (TR Bay 7) on temporary support - Forklift required | 1 | 2026-03-24 | 2026-03-24 | OPERATIONAL | AGI TR Unit 7