## meta_contract
key | value
name | TR Dashboard SSOT
version | 0.8.0
timezone | Asia/Dubai
ssot.activity_is_source_of_truth | TRUE
ssot.derived_fields_read_only | TRUE

## meta_policy
key | value
view_modes | ["live", "history", "approval", "compare"]
reflow.snap_direction | forward
reflow.tie_break | ["lock_level", "priority", "planned_start", "activity_id"]
reflow.calendar_granularity_min | 60

## meta_catalog
key | value
enums.activity_state | ["draft", "planned", "committed", "ready", "in_progress", "paused", "blocked", "done", "verified", "cancelled", "aborted"]
enums.lock_level | ["none", "soft", "hard", "baseline"]
enums.blocker_code | ["NONE", "WEATHER", "PTW", "CERT", "RESOURCE", "LINKSPAN", "BARGE"]
enums.dependency_type | ["FS", "SS", "FF", "SF"]
enums.evidence_stage | ["before_start", "before_complete", "after_complete"]
enums.collision_severity | ["minor", "major", "blocking"]
enums.collision_kind | ["dependency_cycle", "dependency_violation", "constraint_window_violation", "resource_overallocated", "resource_unavailable", "spatial_conflict", "baseline_conflict", "data_incomplete", "risk_hold"]
blocker_codes.NONE.code | NONE
blocker_codes.NONE.description | No blocker
blocker_codes.WEATHER.code | WEATHER
blocker_codes.WEATHER.description | Weather constraint
blocker_codes.PTW.code | PTW
blocker_codes.PTW.description | Permit to Work required
blocker_codes.CERT.code | CERT
blocker_codes.CERT.description | Certificate required
blocker_codes.RESOURCE.code | RESOURCE
blocker_codes.RESOURCE.description | Resource unavailable
blocker_codes.LINKSPAN.code | LINKSPAN
blocker_codes.LINKSPAN.description | Linkspan unavailable
blocker_codes.BARGE.code | BARGE
blocker_codes.BARGE.description | Barge unavailable

## trips
_id | trip_id | name | sequence | tr_ids | activity_ids
TRIP_00 | TRIP_00 | Trip 00 | 0 | [] | ['A1000', 'A1010', 'A1001', 'A1006', 'A2010']
TRIP_99 | TRIP_99 | Trip 99 | 99 | [] | ['A1980', 'A1990', 'A1012', 'A2000', 'A1014', 'A2020']
TRIP_01 | TRIP_01 | Trip 01 | 1 | ['TR_01'] | ['A1004', 'A1002', 'A1003', 'A1013', 'A1023', 'A1033', 'A1043', 'A1053', 'A1025', 'A1005', 'A1030', 'A1040', 'A1060', 'A1070', 'A1081', 'A1090', 'A1091', 'A1100', 'A1110', 'A1121', 'A1122', 'A1140', 'A1141', 'A1150', 'A1181']
TRIP_02 | TRIP_02 | Trip 02 | 2 | ['TR_02'] | ['A2029', 'A2030', 'A2040', 'A2050', 'A2060', 'A2070', 'A2090', 'A2100', 'A2110', 'A2120', 'A2130', 'A2140', 'A2150', 'A2160', 'A2170', 'A2180', 'A2190', 'A2200', 'A2210', 'A2220', 'A2230', 'A2250', 'A2260', 'A2270', 'A2280', 'A2290', 'A2300', 'A2310', 'A2320', 'A2330', 'A2340', 'A2350', 'A2360', 'A2370', 'A2380', 'A2390', 'A2410', 'A2420', 'A2430', 'A2440', 'A2450', 'A2460', 'A2470', 'A2480', 'A2490', 'A2500', 'A2510', 'A2520', 'A2530', 'A2540', 'A2550', 'A2560', 'A2570', 'A2580', 'A2590', 'A2600', 'A2610', 'A2620', 'A2630', 'A2640', 'A2650', 'A2660', 'A2670', 'A2680', 'A2690', 'A2700', 'A2710', 'A2720', 'A2730', 'A2740', 'A2750', 'A2760', 'A2770', 'A2780', 'A2790', 'A2800', 'A2810', 'A2820', 'A2830', 'A2840', 'A2850', 'A2860', 'A2870', 'A2880', 'A2900', 'A2910', 'A2920', 'A2930', 'A2940']
TRIP_03 | TRIP_03 | Trip 03 | 3 | ['TR_03'] | ['TR_03_PREP_MZP']
TRIP_04 | TRIP_04 | Trip 04 | 4 | ['TR_04'] | ['TR_04_PREP_MZP']
TRIP_05 | TRIP_05 | Trip 05 | 5 | ['TR_05'] | ['TR_05_PREP_MZP']
TRIP_06 | TRIP_06 | Trip 06 | 6 | ['TR_06'] | ['TR_06_PREP_MZP']
TRIP_07 | TRIP_07 | Trip 07 | 7 | ['TR_07'] | ['TR_07_PREP_MZP']

## trs
_id | tr_id | trip_id | name | sequence | activity_ids | calc.current_activity_id | calc.current_location_id | calc.risk_score
TR_01 | TR_01 | TRIP_01 | TR 01 | 1 | ['A1004', 'A1002', 'A1003', 'A1013', 'A1023', 'A1033', 'A1043', 'A1053', 'A1025', 'A1005', 'A1030', 'A1040', 'A1060', 'A1070', 'A1081', 'A1090', 'A1091', 'A1100', 'A1110', 'A1121', 'A1122', 'A1140', 'A1141', 'A1150', 'A1181']
TR_02 | TR_02 | TRIP_02 | TR 02 | 2 | ['A2029', 'A2030', 'A2040', 'A2050', 'A2060', 'A2070', 'A2090', 'A2100', 'A2110', 'A2120', 'A2130', 'A2140', 'A2150', 'A2160', 'A2170', 'A2180', 'A2190', 'A2200', 'A2210', 'A2220', 'A2230', 'A2250', 'A2260', 'A2270', 'A2280', 'A2290', 'A2300', 'A2310', 'A2320', 'A2330', 'A2340', 'A2350', 'A2360', 'A2370', 'A2380', 'A2390', 'A2410', 'A2420', 'A2430', 'A2440', 'A2450', 'A2460', 'A2470', 'A2480', 'A2490', 'A2500', 'A2510', 'A2520', 'A2530', 'A2540', 'A2550', 'A2560', 'A2570', 'A2580', 'A2590', 'A2600', 'A2610', 'A2620', 'A2630', 'A2640', 'A2650', 'A2660', 'A2670', 'A2680', 'A2690', 'A2700', 'A2710', 'A2720', 'A2730', 'A2740', 'A2750', 'A2760', 'A2770', 'A2780', 'A2790', 'A2800', 'A2810', 'A2820', 'A2830', 'A2840', 'A2850', 'A2860', 'A2870', 'A2880', 'A2900', 'A2910', 'A2920', 'A2930', 'A2940']
TR_03 | TR_03 | TRIP_03 | TR 03 | 3 | ['TR_03_PREP_MZP'] |  |  | 0
TR_04 | TR_04 | TRIP_04 | TR 04 | 4 | ['TR_04_PREP_MZP'] |  |  | 0
TR_05 | TR_05 | TRIP_05 | TR 05 | 5 | ['TR_05_PREP_MZP'] |  |  | 0
TR_06 | TR_06 | TRIP_06 | TR 06 | 6 | ['TR_06_PREP_MZP'] |  |  | 0
TR_07 | TR_07 | TRIP_07 | TR 07 | 7 | ['TR_07_PREP_MZP'] |  |  | 0

## activities
_id | activity_id | type_id | trip_id | tr_ids | title | state | lock_level | blocker_code | evidence_required | evidence_ids | reflow_pins | plan.start_ts | plan.end_ts | plan.duration_min | plan.duration_mode | plan.location.from_location_id | plan.location.to_location_id | plan.location.route_id | plan.location.geo_fence_ids | plan.dependencies | plan.resources | plan.constraints | plan.notes | actual.start_ts | actual.end_ts | actual.progress_pct | actual.location_override | actual.resource_assignments | actual.notes | calc.es_ts | calc.ef_ts | calc.ls_ts | calc.lf_ts | calc.slack_min | calc.critical_path | calc.collision_ids | calc.collision_severity_max | calc.risk_score | calc.predicted_end_ts | calc.reflow.last_preview_run_id | calc.reflow.last_apply_run_id
A1000 | A1000 | mobilization | TRIP_00 | [] | Mobilization of 1st set of SPMT; Asembly + Function Test | planned | none |  | [] | [] | [] | 2026-01-26T00:00:00+04:00 | 2026-01-26T23:59:59+04:00 | 1440 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-01-26T00:00:00+04:00 | 2026-01-26T23:59:59+04:00 | 2026-01-26T00:00:00+04:00 | 2026-01-26T23:59:59+04:00 | 0 | FALSE | []
A1010 | A1010 | mobilization | TRIP_00 | [] | Mobilization of 2nd set of SPMT; Assembly + Function test | planned | none |  | [] | [] | [] | 2026-02-07T00:00:00+04:00 | 2026-02-07T23:59:59+04:00 | 1440 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-02-07T00:00:00+04:00 | 2026-02-07T23:59:59+04:00 | 2026-02-07T00:00:00+04:00 | 2026-02-07T23:59:59+04:00 | 0 | FALSE | []
A1004 | A1004 | transport | TRIP_01 | ['TR_01'] | TR-01 Transit: MZP → AGI | completed | none |  | [] | [] | [] | 2026-01-28T00:00:00+04:00 | 2026-01-28T23:59:59+04:00 | 1440 | work | LOC_MZP | LOC_AGI | ROUTE_MZP_AGI | [] | [] | [] | [] |  | 2026-01-28T08:00:00+04:00 | 2026-01-28T18:00:00+04:00 | 100 |  | [] |  | 2026-01-28T00:00:00+04:00 | 2026-01-28T23:59:59+04:00 | 2026-01-28T00:00:00+04:00 | 2026-01-28T23:59:59+04:00 | 0 | FALSE | []
A1001 | A1001 | mobilization | TRIP_00 | [] | Mobilization of Marine Equipment and Steelworks | planned | none |  | [] | [] | [] | 2026-01-26T00:00:00+04:00 | 2026-01-26T23:59:59+04:00 | 720 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-01-26T00:00:00+04:00 | 2026-01-26T23:59:59+04:00 | 2026-01-26T00:00:00+04:00 | 2026-01-26T23:59:59+04:00 | 0 | FALSE | []
A1006 | A1006 | mobilization | TRIP_00 | [] | JACKING EQUIPMENT, STEEL BRIDGE | planned | none |  | [] | [] | [] | 2026-02-01T00:00:00+04:00 | 2026-02-02T23:59:59+04:00 | 1440 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-02-01T00:00:00+04:00 | 2026-02-02T23:59:59+04:00 | 2026-02-01T00:00:00+04:00 | 2026-02-02T23:59:59+04:00 | 0 | FALSE | []
A2010 | A2010 | mobilization | TRIP_00 | [] | Mobilization of Jacking Equipment and Steel bridge (prior LCT's arrival to AGI with TR 1&2!)) | planned | none |  | [] | [] | [] | 2026-02-01T00:00:00+04:00 | 2026-02-02T23:59:59+04:00 | 1440 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-02-01T00:00:00+04:00 | 2026-02-02T23:59:59+04:00 | 2026-02-01T00:00:00+04:00 | 2026-02-02T23:59:59+04:00 | 0 | FALSE | []
A1980 | A1980 | demobilization | TRIP_99 | [] | Demobilization of 2nd set of SPMT | planned | none |  | [] | [] | [] | 2026-03-18T00:00:00+04:00 | 2026-03-18T23:59:59+04:00 | 1440 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-03-18T00:00:00+04:00 | 2026-03-18T23:59:59+04:00 | 2026-03-18T00:00:00+04:00 | 2026-03-18T23:59:59+04:00 | 0 | FALSE | []
A1990 | A1990 | demobilization | TRIP_99 | [] | Demobilization of 1st set of SPMT | planned | none |  | [] | [] | [] | 2026-03-22T00:00:00+04:00 | 2026-03-23T23:59:59+04:00 | 1440 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-03-22T00:00:00+04:00 | 2026-03-23T23:59:59+04:00 | 2026-03-22T00:00:00+04:00 | 2026-03-23T23:59:59+04:00 | 0 | FALSE | []
A1012 | A1012 | demobilization | TRIP_99 | [] | MARINE | planned | none |  | [] | [] | [] | 2026-01-28T00:00:00+04:00 | 2026-01-28T23:59:59+04:00 | 1440 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-01-28T00:00:00+04:00 | 2026-01-28T23:59:59+04:00 | 2026-01-28T00:00:00+04:00 | 2026-01-28T23:59:59+04:00 | 0 | FALSE | []
A2000 | A2000 | demobilization | TRIP_99 | [] | Demobilization of Marine Equipment and Steelworks | planned | none |  | [] | [] | [] | 2026-01-28T00:00:00+04:00 | 2026-01-28T23:59:59+04:00 | 1440 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-01-28T00:00:00+04:00 | 2026-01-28T23:59:59+04:00 | 2026-01-28T00:00:00+04:00 | 2026-01-28T23:59:59+04:00 | 0 | FALSE | []
A1014 | A1014 | demobilization | TRIP_99 | [] | JACKING EQUIPMENT, STEEL BRIDGE | planned | none |  | [] | [] | [] | 2026-03-25T00:00:00+04:00 | 2026-03-25T23:59:59+04:00 | 1440 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-03-25T00:00:00+04:00 | 2026-03-25T23:59:59+04:00 | 2026-03-25T00:00:00+04:00 | 2026-03-25T23:59:59+04:00 | 0 | FALSE | []
A2020 | A2020 | demobilization | TRIP_99 | [] | Demobilization of Jacking Equipment and Steel bridge | planned | none |  | [] | [] | [] | 2026-03-25T00:00:00+04:00 | 2026-03-25T23:59:59+04:00 | 1440 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-03-25T00:00:00+04:00 | 2026-03-25T23:59:59+04:00 | 2026-03-25T00:00:00+04:00 | 2026-03-25T23:59:59+04:00 | 0 | FALSE | []
A1002 | A1002 | transport | TRIP_01 | ['TR_01'] | Beam Replacement AGI TR Unit 1 (TR Bay 4) - Two 5t forklifts required | planned | none |  | [] | [] | [] | 2026-01-28T00:00:00+04:00 | 2026-01-28T23:59:59+04:00 | 1440 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-01-28T00:00:00+04:00 | 2026-01-28T23:59:59+04:00 | 2026-01-28T00:00:00+04:00 | 2026-01-28T23:59:59+04:00 | 0 | FALSE | []
A1003 | A1003 | transport | TRIP_01 | ['TR_01'] | Beam Replacement AGI TR Unit 2 (TR Bay 3) - Two 5t forklifts required | planned | none |  | [] | [] | [] | 2026-01-29T00:00:00+04:00 | 2026-01-29T23:59:59+04:00 | 1440 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-01-29T00:00:00+04:00 | 2026-01-29T23:59:59+04:00 | 2026-01-29T00:00:00+04:00 | 2026-01-29T23:59:59+04:00 | 0 | FALSE | []
A1013 | A1013 | transport | TRIP_01 | ['TR_01'] | Beam Replacement AGI TR Unit 3 (TR Bay 2) - Two 5t forklifts required | planned | none |  | [] | [] | [] | 2026-02-14T00:00:00+04:00 | 2026-02-14T23:59:59+04:00 | 1440 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-02-14T00:00:00+04:00 | 2026-02-14T23:59:59+04:00 | 2026-02-14T00:00:00+04:00 | 2026-02-14T23:59:59+04:00 | 0 | FALSE | []
A1023 | A1023 | transport | TRIP_01 | ['TR_01'] | Beam Replacement AGI TR Unit 4 (TR Bay 1) - Two 5t forklifts required | planned | none |  | [] | [] | [] | 2026-02-21T00:00:00+04:00 | 2026-02-21T23:59:59+04:00 | 1440 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-02-21T00:00:00+04:00 | 2026-02-21T23:59:59+04:00 | 2026-02-21T00:00:00+04:00 | 2026-02-21T23:59:59+04:00 | 0 | FALSE | []
A1033 | A1033 | transport | TRIP_01 | ['TR_01'] | Beam Replacement AGI TR Unit 5 (TR Bay 5) - Two 5t forklifts required | planned | none |  | [] | [] | [] | 2026-02-28T00:00:00+04:00 | 2026-02-28T23:59:59+04:00 | 1440 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-02-28T00:00:00+04:00 | 2026-02-28T23:59:59+04:00 | 2026-02-28T00:00:00+04:00 | 2026-02-28T23:59:59+04:00 | 0 | FALSE | []
A1043 | A1043 | transport | TRIP_01 | ['TR_01'] | Beam Replacement AGI TR Unit 6 (TR Bay 6) - Two 5t forklifts required | planned | none |  | [] | [] | [] | 2026-03-07T00:00:00+04:00 | 2026-03-07T23:59:59+04:00 | 1440 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-03-07T00:00:00+04:00 | 2026-03-07T23:59:59+04:00 | 2026-03-07T00:00:00+04:00 | 2026-03-07T23:59:59+04:00 | 0 | FALSE | []
A1053 | A1053 | transport | TRIP_01 | ['TR_01'] | Beam Replacement AGI TR Unit 7 (TR Bay 7) - Two 5t forklifts required | planned | none |  | [] | [] | [] | 2026-03-14T00:00:00+04:00 | 2026-03-14T23:59:59+04:00 | 1440 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-03-14T00:00:00+04:00 | 2026-03-14T23:59:59+04:00 | 2026-03-14T00:00:00+04:00 | 2026-03-14T23:59:59+04:00 | 0 | FALSE | []
A1025 | A1025 | transport | TRIP_01 | ['TR_01'] | Deck Preparations | planned | none |  | [] | [] | [] | 2026-01-28T00:00:00+04:00 | 2026-01-29T23:59:59+04:00 | 2880 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-01-28T00:00:00+04:00 | 2026-01-29T23:59:59+04:00 | 2026-01-28T00:00:00+04:00 | 2026-01-29T23:59:59+04:00 | 0 | FALSE | []
A1005 | A1005 | transport | TRIP_01 | ['TR_01'] | Deck Preparations (Steel sets installation, welding) - Crane Required for steel sets installation | planned | none |  | [] | [] | [] | 2026-01-29T00:00:00+04:00 | 2026-01-29T23:59:59+04:00 | 1440 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-01-29T00:00:00+04:00 | 2026-01-29T23:59:59+04:00 | 2026-01-29T00:00:00+04:00 | 2026-01-29T23:59:59+04:00 | 0 | FALSE | []
A1030 | A1030 | transport | TRIP_01 | ['TR_01'] | Loading of AGI TR Unit 1 on SPMT; lashing; Shifting to Mina Zayed Port RoRo Jetty area | planned | none |  | [] | [] | [] | 2026-01-31T00:00:00+04:00 | 2026-01-31T23:59:59+04:00 | 432 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-01-31T00:00:00+04:00 | 2026-01-31T23:59:59+04:00 | 2026-01-31T00:00:00+04:00 | 2026-01-31T23:59:59+04:00 | 0 | FALSE | []
A1040 | A1040 | transport | TRIP_01 | ['TR_01'] | RoRo Ramp Installation - 5t Frokift and Crane required | planned | none |  | [] | [] | [] | 2026-01-31T00:00:00+04:00 | 2026-01-31T23:59:59+04:00 | 432 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-01-31T00:00:00+04:00 | 2026-01-31T23:59:59+04:00 | 2026-01-31T00:00:00+04:00 | 2026-01-31T23:59:59+04:00 | 0 | FALSE | []
A1060 | A1060 | transport | TRIP_01 | ['TR_01'] | Load-out of AGL TR Unit 1; stool down (8am-10am) | planned | none |  | [] | [] | [] | 2026-01-31T00:00:00+04:00 | 2026-01-31T23:59:59+04:00 | 288 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-01-31T00:00:00+04:00 | 2026-01-31T23:59:59+04:00 | 2026-01-31T00:00:00+04:00 | 2026-01-31T23:59:59+04:00 | 0 | FALSE | []
A1070 | A1070 | transport | TRIP_01 | ['TR_01'] | RoRo ramp removal; Seafastening AGL TR Unit 1 - Crane required | planned | none |  | [] | [] | [] | 2026-01-31T00:00:00+04:00 | 2026-02-02T23:59:59+04:00 | 2160 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-01-31T00:00:00+04:00 | 2026-02-02T23:59:59+04:00 | 2026-01-31T00:00:00+04:00 | 2026-02-02T23:59:59+04:00 | 0 | FALSE | []
A1081 | A1081 | transport | TRIP_01 | ['TR_01'] | MWS; MPI; Sail-away - Marine Transportation by LCT to Al Ghallan Island | planned | none |  | [] | [] | [] | 2026-02-03T00:00:00+04:00 | 2026-02-03T23:59:59+04:00 | 1440 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-02-03T00:00:00+04:00 | 2026-02-03T23:59:59+04:00 | 2026-02-03T00:00:00+04:00 | 2026-02-03T23:59:59+04:00 | 0 | FALSE | []
A1090 | A1090 | transport | TRIP_01 | ['TR_01'] | MMT Crew Mob to AGI; Site Induction; Meeting with Client | planned | none |  | [] | [] | [] | 2026-02-04T00:00:00+04:00 | 2026-02-04T23:59:59+04:00 | 720 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-02-04T00:00:00+04:00 | 2026-02-04T23:59:59+04:00 | 2026-02-04T00:00:00+04:00 | 2026-02-04T23:59:59+04:00 | 0 | FALSE | []
A1091 | A1091 | transport | TRIP_01 | ['TR_01'] | LCT Arrival; Berthing at AGL RoRo Jetty | planned | none |  | [] | [] | [] | 2026-02-04T00:00:00+04:00 | 2026-02-04T23:59:59+04:00 | 720 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-02-04T00:00:00+04:00 | 2026-02-04T23:59:59+04:00 | 2026-02-04T00:00:00+04:00 | 2026-02-04T23:59:59+04:00 | 0 | FALSE | []
A1100 | A1100 | transport | TRIP_01 | ['TR_01'] | Unlashing and cutting; steel sets preparations - Forklift required | planned | none |  | [] | [] | [] | 2026-02-04T00:00:00+04:00 | 2026-02-04T23:59:59+04:00 | 720 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-02-04T00:00:00+04:00 | 2026-02-04T23:59:59+04:00 | 2026-02-04T00:00:00+04:00 | 2026-02-04T23:59:59+04:00 | 0 | FALSE | []
A1110 | A1110 | transport | TRIP_01 | ['TR_01'] | Load-in of AGI TR Unit 1 (including RoRo Ramp Installation); store on Jetty - Crane required | planned | none |  | [] | [] | [] | 2026-02-05T00:00:00+04:00 | 2026-02-05T23:59:59+04:00 | 1440 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-02-05T00:00:00+04:00 | 2026-02-05T23:59:59+04:00 | 2026-02-05T00:00:00+04:00 | 2026-02-05T23:59:59+04:00 | 0 | FALSE | []
A1121 | A1121 | transport | TRIP_01 | ['TR_01'] | LCT Sails back to MZP to collect TR Unit 1 | planned | none |  | [] | [] | [] | 2026-02-06T00:00:00+04:00 | 2026-02-06T23:59:59+04:00 | 1440 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-02-06T00:00:00+04:00 | 2026-02-06T23:59:59+04:00 | 2026-02-06T00:00:00+04:00 | 2026-02-06T23:59:59+04:00 | 0 | FALSE | []
A1122 | A1122 | transport | TRIP_01 | ['TR_01'] | Steel bridge Installation - Crane required | planned | none |  | [] | [] | [] | 2026-02-06T00:00:00+04:00 | 2026-02-06T23:59:59+04:00 | 432 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-02-06T00:00:00+04:00 | 2026-02-06T23:59:59+04:00 | 2026-02-06T00:00:00+04:00 | 2026-02-06T23:59:59+04:00 | 0 | FALSE | []
A1140 | A1140 | transport | TRIP_01 | ['TR_01'] | AGL TR Unit 1 (TR Bay 4) load on SPMT; lashing; Transportation and JD (steel set to be delivered to bay area by trailer) | planned | none |  | [] | [] | [] | 2026-02-06T00:00:00+04:00 | 2026-02-06T23:59:59+04:00 | 1008 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-02-06T00:00:00+04:00 | 2026-02-06T23:59:59+04:00 | 2026-02-06T00:00:00+04:00 | 2026-02-06T23:59:59+04:00 | 0 | FALSE | []
A1141 | A1141 | transport | TRIP_01 | ['TR_01'] | Turning of AGI TR Unit 1 (TR Bay 4) - 10t Forklift required | planned | none |  | [] | [] | [] | 2026-02-07T00:00:00+04:00 | 2026-02-09T23:59:59+04:00 | 4320 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-02-07T00:00:00+04:00 | 2026-02-09T23:59:59+04:00 | 2026-02-07T00:00:00+04:00 | 2026-02-09T23:59:59+04:00 | 0 | FALSE | []
A1150 | A1150 | transport | TRIP_01 | ['TR_01'] | Jacking down of AGI TR Unit 1 (TR Bay 4) on temporary support - Forklift required | planned | none |  | [] | [] | [] | 2026-02-10T00:00:00+04:00 | 2026-02-10T23:59:59+04:00 | 1440 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-02-10T00:00:00+04:00 | 2026-02-10T23:59:59+04:00 | 2026-02-10T00:00:00+04:00 | 2026-02-10T23:59:59+04:00 | 0 | FALSE | []
A1181 | A1181 | transport | TRIP_01 | ['TR_01'] | SPMT shifting back to Port | planned | none |  | [] | [] | [] | 2026-02-08T00:00:00+04:00 | 2026-02-08T23:59:59+04:00 | 720 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-02-08T00:00:00+04:00 | 2026-02-08T23:59:59+04:00 | 2026-02-08T00:00:00+04:00 | 2026-02-08T23:59:59+04:00 | 0 | FALSE | []
A2029 | A2029 | transport | TRIP_02 | ['TR_02'] | LCT Arrives at MZP; Deck preparations | planned | none |  | [] | [] | [] | 2026-02-07T00:00:00+04:00 | 2026-02-07T23:59:59+04:00 | 1440 | work | LOC_MZP | LOC_MZP |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-02-07T00:00:00+04:00 | 2026-02-07T23:59:59+04:00 | 2026-02-07T00:00:00+04:00 | 2026-02-07T23:59:59+04:00 | 0 | FALSE | []
A2030 | A2030 | transport | TRIP_02 | ['TR_02'] | Loading of AGI TR Unit 2 on SPMT; lashing; Shifting to Mina Zayed Port RoRo Jetty area | planned | none |  | [] | [] | [] | 2026-02-08T00:00:00+04:00 | 2026-02-08T23:59:59+04:00 | 432 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-02-08T00:00:00+04:00 | 2026-02-08T23:59:59+04:00 | 2026-02-08T00:00:00+04:00 | 2026-02-08T23:59:59+04:00 | 0 | FALSE | []
A2040 | A2040 | transport | TRIP_02 | ['TR_02'] | RoRo Ramp Installation - 5t Frokift and Crane required | planned | none |  | [] | [] | [] | 2026-02-08T00:00:00+04:00 | 2026-02-08T23:59:59+04:00 | 432 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-02-08T00:00:00+04:00 | 2026-02-08T23:59:59+04:00 | 2026-02-08T00:00:00+04:00 | 2026-02-08T23:59:59+04:00 | 0 | FALSE | []
A2050 | A2050 | transport | TRIP_02 | ['TR_02'] | Load-out of AGL TR Unit 2; stool down | planned | none |  | [] | [] | [] | 2026-02-08T00:00:00+04:00 | 2026-02-08T23:59:59+04:00 | 288 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-02-08T00:00:00+04:00 | 2026-02-08T23:59:59+04:00 | 2026-02-08T00:00:00+04:00 | 2026-02-08T23:59:59+04:00 | 0 | FALSE | []
A2060 | A2060 | transport | TRIP_02 | ['TR_02'] | RoRo ramp removal; Seafastening AGL TR Unit 2 - Crane required | planned | none |  | [] | [] | [] | 2026-02-08T00:00:00+04:00 | 2026-02-09T23:59:59+04:00 | 2160 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-02-08T00:00:00+04:00 | 2026-02-09T23:59:59+04:00 | 2026-02-08T00:00:00+04:00 | 2026-02-09T23:59:59+04:00 | 0 | FALSE | []
A2070 | A2070 | transport | TRIP_02 | ['TR_02'] | MWS; MPI; Sail-away - Marine Transportation by LCT to Al Ghallan Island | planned | none |  | [] | [] | [] | 2026-02-10T00:00:00+04:00 | 2026-02-10T23:59:59+04:00 | 1440 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-02-10T00:00:00+04:00 | 2026-02-10T23:59:59+04:00 | 2026-02-10T00:00:00+04:00 | 2026-02-10T23:59:59+04:00 | 0 | FALSE | []
A2090 | A2090 | transport | TRIP_02 | ['TR_02'] | LCT Arrival; Berthing at AGL RoRo Jetty | planned | none |  | [] | [] | [] | 2026-02-11T00:00:00+04:00 | 2026-02-11T23:59:59+04:00 | 720 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-02-11T00:00:00+04:00 | 2026-02-11T23:59:59+04:00 | 2026-02-11T00:00:00+04:00 | 2026-02-11T23:59:59+04:00 | 0 | FALSE | []
A2100 | A2100 | transport | TRIP_02 | ['TR_02'] | Unlashing and cutting; steel sets preparations - Forklift required | planned | none |  | [] | [] | [] | 2026-02-11T00:00:00+04:00 | 2026-02-11T23:59:59+04:00 | 720 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-02-11T00:00:00+04:00 | 2026-02-11T23:59:59+04:00 | 2026-02-11T00:00:00+04:00 | 2026-02-11T23:59:59+04:00 | 0 | FALSE | []
A2110 | A2110 | transport | TRIP_02 | ['TR_02'] | Load-in of AGI TR Unit 2 (including RoRo Ramp Installation); store on Jetty - Crane required | planned | none |  | [] | [] | [] | 2026-02-12T00:00:00+04:00 | 2026-02-12T23:59:59+04:00 | 1440 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-02-12T00:00:00+04:00 | 2026-02-12T23:59:59+04:00 | 2026-02-12T00:00:00+04:00 | 2026-02-12T23:59:59+04:00 | 0 | FALSE | []
A2120 | A2120 | transport | TRIP_02 | ['TR_02'] | LCT Sails back to MZP to collect TR Unit 3 (SPMT to bring back 2pcs of 7.45m transport beam) | planned | none |  | [] | [] | [] | 2026-02-13T00:00:00+04:00 | 2026-02-13T23:59:59+04:00 | 1440 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-02-13T00:00:00+04:00 | 2026-02-13T23:59:59+04:00 | 2026-02-13T00:00:00+04:00 | 2026-02-13T23:59:59+04:00 | 0 | FALSE | []
A2130 | A2130 | transport | TRIP_02 | ['TR_02'] | Steel bridge Installation - Crane required | planned | none |  | [] | [] | [] | 2026-02-13T00:00:00+04:00 | 2026-02-13T23:59:59+04:00 | 432 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-02-13T00:00:00+04:00 | 2026-02-13T23:59:59+04:00 | 2026-02-13T00:00:00+04:00 | 2026-02-13T23:59:59+04:00 | 0 | FALSE | []
A2140 | A2140 | transport | TRIP_02 | ['TR_02'] | AGL TR Unit 2 (TR Bay 3) load on SPMT; lashing; Transportation and JD (steel set to be delivered to bay area by trailer) | planned | none |  | [] | [] | [] | 2026-02-13T00:00:00+04:00 | 2026-02-13T23:59:59+04:00 | 1008 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-02-13T00:00:00+04:00 | 2026-02-13T23:59:59+04:00 | 2026-02-13T00:00:00+04:00 | 2026-02-13T23:59:59+04:00 | 0 | FALSE | []
A2150 | A2150 | transport | TRIP_02 | ['TR_02'] | Turning of AGI TR Unit 2 (TR Bay 3) - 10t Forklift required | planned | none |  | [] | [] | [] | 2026-02-14T00:00:00+04:00 | 2026-02-16T23:59:59+04:00 | 4320 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-02-14T00:00:00+04:00 | 2026-02-16T23:59:59+04:00 | 2026-02-14T00:00:00+04:00 | 2026-02-16T23:59:59+04:00 | 0 | FALSE | []
A2160 | A2160 | transport | TRIP_02 | ['TR_02'] | Jacking down of AGI TR Unit 2 (TR Bay 3) on temporary support - Forklift required | planned | none |  | [] | [] | [] | 2026-02-17T00:00:00+04:00 | 2026-02-17T23:59:59+04:00 | 1440 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-02-17T00:00:00+04:00 | 2026-02-17T23:59:59+04:00 | 2026-02-17T00:00:00+04:00 | 2026-02-17T23:59:59+04:00 | 0 | FALSE | []
A2170 | A2170 | transport | TRIP_02 | ['TR_02'] | SPMT shifting back to Port | planned | none |  | [] | [] | [] | 2026-02-15T00:00:00+04:00 | 2026-02-15T23:59:59+04:00 | 720 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-02-15T00:00:00+04:00 | 2026-02-15T23:59:59+04:00 | 2026-02-15T00:00:00+04:00 | 2026-02-15T23:59:59+04:00 | 0 | FALSE | []
A2180 | A2180 | transport | TRIP_02 | ['TR_02'] | LCT Arrives at MZP; Deck preparations; Beam replacement | planned | none |  | [] | [] | [] | 2026-02-14T00:00:00+04:00 | 2026-02-14T23:59:59+04:00 | 1440 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-02-14T00:00:00+04:00 | 2026-02-14T23:59:59+04:00 | 2026-02-14T00:00:00+04:00 | 2026-02-14T23:59:59+04:00 | 0 | FALSE | []
A2190 | A2190 | transport | TRIP_02 | ['TR_02'] | Loading of AGI TR Unit 3 on SPMT; lashing; Shifting to Mina Zayed Port RoRo Jetty area | planned | none |  | [] | [] | [] | 2026-02-15T00:00:00+04:00 | 2026-02-15T23:59:59+04:00 | 432 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-02-15T00:00:00+04:00 | 2026-02-15T23:59:59+04:00 | 2026-02-15T00:00:00+04:00 | 2026-02-15T23:59:59+04:00 | 0 | FALSE | []
A2200 | A2200 | transport | TRIP_02 | ['TR_02'] | RoRo Ramp Installation - 5t Frokift and Crane required | planned | none |  | [] | [] | [] | 2026-02-15T00:00:00+04:00 | 2026-02-15T23:59:59+04:00 | 432 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-02-15T00:00:00+04:00 | 2026-02-15T23:59:59+04:00 | 2026-02-15T00:00:00+04:00 | 2026-02-15T23:59:59+04:00 | 0 | FALSE | []
A2210 | A2210 | transport | TRIP_02 | ['TR_02'] | Load-out of AGL TR Unit 3; stool down | planned | none |  | [] | [] | [] | 2026-02-15T00:00:00+04:00 | 2026-02-15T23:59:59+04:00 | 288 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-02-15T00:00:00+04:00 | 2026-02-15T23:59:59+04:00 | 2026-02-15T00:00:00+04:00 | 2026-02-15T23:59:59+04:00 | 0 | FALSE | []
A2220 | A2220 | transport | TRIP_02 | ['TR_02'] | RoRo ramp removal; Seafastening AGL TR Unit 3 - Crane required | planned | none |  | [] | [] | [] | 2026-02-15T00:00:00+04:00 | 2026-02-16T23:59:59+04:00 | 2160 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-02-15T00:00:00+04:00 | 2026-02-16T23:59:59+04:00 | 2026-02-15T00:00:00+04:00 | 2026-02-16T23:59:59+04:00 | 0 | FALSE | []
A2230 | A2230 | transport | TRIP_02 | ['TR_02'] | MWS; MPI; Sail-away - Marine Transportation by LCT to Al Ghallan Island | planned | none |  | [] | [] | [] | 2026-02-17T00:00:00+04:00 | 2026-02-17T23:59:59+04:00 | 1440 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-02-17T00:00:00+04:00 | 2026-02-17T23:59:59+04:00 | 2026-02-17T00:00:00+04:00 | 2026-02-17T23:59:59+04:00 | 0 | FALSE | []
A2250 | A2250 | transport | TRIP_02 | ['TR_02'] | LCT Arrival; Berthing at AGL RoRo Jetty | planned | none |  | [] | [] | [] | 2026-02-18T00:00:00+04:00 | 2026-02-18T23:59:59+04:00 | 720 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-02-18T00:00:00+04:00 | 2026-02-18T23:59:59+04:00 | 2026-02-18T00:00:00+04:00 | 2026-02-18T23:59:59+04:00 | 0 | FALSE | []
A2260 | A2260 | transport | TRIP_02 | ['TR_02'] | Unlashing and cutting; steel sets preparations - Forklift required | planned | none |  | [] | [] | [] | 2026-02-18T00:00:00+04:00 | 2026-02-18T23:59:59+04:00 | 720 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-02-18T00:00:00+04:00 | 2026-02-18T23:59:59+04:00 | 2026-02-18T00:00:00+04:00 | 2026-02-18T23:59:59+04:00 | 0 | FALSE | []
A2270 | A2270 | transport | TRIP_02 | ['TR_02'] | Load-in of AGI TR Unit 3 (including RoRo Ramp Installation); store on Jetty - Crane required | planned | none |  | [] | [] | [] | 2026-02-19T00:00:00+04:00 | 2026-02-19T23:59:59+04:00 | 1440 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-02-19T00:00:00+04:00 | 2026-02-19T23:59:59+04:00 | 2026-02-19T00:00:00+04:00 | 2026-02-19T23:59:59+04:00 | 0 | FALSE | []
A2280 | A2280 | transport | TRIP_02 | ['TR_02'] | LCT Sails back to MZP to collect TR Unit 4 | planned | none |  | [] | [] | [] | 2026-02-20T00:00:00+04:00 | 2026-02-20T23:59:59+04:00 | 1440 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-02-20T00:00:00+04:00 | 2026-02-20T23:59:59+04:00 | 2026-02-20T00:00:00+04:00 | 2026-02-20T23:59:59+04:00 | 0 | FALSE | []
A2290 | A2290 | transport | TRIP_02 | ['TR_02'] | Steel bridge Installation - Crane required | planned | none |  | [] | [] | [] | 2026-02-20T00:00:00+04:00 | 2026-02-20T23:59:59+04:00 | 432 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-02-20T00:00:00+04:00 | 2026-02-20T23:59:59+04:00 | 2026-02-20T00:00:00+04:00 | 2026-02-20T23:59:59+04:00 | 0 | FALSE | []
A2300 | A2300 | transport | TRIP_02 | ['TR_02'] | AGL TR Unit 3 (TR Bay 2) load on SPMT; lashing; Transportation and JD (steel set to be delivered to bay area by trailer) | planned | none |  | [] | [] | [] | 2026-02-20T00:00:00+04:00 | 2026-02-20T23:59:59+04:00 | 1008 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-02-20T00:00:00+04:00 | 2026-02-20T23:59:59+04:00 | 2026-02-20T00:00:00+04:00 | 2026-02-20T23:59:59+04:00 | 0 | FALSE | []
A2310 | A2310 | transport | TRIP_02 | ['TR_02'] | Turning of AGI TR Unit 3 (TR Bay 2) - 10t Forklift required | planned | none |  | [] | [] | [] | 2026-02-21T00:00:00+04:00 | 2026-02-23T23:59:59+04:00 | 4320 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-02-21T00:00:00+04:00 | 2026-02-23T23:59:59+04:00 | 2026-02-21T00:00:00+04:00 | 2026-02-23T23:59:59+04:00 | 0 | FALSE | []
A2320 | A2320 | transport | TRIP_02 | ['TR_02'] | Jacking down of AGI TR Unit 3 (TR Bay 2) on temporary support - Forklift required | planned | none |  | [] | [] | [] | 2026-02-24T00:00:00+04:00 | 2026-02-24T23:59:59+04:00 | 1440 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-02-24T00:00:00+04:00 | 2026-02-24T23:59:59+04:00 | 2026-02-24T00:00:00+04:00 | 2026-02-24T23:59:59+04:00 | 0 | FALSE | []
A2330 | A2330 | transport | TRIP_02 | ['TR_02'] | SPMT shifting back to Port | planned | none |  | [] | [] | [] | 2026-02-22T00:00:00+04:00 | 2026-02-22T23:59:59+04:00 | 720 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-02-22T00:00:00+04:00 | 2026-02-22T23:59:59+04:00 | 2026-02-22T00:00:00+04:00 | 2026-02-22T23:59:59+04:00 | 0 | FALSE | []
A2340 | A2340 | transport | TRIP_02 | ['TR_02'] | LCT Arrives at MZP; Deck preparations; Beam replacement | planned | none |  | [] | [] | [] | 2026-02-21T00:00:00+04:00 | 2026-02-21T23:59:59+04:00 | 1440 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-02-21T00:00:00+04:00 | 2026-02-21T23:59:59+04:00 | 2026-02-21T00:00:00+04:00 | 2026-02-21T23:59:59+04:00 | 0 | FALSE | []
A2350 | A2350 | transport | TRIP_02 | ['TR_02'] | Loading of AGI TR Unit 4 on SPMT; lashing; Shifting to Mina Zayed Port RoRo Jetty area | planned | none |  | [] | [] | [] | 2026-02-22T00:00:00+04:00 | 2026-02-22T23:59:59+04:00 | 432 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-02-22T00:00:00+04:00 | 2026-02-22T23:59:59+04:00 | 2026-02-22T00:00:00+04:00 | 2026-02-22T23:59:59+04:00 | 0 | FALSE | []
A2360 | A2360 | transport | TRIP_02 | ['TR_02'] | RoRo Ramp Installation - 5t Frokift and Crane required | planned | none |  | [] | [] | [] | 2026-02-22T00:00:00+04:00 | 2026-02-22T23:59:59+04:00 | 432 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-02-22T00:00:00+04:00 | 2026-02-22T23:59:59+04:00 | 2026-02-22T00:00:00+04:00 | 2026-02-22T23:59:59+04:00 | 0 | FALSE | []
A2370 | A2370 | transport | TRIP_02 | ['TR_02'] | Load-out of AGL TR Unit 4; stool down | planned | none |  | [] | [] | [] | 2026-02-22T00:00:00+04:00 | 2026-02-22T23:59:59+04:00 | 288 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-02-22T00:00:00+04:00 | 2026-02-22T23:59:59+04:00 | 2026-02-22T00:00:00+04:00 | 2026-02-22T23:59:59+04:00 | 0 | FALSE | []
A2380 | A2380 | transport | TRIP_02 | ['TR_02'] | RoRo ramp removal; Seafastening AGL TR Unit 4 - Crane required | planned | none |  | [] | [] | [] | 2026-02-22T00:00:00+04:00 | 2026-02-23T23:59:59+04:00 | 2160 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-02-22T00:00:00+04:00 | 2026-02-23T23:59:59+04:00 | 2026-02-22T00:00:00+04:00 | 2026-02-23T23:59:59+04:00 | 0 | FALSE | []
A2390 | A2390 | transport | TRIP_02 | ['TR_02'] | MWS; MPI; Sail-away - Marine Transportation by LCT to Al Ghallan Island | planned | none |  | [] | [] | [] | 2026-02-24T00:00:00+04:00 | 2026-02-24T23:59:59+04:00 | 1440 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-02-24T00:00:00+04:00 | 2026-02-24T23:59:59+04:00 | 2026-02-24T00:00:00+04:00 | 2026-02-24T23:59:59+04:00 | 0 | FALSE | []
A2410 | A2410 | transport | TRIP_02 | ['TR_02'] | LCT Arrival; Berthing at AGL RoRo Jetty | planned | none |  | [] | [] | [] | 2026-02-25T00:00:00+04:00 | 2026-02-25T23:59:59+04:00 | 720 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-02-25T00:00:00+04:00 | 2026-02-25T23:59:59+04:00 | 2026-02-25T00:00:00+04:00 | 2026-02-25T23:59:59+04:00 | 0 | FALSE | []
A2420 | A2420 | transport | TRIP_02 | ['TR_02'] | Unlashing and cutting; steel sets preparations - Forklift required | planned | none |  | [] | [] | [] | 2026-02-25T00:00:00+04:00 | 2026-02-25T23:59:59+04:00 | 720 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-02-25T00:00:00+04:00 | 2026-02-25T23:59:59+04:00 | 2026-02-25T00:00:00+04:00 | 2026-02-25T23:59:59+04:00 | 0 | FALSE | []
A2430 | A2430 | transport | TRIP_02 | ['TR_02'] | Load-in of AGI TR Unit 4 (including RoRo Ramp Installation); store on Jetty - Crane required | planned | none |  | [] | [] | [] | 2026-02-26T00:00:00+04:00 | 2026-02-26T23:59:59+04:00 | 1440 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-02-26T00:00:00+04:00 | 2026-02-26T23:59:59+04:00 | 2026-02-26T00:00:00+04:00 | 2026-02-26T23:59:59+04:00 | 0 | FALSE | []
A2440 | A2440 | transport | TRIP_02 | ['TR_02'] | LCT Sails back to MZP to collect TR Unit 5 | planned | none |  | [] | [] | [] | 2026-02-27T00:00:00+04:00 | 2026-02-27T23:59:59+04:00 | 1440 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-02-27T00:00:00+04:00 | 2026-02-27T23:59:59+04:00 | 2026-02-27T00:00:00+04:00 | 2026-02-27T23:59:59+04:00 | 0 | FALSE | []
A2450 | A2450 | transport | TRIP_02 | ['TR_02'] | Steel bridge Installation - Crane required | planned | none |  | [] | [] | [] | 2026-02-27T00:00:00+04:00 | 2026-02-27T23:59:59+04:00 | 432 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-02-27T00:00:00+04:00 | 2026-02-27T23:59:59+04:00 | 2026-02-27T00:00:00+04:00 | 2026-02-27T23:59:59+04:00 | 0 | FALSE | []
A2460 | A2460 | transport | TRIP_02 | ['TR_02'] | AGL TR Unit 4 (TR Bay 1) load on SPMT; lashing; Transportation and JD (steel set to be delivered to bay area by trailer) | planned | none |  | [] | [] | [] | 2026-02-27T00:00:00+04:00 | 2026-02-27T23:59:59+04:00 | 1008 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-02-27T00:00:00+04:00 | 2026-02-27T23:59:59+04:00 | 2026-02-27T00:00:00+04:00 | 2026-02-27T23:59:59+04:00 | 0 | FALSE | []
A2470 | A2470 | transport | TRIP_02 | ['TR_02'] | Turning of AGI TR Unit 4 (TR Bay 1) - 10t Forklift required | planned | none |  | [] | [] | [] | 2026-02-28T00:00:00+04:00 | 2026-03-02T23:59:59+04:00 | 4320 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-02-28T00:00:00+04:00 | 2026-03-02T23:59:59+04:00 | 2026-02-28T00:00:00+04:00 | 2026-03-02T23:59:59+04:00 | 0 | FALSE | []
A2480 | A2480 | transport | TRIP_02 | ['TR_02'] | Jacking down of AGI TR Unit 4 (TR Bay 1) on temporary support - Forklift required | planned | none |  | [] | [] | [] | 2026-03-03T00:00:00+04:00 | 2026-03-03T23:59:59+04:00 | 1440 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-03-03T00:00:00+04:00 | 2026-03-03T23:59:59+04:00 | 2026-03-03T00:00:00+04:00 | 2026-03-03T23:59:59+04:00 | 0 | FALSE | []
A2490 | A2490 | transport | TRIP_02 | ['TR_02'] | SPMT shifting back to Port | planned | none |  | [] | [] | [] | 2026-03-01T00:00:00+04:00 | 2026-03-01T23:59:59+04:00 | 720 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-03-01T00:00:00+04:00 | 2026-03-01T23:59:59+04:00 | 2026-03-01T00:00:00+04:00 | 2026-03-01T23:59:59+04:00 | 0 | FALSE | []
A2500 | A2500 | transport | TRIP_02 | ['TR_02'] | LCT Arrives at MZP; Deck preparations; Beam replacement | planned | none |  | [] | [] | [] | 2026-02-28T00:00:00+04:00 | 2026-02-28T23:59:59+04:00 | 1440 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-02-28T00:00:00+04:00 | 2026-02-28T23:59:59+04:00 | 2026-02-28T00:00:00+04:00 | 2026-02-28T23:59:59+04:00 | 0 | FALSE | []
A2510 | A2510 | transport | TRIP_02 | ['TR_02'] | Loading of AGI TR Unit 5 on SPMT; lashing; Shifting to Mina Zayed Port RoRo Jetty area | planned | none |  | [] | [] | [] | 2026-03-01T00:00:00+04:00 | 2026-03-01T23:59:59+04:00 | 432 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-03-01T00:00:00+04:00 | 2026-03-01T23:59:59+04:00 | 2026-03-01T00:00:00+04:00 | 2026-03-01T23:59:59+04:00 | 0 | FALSE | []
A2520 | A2520 | transport | TRIP_02 | ['TR_02'] | RoRo Ramp Installation - 5t Frokift and Crane required | planned | none |  | [] | [] | [] | 2026-03-01T00:00:00+04:00 | 2026-03-01T23:59:59+04:00 | 432 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-03-01T00:00:00+04:00 | 2026-03-01T23:59:59+04:00 | 2026-03-01T00:00:00+04:00 | 2026-03-01T23:59:59+04:00 | 0 | FALSE | []
A2530 | A2530 | transport | TRIP_02 | ['TR_02'] | Load-out of AGL TR Unit 5; stool down | planned | none |  | [] | [] | [] | 2026-03-01T00:00:00+04:00 | 2026-03-01T23:59:59+04:00 | 288 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-03-01T00:00:00+04:00 | 2026-03-01T23:59:59+04:00 | 2026-03-01T00:00:00+04:00 | 2026-03-01T23:59:59+04:00 | 0 | FALSE | []
A2540 | A2540 | transport | TRIP_02 | ['TR_02'] | RoRo ramp removal; Seafastening AGL TR Unit 5 - Crane required | planned | none |  | [] | [] | [] | 2026-03-01T00:00:00+04:00 | 2026-03-02T23:59:59+04:00 | 2160 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-03-01T00:00:00+04:00 | 2026-03-02T23:59:59+04:00 | 2026-03-01T00:00:00+04:00 | 2026-03-02T23:59:59+04:00 | 0 | FALSE | []
A2550 | A2550 | transport | TRIP_02 | ['TR_02'] | MWS; MPI; Sail-away - Marine Transportation by LCT to Al Ghallan Island | planned | none |  | [] | [] | [] | 2026-03-03T00:00:00+04:00 | 2026-03-03T23:59:59+04:00 | 1440 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-03-03T00:00:00+04:00 | 2026-03-03T23:59:59+04:00 | 2026-03-03T00:00:00+04:00 | 2026-03-03T23:59:59+04:00 | 0 | FALSE | []
A2560 | A2560 | transport | TRIP_02 | ['TR_02'] | LCT Arrival; Berthing at AGL RoRo Jetty | planned | none |  | [] | [] | [] | 2026-03-04T00:00:00+04:00 | 2026-03-04T23:59:59+04:00 | 720 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-03-04T00:00:00+04:00 | 2026-03-04T23:59:59+04:00 | 2026-03-04T00:00:00+04:00 | 2026-03-04T23:59:59+04:00 | 0 | FALSE | []
A2570 | A2570 | transport | TRIP_02 | ['TR_02'] | Unlashing and cutting; steel sets preparations - Forklift required | planned | none |  | [] | [] | [] | 2026-03-04T00:00:00+04:00 | 2026-03-04T23:59:59+04:00 | 720 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-03-04T00:00:00+04:00 | 2026-03-04T23:59:59+04:00 | 2026-03-04T00:00:00+04:00 | 2026-03-04T23:59:59+04:00 | 0 | FALSE | []
A2580 | A2580 | transport | TRIP_02 | ['TR_02'] | Load-in of AGI TR Unit 5 (including RoRo Ramp Installation); store on Jetty - Crane required | planned | none |  | [] | [] | [] | 2026-03-05T00:00:00+04:00 | 2026-03-05T23:59:59+04:00 | 1440 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-03-05T00:00:00+04:00 | 2026-03-05T23:59:59+04:00 | 2026-03-05T00:00:00+04:00 | 2026-03-05T23:59:59+04:00 | 0 | FALSE | []
A2590 | A2590 | transport | TRIP_02 | ['TR_02'] | LCT Sails back to MZP to collect TR Unit 6 | planned | none |  | [] | [] | [] | 2026-03-06T00:00:00+04:00 | 2026-03-06T23:59:59+04:00 | 1440 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-03-06T00:00:00+04:00 | 2026-03-06T23:59:59+04:00 | 2026-03-06T00:00:00+04:00 | 2026-03-06T23:59:59+04:00 | 0 | FALSE | []
A2600 | A2600 | transport | TRIP_02 | ['TR_02'] | Steel bridge Installation - Crane required | planned | none |  | [] | [] | [] | 2026-03-06T00:00:00+04:00 | 2026-03-06T23:59:59+04:00 | 432 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-03-06T00:00:00+04:00 | 2026-03-06T23:59:59+04:00 | 2026-03-06T00:00:00+04:00 | 2026-03-06T23:59:59+04:00 | 0 | FALSE | []
A2610 | A2610 | transport | TRIP_02 | ['TR_02'] | AGL TR Unit 5 (TR Bay 5) load on SPMT; lashing; Transportation and JD (steel set to be delivered to bay area by trailer) | planned | none |  | [] | [] | [] | 2026-03-06T00:00:00+04:00 | 2026-03-06T23:59:59+04:00 | 1008 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-03-06T00:00:00+04:00 | 2026-03-06T23:59:59+04:00 | 2026-03-06T00:00:00+04:00 | 2026-03-06T23:59:59+04:00 | 0 | FALSE | []
A2620 | A2620 | transport | TRIP_02 | ['TR_02'] | Turning of AGI TR Unit 5 (TR Bay 5) - 10t Forklift required | planned | none |  | [] | [] | [] | 2026-03-07T00:00:00+04:00 | 2026-03-09T23:59:59+04:00 | 4320 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-03-07T00:00:00+04:00 | 2026-03-09T23:59:59+04:00 | 2026-03-07T00:00:00+04:00 | 2026-03-09T23:59:59+04:00 | 0 | FALSE | []
A2630 | A2630 | transport | TRIP_02 | ['TR_02'] | Jacking down of AGI TR Unit 5 (TR Bay 5) on temporary support - Forklift required | planned | none |  | [] | [] | [] | 2026-03-10T00:00:00+04:00 | 2026-03-10T23:59:59+04:00 | 1440 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-03-10T00:00:00+04:00 | 2026-03-10T23:59:59+04:00 | 2026-03-10T00:00:00+04:00 | 2026-03-10T23:59:59+04:00 | 0 | FALSE | []
A2640 | A2640 | transport | TRIP_02 | ['TR_02'] | SPMT shifting back to Port | planned | none |  | [] | [] | [] | 2026-03-08T00:00:00+04:00 | 2026-03-08T23:59:59+04:00 | 720 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-03-08T00:00:00+04:00 | 2026-03-08T23:59:59+04:00 | 2026-03-08T00:00:00+04:00 | 2026-03-08T23:59:59+04:00 | 0 | FALSE | []
A2650 | A2650 | transport | TRIP_02 | ['TR_02'] | LCT Arrives at MZP; Deck preparations; Beam replacement | planned | none |  | [] | [] | [] | 2026-03-07T00:00:00+04:00 | 2026-03-07T23:59:59+04:00 | 1440 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-03-07T00:00:00+04:00 | 2026-03-07T23:59:59+04:00 | 2026-03-07T00:00:00+04:00 | 2026-03-07T23:59:59+04:00 | 0 | FALSE | []
A2660 | A2660 | transport | TRIP_02 | ['TR_02'] | Loading of AGI TR Unit 6 on SPMT; lashing; Shifting to Mina Zayed Port RoRo Jetty area | planned | none |  | [] | [] | [] | 2026-03-08T00:00:00+04:00 | 2026-03-08T23:59:59+04:00 | 432 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-03-08T00:00:00+04:00 | 2026-03-08T23:59:59+04:00 | 2026-03-08T00:00:00+04:00 | 2026-03-08T23:59:59+04:00 | 0 | FALSE | []
A2670 | A2670 | transport | TRIP_02 | ['TR_02'] | RoRo Ramp Installation - 5t Frokift and Crane required | planned | none |  | [] | [] | [] | 2026-03-08T00:00:00+04:00 | 2026-03-08T23:59:59+04:00 | 432 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-03-08T00:00:00+04:00 | 2026-03-08T23:59:59+04:00 | 2026-03-08T00:00:00+04:00 | 2026-03-08T23:59:59+04:00 | 0 | FALSE | []
A2680 | A2680 | transport | TRIP_02 | ['TR_02'] | Load-out of AGL TR Unit 6; stool down | planned | none |  | [] | [] | [] | 2026-03-08T00:00:00+04:00 | 2026-03-08T23:59:59+04:00 | 288 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-03-08T00:00:00+04:00 | 2026-03-08T23:59:59+04:00 | 2026-03-08T00:00:00+04:00 | 2026-03-08T23:59:59+04:00 | 0 | FALSE | []
A2690 | A2690 | transport | TRIP_02 | ['TR_02'] | RoRo ramp removal; Seafastening AGL TR Unit 6 - Crane required | planned | none |  | [] | [] | [] | 2026-03-08T00:00:00+04:00 | 2026-03-09T23:59:59+04:00 | 2160 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-03-08T00:00:00+04:00 | 2026-03-09T23:59:59+04:00 | 2026-03-08T00:00:00+04:00 | 2026-03-09T23:59:59+04:00 | 0 | FALSE | []
A2700 | A2700 | transport | TRIP_02 | ['TR_02'] | MWS; MPI; Sail-away - Marine Transportation by LCT to Al Ghallan Island | planned | none |  | [] | [] | [] | 2026-03-10T00:00:00+04:00 | 2026-03-10T23:59:59+04:00 | 1440 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-03-10T00:00:00+04:00 | 2026-03-10T23:59:59+04:00 | 2026-03-10T00:00:00+04:00 | 2026-03-10T23:59:59+04:00 | 0 | FALSE | []
A2710 | A2710 | transport | TRIP_02 | ['TR_02'] | LCT Arrival; Berthing at AGL RoRo Jetty | planned | none |  | [] | [] | [] | 2026-03-11T00:00:00+04:00 | 2026-03-11T23:59:59+04:00 | 720 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-03-11T00:00:00+04:00 | 2026-03-11T23:59:59+04:00 | 2026-03-11T00:00:00+04:00 | 2026-03-11T23:59:59+04:00 | 0 | FALSE | []
A2720 | A2720 | transport | TRIP_02 | ['TR_02'] | Unlashing and cutting; steel sets preparations - Forklift required | planned | none |  | [] | [] | [] | 2026-03-11T00:00:00+04:00 | 2026-03-11T23:59:59+04:00 | 720 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-03-11T00:00:00+04:00 | 2026-03-11T23:59:59+04:00 | 2026-03-11T00:00:00+04:00 | 2026-03-11T23:59:59+04:00 | 0 | FALSE | []
A2730 | A2730 | transport | TRIP_02 | ['TR_02'] | Load-in of AGI TR Unit 6 (including RoRo Ramp Installation); store on Jetty - Crane required | planned | none |  | [] | [] | [] | 2026-03-12T00:00:00+04:00 | 2026-03-12T23:59:59+04:00 | 1440 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-03-12T00:00:00+04:00 | 2026-03-12T23:59:59+04:00 | 2026-03-12T00:00:00+04:00 | 2026-03-12T23:59:59+04:00 | 0 | FALSE | []
A2740 | A2740 | transport | TRIP_02 | ['TR_02'] | LCT Sails back to MZP to collect TR Unit 7 | planned | none |  | [] | [] | [] | 2026-03-13T00:00:00+04:00 | 2026-03-13T23:59:59+04:00 | 1440 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-03-13T00:00:00+04:00 | 2026-03-13T23:59:59+04:00 | 2026-03-13T00:00:00+04:00 | 2026-03-13T23:59:59+04:00 | 0 | FALSE | []
A2750 | A2750 | transport | TRIP_02 | ['TR_02'] | Steel bridge Installation - Crane required | planned | none |  | [] | [] | [] | 2026-03-13T00:00:00+04:00 | 2026-03-13T23:59:59+04:00 | 432 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-03-13T00:00:00+04:00 | 2026-03-13T23:59:59+04:00 | 2026-03-13T00:00:00+04:00 | 2026-03-13T23:59:59+04:00 | 0 | FALSE | []
A2760 | A2760 | transport | TRIP_02 | ['TR_02'] | AGL TR Unit 6 (TR Bay 6) load on SPMT; lashing; Transportation and JD (steel set to be delivered to bay area by trailer) | planned | none |  | [] | [] | [] | 2026-03-13T00:00:00+04:00 | 2026-03-13T23:59:59+04:00 | 1008 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-03-13T00:00:00+04:00 | 2026-03-13T23:59:59+04:00 | 2026-03-13T00:00:00+04:00 | 2026-03-13T23:59:59+04:00 | 0 | FALSE | []
A2770 | A2770 | transport | TRIP_02 | ['TR_02'] | Turning of AGI TR Unit 6 (TR Bay 6) - 10t Forklift required | planned | none |  | [] | [] | [] | 2026-03-14T00:00:00+04:00 | 2026-03-16T23:59:59+04:00 | 4320 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-03-14T00:00:00+04:00 | 2026-03-16T23:59:59+04:00 | 2026-03-14T00:00:00+04:00 | 2026-03-16T23:59:59+04:00 | 0 | FALSE | []
A2780 | A2780 | transport | TRIP_02 | ['TR_02'] | Jacking down of AGI TR Unit 6 (TR Bay 6) on temporary support - Forklift required | planned | none |  | [] | [] | [] | 2026-03-17T00:00:00+04:00 | 2026-03-17T23:59:59+04:00 | 1440 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-03-17T00:00:00+04:00 | 2026-03-17T23:59:59+04:00 | 2026-03-17T00:00:00+04:00 | 2026-03-17T23:59:59+04:00 | 0 | FALSE | []
A2790 | A2790 | transport | TRIP_02 | ['TR_02'] | SPMT shifting back to Port | planned | none |  | [] | [] | [] | 2026-03-15T00:00:00+04:00 | 2026-03-15T23:59:59+04:00 | 720 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-03-15T00:00:00+04:00 | 2026-03-15T23:59:59+04:00 | 2026-03-15T00:00:00+04:00 | 2026-03-15T23:59:59+04:00 | 0 | FALSE | []
A2800 | A2800 | transport | TRIP_02 | ['TR_02'] | LCT Arrives at MZP; Deck preparations; Beam replacement | planned | none |  | [] | [] | [] | 2026-03-14T00:00:00+04:00 | 2026-03-14T23:59:59+04:00 | 1440 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-03-14T00:00:00+04:00 | 2026-03-14T23:59:59+04:00 | 2026-03-14T00:00:00+04:00 | 2026-03-14T23:59:59+04:00 | 0 | FALSE | []
A2810 | A2810 | transport | TRIP_02 | ['TR_02'] | Loading of AGI TR Unit 7 on SPMT; lashing; Shifting to Mina Zayed Port RoRo Jetty area | planned | none |  | [] | [] | [] | 2026-03-15T00:00:00+04:00 | 2026-03-15T23:59:59+04:00 | 432 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-03-15T00:00:00+04:00 | 2026-03-15T23:59:59+04:00 | 2026-03-15T00:00:00+04:00 | 2026-03-15T23:59:59+04:00 | 0 | FALSE | []
A2820 | A2820 | transport | TRIP_02 | ['TR_02'] | RoRo Ramp Installation - 5t Frokift and Crane required | planned | none |  | [] | [] | [] | 2026-03-15T00:00:00+04:00 | 2026-03-15T23:59:59+04:00 | 432 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-03-15T00:00:00+04:00 | 2026-03-15T23:59:59+04:00 | 2026-03-15T00:00:00+04:00 | 2026-03-15T23:59:59+04:00 | 0 | FALSE | []
A2830 | A2830 | transport | TRIP_02 | ['TR_02'] | Load-out of AGL TR Unit 7; stool down | planned | none |  | [] | [] | [] | 2026-03-15T00:00:00+04:00 | 2026-03-15T23:59:59+04:00 | 288 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-03-15T00:00:00+04:00 | 2026-03-15T23:59:59+04:00 | 2026-03-15T00:00:00+04:00 | 2026-03-15T23:59:59+04:00 | 0 | FALSE | []
A2840 | A2840 | transport | TRIP_02 | ['TR_02'] | RoRo ramp removal; Seafastening AGL TR Unit 7 - Crane required | planned | none |  | [] | [] | [] | 2026-03-15T00:00:00+04:00 | 2026-03-16T23:59:59+04:00 | 2160 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-03-15T00:00:00+04:00 | 2026-03-16T23:59:59+04:00 | 2026-03-15T00:00:00+04:00 | 2026-03-16T23:59:59+04:00 | 0 | FALSE | []
A2850 | A2850 | transport | TRIP_02 | ['TR_02'] | MWS; MPI; Sail-away - Marine Transportation by LCT to Al Ghallan Island | planned | none |  | [] | [] | [] | 2026-03-17T00:00:00+04:00 | 2026-03-17T23:59:59+04:00 | 1440 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-03-17T00:00:00+04:00 | 2026-03-17T23:59:59+04:00 | 2026-03-17T00:00:00+04:00 | 2026-03-17T23:59:59+04:00 | 0 | FALSE | []
A2860 | A2860 | transport | TRIP_02 | ['TR_02'] | LCT Arrival; Berthing at AGL RoRo Jetty | planned | none |  | [] | [] | [] | 2026-03-18T00:00:00+04:00 | 2026-03-18T23:59:59+04:00 | 720 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-03-18T00:00:00+04:00 | 2026-03-18T23:59:59+04:00 | 2026-03-18T00:00:00+04:00 | 2026-03-18T23:59:59+04:00 | 0 | FALSE | []
A2870 | A2870 | transport | TRIP_02 | ['TR_02'] | Unlashing and cutting; steel sets preparations - Forklift required | planned | none |  | [] | [] | [] | 2026-03-18T00:00:00+04:00 | 2026-03-18T23:59:59+04:00 | 720 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-03-18T00:00:00+04:00 | 2026-03-18T23:59:59+04:00 | 2026-03-18T00:00:00+04:00 | 2026-03-18T23:59:59+04:00 | 0 | FALSE | []
A2880 | A2880 | transport | TRIP_02 | ['TR_02'] | Load-in of AGI TR Unit 7 (including RoRo Ramp Installation); store on Jetty - Crane required | planned | none |  | [] | [] | [] | 2026-03-19T00:00:00+04:00 | 2026-03-19T23:59:59+04:00 | 1440 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-03-19T00:00:00+04:00 | 2026-03-19T23:59:59+04:00 | 2026-03-19T00:00:00+04:00 | 2026-03-19T23:59:59+04:00 | 0 | FALSE | []
A2900 | A2900 | transport | TRIP_02 | ['TR_02'] | Steel bridge Installation - Crane required | planned | none |  | [] | [] | [] | 2026-03-20T00:00:00+04:00 | 2026-03-20T23:59:59+04:00 | 432 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-03-20T00:00:00+04:00 | 2026-03-20T23:59:59+04:00 | 2026-03-20T00:00:00+04:00 | 2026-03-20T23:59:59+04:00 | 0 | FALSE | []
A2910 | A2910 | transport | TRIP_02 | ['TR_02'] | AGL TR Unit 7 (TR Bay 7) load on SPMT; lashing; Transportation and JD (steel set to be delivered to bay area by trailer) | planned | none |  | [] | [] | [] | 2026-03-20T00:00:00+04:00 | 2026-03-20T23:59:59+04:00 | 1008 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-03-20T00:00:00+04:00 | 2026-03-20T23:59:59+04:00 | 2026-03-20T00:00:00+04:00 | 2026-03-20T23:59:59+04:00 | 0 | FALSE | []
A2920 | A2920 | transport | TRIP_02 | ['TR_02'] | Turning of AGI TR Unit 7 (TR Bay 7) - 10t Forklift required | planned | none |  | [] | [] | [] | 2026-03-21T00:00:00+04:00 | 2026-03-23T23:59:59+04:00 | 4320 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-03-21T00:00:00+04:00 | 2026-03-23T23:59:59+04:00 | 2026-03-21T00:00:00+04:00 | 2026-03-23T23:59:59+04:00 | 0 | FALSE | []
A2930 | A2930 | transport | TRIP_02 | ['TR_02'] | Jacking down of AGI TR Unit 7 (TR Bay 7) on temporary support - Forklift required | planned | none |  | [] | [] | [] | 2026-03-24T00:00:00+04:00 | 2026-03-24T23:59:59+04:00 | 1440 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-03-24T00:00:00+04:00 | 2026-03-24T23:59:59+04:00 | 2026-03-24T00:00:00+04:00 | 2026-03-24T23:59:59+04:00 | 0 | FALSE | []
A2940 | A2940 | transport | TRIP_02 | ['TR_02'] | SPMT shifting back to Port | planned | none |  | [] | [] | [] | 2026-03-22T00:00:00+04:00 | 2026-03-22T23:59:59+04:00 | 720 | work |  |  |  | [] | [] | [] | [] | [5 empty] | [] |  | 2026-03-22T00:00:00+04:00 | 2026-03-22T23:59:59+04:00 | 2026-03-22T00:00:00+04:00 | 2026-03-22T23:59:59+04:00 | 0 | FALSE | []
TR_03_PREP_MZP | TR_03_PREP_MZP | preparation | TRIP_03 | ['TR_03'] | TR 03 Preparation at MZP | planned | none |  | [] | [] | [] | 2026-02-10T00:00:00+04:00 | 2026-02-10T23:59:59+04:00 | 1440 | work | LOC_MZP | LOC_MZP |  | [] | [] | [] | [] | Placeholder activity for TR 03 at Mina Zayed Port |  |  |  |  | [] |  | 2026-02-10T00:00:00+04:00 | 2026-02-10T23:59:59+04:00 | 2026-02-10T00:00:00+04:00 | 2026-02-10T23:59:59+04:00 | 0 | FALSE | []
TR_04_PREP_MZP | TR_04_PREP_MZP | preparation | TRIP_04 | ['TR_04'] | TR 04 Preparation at MZP | planned | none |  | [] | [] | [] | 2026-02-10T00:00:00+04:00 | 2026-02-10T23:59:59+04:00 | 1440 | work | LOC_MZP | LOC_MZP |  | [] | [] | [] | [] | Placeholder activity for TR 04 at Mina Zayed Port |  |  |  |  | [] |  | 2026-02-10T00:00:00+04:00 | 2026-02-10T23:59:59+04:00 | 2026-02-10T00:00:00+04:00 | 2026-02-10T23:59:59+04:00 | 0 | FALSE | []
TR_05_PREP_MZP | TR_05_PREP_MZP | preparation | TRIP_05 | ['TR_05'] | TR 05 Preparation at MZP | planned | none |  | [] | [] | [] | 2026-02-10T00:00:00+04:00 | 2026-02-10T23:59:59+04:00 | 1440 | work | LOC_MZP | LOC_MZP |  | [] | [] | [] | [] | Placeholder activity for TR 05 at Mina Zayed Port |  |  |  |  | [] |  | 2026-02-10T00:00:00+04:00 | 2026-02-10T23:59:59+04:00 | 2026-02-10T00:00:00+04:00 | 2026-02-10T23:59:59+04:00 | 0 | FALSE | []
TR_06_PREP_MZP | TR_06_PREP_MZP | preparation | TRIP_06 | ['TR_06'] | TR 06 Preparation at MZP | planned | none |  | [] | [] | [] | 2026-02-10T00:00:00+04:00 | 2026-02-10T23:59:59+04:00 | 1440 | work | LOC_MZP | LOC_MZP |  | [] | [] | [] | [] | Placeholder activity for TR 06 at Mina Zayed Port |  |  |  |  | [] |  | 2026-02-10T00:00:00+04:00 | 2026-02-10T23:59:59+04:00 | 2026-02-10T00:00:00+04:00 | 2026-02-10T23:59:59+04:00 | 0 | FALSE | []
TR_07_PREP_MZP | TR_07_PREP_MZP | preparation | TRIP_07 | ['TR_07'] | TR 07 Preparation at MZP | planned | none |  | [] | [] | [] | 2026-02-10T00:00:00+04:00 | 2026-02-10T23:59:59+04:00 | 1440 | work | LOC_MZP | LOC_MZP |  | [] | [] | [] | [] | Placeholder activity for TR 07 at Mina Zayed Port |  |  |  |  | [] |  | 2026-02-10T00:00:00+04:00 | 2026-02-10T23:59:59+04:00 | 2026-02-10T00:00:00+04:00 | 2026-02-10T23:59:59+04:00 | 0 | FALSE | []

## locations
_id | location_id | name | lat | lon | zone | notes
LOC_MZP | LOC_MZP | Mina Zayed Port | 24.5249 | 54.378 | port | Main port facility - Corrected coordinates
LOC_AGI | LOC_AGI | AGI Jetty (Al Ghallan Island) | 24.8411 | 53.6586 | offshore | Al Ghallan Island destination

## baselines_meta
key | value
current_baseline_id

## history_events
event_id | timestamp | event_type | actor | activity_id | delta.entities.locations.new.LOC_MZP | delta.entities.locations.new.LOC_AGI | delta.entities.trs.old | delta.entities.trs.new | delta.state.old | delta.state.new | delta.actual.start_ts.old | delta.actual.start_ts.new | delta.actual.end_ts.old | delta.actual.end_ts.new | delta.plan.location.to_location_id.old | delta.plan.location.to_location_id.new | metadata.location_id | metadata.location_name | metadata.old_coordinates.lat | metadata.old_coordinates.lon | metadata.new_coordinates.lat | metadata.new_coordinates.lon | metadata.reason | metadata.offset_meters
EVT_1770232731268_LOC_INIT | 2026-02-04T19:18:51+04:00 | location_data_initialization | tr-implementer |  | added | added
EVT_1770232731268_TR_CREATED | 2026-02-04T19:18:51+04:00 | tr_entities_created | tr-implementer |  |  |  | ['TR_01', 'TR_02'] | ['TR_01', 'TR_02', 'TR_03', 'TR_04', 'TR_05', 'TR_06', 'TR_07']
EVT_1770232731268_TR01_AGI | 2026-02-04T19:18:51+04:00 | actual_completed | tr-implementer | A1004 |  |  |  |  | planned | done |  | 2026-01-28T08:00:00+04:00 |  | 2026-01-28T18:00:00+04:00 |  | LOC_AGI
EVT_1770237900000_LOC_MZP_COORD_FIX | 2026-02-04T20:45:00+04:00 | location_coordinates_corrected | system | [13 empty] | LOC_MZP | Mina Zayed Port | 24.5327 | 54.3782 | 24.5249 | 54.378 | Corrected to accurate Mina Zayed Port coordinates | ~870m correction (north to south)