## adnoc
SN | Date | DURATION TIMES | DURATION HRS | DURATION DAYS | Activity | level1 | level2 | activity_id | activity_name
1 | 2026-01-25 | 04:30 Hrs | 25.5 | 1.06 | Vessel released from shipping and sailed to MZP anchorage to berth on 26 Jan 2026 as requested by SCT. | MOBILIZATION | MARINE |  | MARINE
2 | 2026-01-26 | 06:00 Hrs | 35.63 | 1.48 | Vessel remained at anchorage as Berth wasn’t secured | MOBILIZATION | MARINE | A1001 | Mobilization of Marine Equipment and Steelworks
3 | 2026-01-27 | 17:38 Hrs | 23.37 | 0.97 | Bushra Berthed at MZP RoRo Berth No. 5 | OPERATIONAL | Deck Preparations | A1004 | Deck Preparations (D-ring cutting; marking, steel sets installation) - One 5t forklift and Crane required
4 | 2026-01-28 | 17:00 Hrs | 65.5 | 2.73 | Grillage, stools installed and welding completed onboard Bushra. | OPERATIONAL | Deck Preparations | A1005 | Deck Preparations (Steel sets installation, welding) - Crane Required for steel sets installation
5 | 2026-01-31 | 10:30 Hrs | 0.5 | 0.02 | Loading Permission received by MZP Harbor Master. | OPERATIONAL | AGI TR Unit 1 | A1060 | Load-out of AGL TR Unit 1; stool down (8am-10am)
6 | 2026-01-31 | 11:00 Hrs | 9.6 | 0.4 | Loading TR No. 1 Completed | OPERATIONAL | AGI TR Unit 1 | A1070 | RoRo ramp removal; Seafastening AGL TR Unit 1 - Crane required
7 | 2026-01-31 | 20:36 Hrs | 9.4 | 0.39 | MWS Sail away certificate was received Bushra Cast off MZP | OPERATIONAL | AGI TR Unit 1 | A1070 | RoRo ramp removal; Seafastening AGL TR Unit 1 - Crane required
8 | 2026-02-01 | 06:00 Hrs | 47 | 1.96 | Bushra Dropped anchor at Al Ghallan Anchorage waiting for Berth | OPERATIONAL | AGI TR Unit 1 | A1081 | MWS; MPI; Sail-away - Marine Transportation by LCT to Al Ghallan Island
9 | 2026-02-03 | 05:00 Hrs | 35.1 | 1.46 | MMT team travelled from Mina Port to AGI for TR No. 1 offloading | OPERATIONAL | AGI TR Unit 1 | A1090 | MMT Crew Mob to AGI; Site Induction; Meeting with Client
10 | 2026-02-04 | 16:06 Hrs | 4.4 | 0.18 | Bushra Berthed alongside West RoRo Berth No. 3 at AGI | OPERATIONAL | AGI TR Unit 1 | A1091 | LCT Arrival; Berthing at AGL RoRo Jetty
11 | 2026-02-04 | 20:30 Hrs | 86.5 | 3.6 | J62 arrived to AGI with Lifting clamps for TR No. 1 offloading | OPERATIONAL | AGI TR Unit 1 | A1122 | Steel bridge Installation - Crane required
12 | 2026-02-08 | 11:00 Hrs | 3.63 | 0.15 | Tr No. 1 Offloaded at AGI | OPERATIONAL | AGI TR Unit 1 | A1150 | Jacking down of AGI TR Unit 1 (TR Bay 4) on temporary support - Forklift required
13 | 2026-02-08 | 14:38 Hrs | 8.07 | 0.34 | Bushra Sailed from AGI | OPERATIONAL | AGI TR Unit 1 | A1121 | LCT Sails back to MZP to collect TR Unit 1
14 | 2026-02-08 | 08:04 Hrs | 8.07 | 0.34 | Bushra dropped anchor at MZP anchorage waiting for berth | OPERATIONAL | AGI TR Unit 1 | A1121 | LCT Sails back to MZP to collect TR Unit 1