## Bushra
NO | START DATE | START TIME | END DATE | END TIME | DURATION TIMES | DURATION HRS | DURATION DAYS | Activity | level1 | level2 | activity_id | activity_name
1 | 2026-01-27 | 0:00 | 2026-01-28 | 9:00 | 33:00 HRS | 33 | 1.38 | SECURED ALONGSIDE MINA ZAYED RORO BERTH /PILOT OFF | OPERATIONAL | Deck Preparations | A1004 | Deck Preparations (D-ring cutting; marking, steel sets installation) - One 5t forklift and Crane required
2 | 2026-01-28 | 0:00 | 2026-01-28 | 10:12 | 10:12 HRS | 10.2 | 0.42 | COMMENCE DECK PREPARATION | OPERATIONAL | Deck Preparations | A1005 | Deck Preparations (Steel sets installation, welding) - Crane Required for steel sets installation
3 | 2026-01-28 | 0:00 | 2026-01-28 | 10:30 | 10:30 HRS | 10.5 | 0.44 | START CUTTING PAD EYE | OPERATIONAL | Deck Preparations | A1005 | Deck Preparations (Steel sets installation, welding) - Crane Required for steel sets installation
4 | 2026-01-28 | 0:00 | 2026-01-28 | 13:00 | 13:00 HRS | 13 | 0.54 | RAMP DOOR LOWERED | OPERATIONAL | Deck Preparations | A1005 | Deck Preparations (Steel sets installation, welding) - Crane Required for steel sets installation
5 | 2026-01-28 | 0:00 | 2026-01-28 | 14:24 | 14:24 HRS | 14.4 | 0.6 | LUNCH BREAK | OPERATIONAL | Deck Preparations | A1005 | Deck Preparations (Steel sets installation, welding) - Crane Required for steel sets installation
6 | 2026-01-28 | 0:00 | 2026-01-28 | 15:00 | 15:00 HRS | 15 | 0.62 | RESUME DECK PREPARATION WORK | OPERATIONAL | Deck Preparations | A1005 | Deck Preparations (Steel sets installation, welding) - Crane Required for steel sets installation
7 | 2026-01-28 | 0:00 | 2026-01-29 | 0:00 | 24:00 HRS | 24 | 1 | STOP DECK PREPARATION WORK | OPERATIONAL | Deck Preparations | A1005 | Deck Preparations (Steel sets installation, welding) - Crane Required for steel sets installation
8 | 2026-01-29 | 0:00 | 2026-01-30 | 0:00 | 24:00 HRS | 24 | 1 | MINA ZAYED PORT | OPERATIONAL | Deck Preparations |  | Waiting at MZP for load-out
9 | 2026-01-30 | 0:00 | 2026-01-31 | 0:00 | 24:00 HRS | 24 | 1 | MINA ZAYED PORT | OPERATIONAL | AGI TR Unit 1 | A1070 | RoRo ramp removal; Seafastening AGL TR Unit 1 - Crane required
10 | 2026-01-31 | 0:00 | 2026-01-31 | 1:45 | 01:45 HRS | 1.75 | 0.07 | MINA ZAYED PORT/ DECK PREPARATION IN PROGRESS | OPERATIONAL | AGI TR Unit 1 | A1070 | RoRo ramp removal; Seafastening AGL TR Unit 1 - Crane required
11 | 2026-01-31 | 0:00 | 2026-01-31 | 10:30 | 10:30 HRS | 10.5 | 0.44 | COMMENCE PUMPING WATER TRANSFER TO TANKER TRUCK | OPERATIONAL | AGI TR Unit 1 | A1070 | RoRo ramp removal; Seafastening AGL TR Unit 1 - Crane required
12 | 2026-01-31 | 0:00 | 2026-01-31 | 10:51 | 10:51 HRS | 10.85 | 0.45 | COMMENCE LOADING TRANSFORMER CARGO | OPERATIONAL | AGI TR Unit 1 | A1070 | RoRo ramp removal; Seafastening AGL TR Unit 1 - Crane required
13 | 2026-01-31 | 0:00 | 2026-01-31 | 10:54 | 10:54 HRS | 10.9 | 0.45 | TRANSFORMER IN POSITION | OPERATIONAL | AGI TR Unit 1 | A1070 | RoRo ramp removal; Seafastening AGL TR Unit 1 - Crane required
14 | 2026-01-31 | 0:00 | 2026-01-31 | 13:00 | 13:00 HRS | 13 | 0.54 | COMPLETE TRANSFORMER INSPECTION | OPERATIONAL | AGI TR Unit 1 | A1070 | RoRo ramp removal; Seafastening AGL TR Unit 1 - Crane required
15 | 2026-01-31 | 0:00 | 2026-01-31 | 13:45 | 13:45 HRS | 13.75 | 0.57 | LUNCH BREAK | OPERATIONAL | AGI TR Unit 1 | A1070 | RoRo ramp removal; Seafastening AGL TR Unit 1 - Crane required
16 | 2026-01-31 | 0:00 | 2026-01-31 | 15:00 | 15:00 HRS | 15 | 0.62 | RESUME CARGO SECURING JOB AND WELDING | OPERATIONAL | AGI TR Unit 1 | A1070 | RoRo ramp removal; Seafastening AGL TR Unit 1 - Crane required
17 | 2026-01-31 | 0:00 | 2026-01-31 | 16:45 | 16:45 HRS | 16.75 | 0.7 | COMMENCE DISCHARGE PORTABLE GENERATOR WELDING SECURING IN PROGRESS | OPERATIONAL | AGI TR Unit 1 | A1070 | RoRo ramp removal; Seafastening AGL TR Unit 1 - Crane required
18 | 2026-01-31 | 0:00 | 2026-01-31 | 20:24 | 20:24 HRS | 20.4 | 0.85 | COMPLETED LASHING AND SECURING JOB/NDT COMPLETED | OPERATIONAL | AGI TR Unit 1 | A1070 | RoRo ramp removal; Seafastening AGL TR Unit 1 - Crane required
19 | 2026-01-31 | 0:00 | 2026-01-31 | 20:30 | 20:30 HRS | 20.5 | 0.85 | PILOT ONBOARD - CASTED OFF MZP | OPERATIONAL | AGI TR Unit 1 | A1070 | RoRo ramp removal; Seafastening AGL TR Unit 1 - Crane required
20 | 2026-01-31 | 0:00 | 2026-01-31 | 21:00 | 21:00 HRS | 21 | 0.88 | PILOT OFF - MANOUVRE OT AL GHALLAN | OPERATIONAL | AGI TR Unit 1 | A1070 | RoRo ramp removal; Seafastening AGL TR Unit 1 - Crane required
21 | 2026-01-31 | 0:00 | 2026-02-01 | 6:00 | 30:00 HRS | 30 | 1.25 | CLEAR MINA ZAYED CHANNEL | OPERATIONAL | AGI TR Unit 1 | A1081 | MWS; MPI; Sail-away - Marine Transportation by LCT to Al Ghallan Island
22 | 2026-02-01 | 0:00 | 2026-02-02 | 0:00 | 24:00 HRS | 24 | 1 | DROPPED ANCHOR AT SOUTH ZAKUM AREA WAITING INSTRUCTIONS | OPERATIONAL | AGI TR Unit 1 | A1081 | MWS; MPI; Sail-away - Marine Transportation by LCT to Al Ghallan Island
23 | 2026-02-02 | 0:00 | 2026-02-03 | 0:00 | 24:00 HRS | 24 | 1 | DROPPED ANCHOR AT SOUTH ZAKUM AREA WAITING INSTRUCTIONS | OPERATIONAL | AGI TR Unit 1 | A1090 | MMT Crew Mob to AGI; Site Induction; Meeting with Client
24 | 2026-02-03 | 0:00 | 2026-02-04 | 0:00 | 24:00 HRS | 24 | 1 | DROPPED ANCHOR AT SOUTH ZAKUM AREA WAITING INSTRUCTIONS | OPERATIONAL | AGI TR Unit 1 | A1110 | Load-in of AGI TR Unit 1 (including RoRo Ramp Installation); store on Jetty - Crane required
25 | 2026-02-04 | 0:00 | 2026-02-04 | 12:12 | 12:12 HRS | 12.2 | 0.51 | DROPPED ANCHOR AT SOUTH ZAKUM AREA WAITING INSTRUCTIONS | OPERATIONAL | AGI TR Unit 1 | A1091 | LCT Arrival; Berthing at AGL RoRo Jetty
26 | 2026-02-04 | 0:00 | 2026-02-04 | 12:18 | 12:18 HRS | 12.3 | 0.51 | START HEAVE UP ANCHOR | OPERATIONAL | AGI TR Unit 1 | A1091 | LCT Arrival; Berthing at AGL RoRo Jetty
27 | 2026-02-04 | 0:00 | 2026-02-04 | 13:48 | 13:48 HRS | 13.8 | 0.57 | ANCHOR AWEIGH PROCEED TO AL GHALLAN | OPERATIONAL | AGI TR Unit 1 | A1091 | LCT Arrival; Berthing at AGL RoRo Jetty
28 | 2026-02-04 | 0:00 | 2026-02-04 | 14:06 | 14:06 HRS | 14.1 | 0.59 | ENTERED FIELD LIMIT ZAKUM FIELD | OPERATIONAL | AGI TR Unit 1 | A1091 | LCT Arrival; Berthing at AGL RoRo Jetty
29 | 2026-02-04 | 0:00 | 2026-02-04 | 15:24 | 15:24 HRS | 15.4 | 0.64 | ENTERED CHANNEL | OPERATIONAL | AGI TR Unit 1 | A1091 | LCT Arrival; Berthing at AGL RoRo Jetty
30 | 2026-02-04 | 0:00 | 2026-02-04 | 15:45 | 15:45 HRS | 15.75 | 0.66 | ARRIVED BLANKET AREA | OPERATIONAL | AGI TR Unit 1 | A1091 | LCT Arrival; Berthing at AGL RoRo Jetty
31 | 2026-02-04 | 0:00 | 2026-02-04 | 16:06 | 16:06 HRS | 16.1 | 0.67 | PASSING BREAKWATER | OPERATIONAL | AGI TR Unit 1 | A1091 | LCT Arrival; Berthing at AGL RoRo Jetty
32 | 2026-02-04 | 0:00 | [5 empty] | SECURED ALONGSIDE AL GHALLAN WEST PORT BERTH 3/WAITING INSTRUCTIONS | OPERATIONAL | AGI TR Unit 1 | A1091 | LCT Arrival; Berthing at AGL RoRo Jetty