## wa group
NO | START DATE | START TIME | END DATE | END TIME | DURATION TIMES | DURATION HRS | DURATION DAYS | Activity | level1 | level2 | activity_id | activity_name
1 | 2026-01-24 | 10:47 | 2026-01-24 | 11:34 | 00:47 HRS | 0.78 | 0.03 | CHA: MZP load-out readiness 요약(Deck prep 27–28 Jan, Load-out target 29 Jan AM, Tide≥2.00m, 자원 24h 사전요청, tug/TBC, Ramp certificate 필요 가능)
2 |  |  | 2026-01-25 | 9:08 |  |  |  | LCT Bushra: Musaffah short stay drop anchor 25/01/2026 0854 hrs
3 | 2026-01-25 | 9:08 | 2026-01-25 | 9:11 | 00:03 HRS | 0.05 | 0 | Capt Igor: Samsung agent가 MZP berth arrange 전까지 anchorage 대기
4 | 2026-01-25 | 9:11 | 2026-01-25 | 9:12 | 00:01 HRS | 0.02 | 0 | 상욱: Noted
5 | 2026-01-25 | 9:12 | 2026-01-25 | 9:35 | 00:23 HRS | 0.38 | 0.02 | LCT Bushra: Noted
6 |  |  | 2026-01-26 | 10:03 |  |  |  | Adnoc Ouda: Bushra MZP 도착 시점 문의(27 Jan?) | MOBILIZATION | MARINE | A1001 | Mobilization of Marine Equipment and Steelworks
7 | 2026-01-26 | 10:03 | 2026-01-26 | 10:12 | 00:09 HRS | 0.15 | 0.01 | CHA: 2026-01-27 08:00 AM | MOBILIZATION | SPMT | A1000 | Mobilization of 1st set of SPMT; Asembly + Function Test
8 | 2026-01-26 | 10:12 | 2026-01-26 | 10:14 | 00:02 HRS | 0.03 | 0 | Adnoc Ouda: Bushra 27 Jan 08:00 도착 준비 지시(berth/pilot/agent) | MOBILIZATION | MARINE | A1001 | Mobilization of Marine Equipment and Steelworks
9 | 2026-01-26 | 10:14 | 2026-01-26 | 10:22 | 00:08 HRS | 0.13 | 0.01 | Yoonus: Ramp certificates ASAP 요청 | MOBILIZATION | SPMT | A1000 | Mobilization of 1st set of SPMT; Asembly + Function Test
10 | 2026-01-26 | 10:22 | 2026-01-26 | 11:06 | 00:44 HRS | 0.73 | 0.03 | Yulia(MAMMOET): 10 forklift + 25t(이상) mobile crane 요청(14t mats 2pcs) | MOBILIZATION | SPMT | A1000 | Mobilization of 1st set of SPMT; Asembly + Function Test
11 | 2026-01-26 | 11:06 | 2026-01-26 | 11:07 | 00:01 HRS | 0.02 | 0 | CHA: NOTED | MOBILIZATION | SPMT | A1000 | Mobilization of 1st set of SPMT; Asembly + Function Test
12 | 2026-01-26 | 11:07 | 2026-01-26 | 11:13 | 00:06 HRS | 0.1 | 0 | Adnoc Ouda: Sent by mail | MOBILIZATION | SPMT | A1000 | Mobilization of 1st set of SPMT; Asembly + Function Test
13 | 2026-01-26 | 11:13 | 2026-01-26 | 14:10 | 02:57 HRS | 2.95 | 0.12 | Yulia: 5 trailers 도착, forklift/crane 제공 시점 문의 | MOBILIZATION | SPMT | A1000 | Mobilization of 1st set of SPMT; Asembly + Function Test
14 | 2026-01-26 | 14:10 | 2026-01-26 | 14:11 | 00:01 HRS | 0.02 | 0 | CHA: I check Ofco team | MOBILIZATION | SPMT | A1000 | Mobilization of 1st set of SPMT; Asembly + Function Test
15 | 2026-01-26 | 14:11 | 2026-01-26 | 14:53 | 00:42 HRS | 0.7 | 0.03 | Yulia: No crane and forklift until now =( | MOBILIZATION | SPMT | A1000 | Mobilization of 1st set of SPMT; Asembly + Function Test
16 | 2026-01-26 | 14:53 | 2026-01-26 | 15:00 | 00:07 HRS | 0.12 | 0.01 | Yoonus: F/L only available now, follow-up 중 | MOBILIZATION | SPMT | A1000 | Mobilization of 1st set of SPMT; Asembly + Function Test
17 | 2026-01-26 | 15:00 | 2026-01-26 | 15:00 | 00:00 HRS | 0 | 0 | Yoonus: F/L will be coming soon | MOBILIZATION | SPMT | A1000 | Mobilization of 1st set of SPMT; Asembly + Function Test
18 | 2026-01-26 | 15:00 | 2026-01-26 | 15:01 | 00:01 HRS | 0.02 | 0 | Yulia: 20t forklift면 crane 불필요(14t mats) | MOBILIZATION | SPMT | A1000 | Mobilization of 1st set of SPMT; Asembly + Function Test
19 | 2026-01-26 | 15:01 | 2026-01-26 | 15:01 | 00:00 HRS | 0 | 0 | Yoonus: this is 15T F/L | MOBILIZATION | SPMT | A1000 | Mobilization of 1st set of SPMT; Asembly + Function Test
20 | 2026-01-26 | 15:01 | 2026-01-26 | 15:49 | 00:48 HRS | 0.8 | 0.03 | Yoonus: meeting scheduled tomorrow with Mina Zayed HM | MOBILIZATION | MARINE | A1001 | Mobilization of Marine Equipment and Steelworks
21 | 2026-01-26 | 15:49 | 2026-01-26 | 15:57 | 00:08 HRS | 0.13 | 0.01 | Yulia: Until now no forklift... | MOBILIZATION | SPMT | A1000 | Mobilization of 1st set of SPMT; Asembly + Function Test
22 | 2026-01-26 | 15:57 | 2026-01-26 | 16:09 | 00:12 HRS | 0.2 | 0.01 | Yulia: 6pm 이후 offload 불가, forklift ASAP | MOBILIZATION | SPMT | A1000 | Mobilization of 1st set of SPMT; Asembly + Function Test
23 | 2026-01-26 | 16:09 | 2026-01-26 | 16:10 | 00:01 HRS | 0.02 | 0 | 상욱: OFCO team..pls.. | MOBILIZATION | SPMT | A1000 | Mobilization of 1st set of SPMT; Asembly + Function Test
24 | 2026-01-26 | 16:10 | 2026-01-26 | 16:13 | 00:03 HRS | 0.05 | 0 | CHA: The operation will start soon | MOBILIZATION | SPMT | A1000 | Mobilization of 1st set of SPMT; Asembly + Function Test
25 | 2026-01-26 | 16:13 | 2026-01-26 | 16:19 | 00:06 HRS | 0.1 | 0 | Yoonus: labour and forklift is there(현장), supervisor 번호 공유 | MOBILIZATION | SPMT | A1000 | Mobilization of 1st set of SPMT; Asembly + Function Test
26 | 2026-01-26 | 16:19 | 2026-01-26 | 17:29 | 01:10 HRS | 1.17 | 0.05 | Yulia: 내일 계획(08:00 SPMT/70t crane/10t FL/점심 후 2x10t FL) | MOBILIZATION | SPMT | A1000 | Mobilization of 1st set of SPMT; Asembly + Function Test
27 | 2026-01-26 | 17:29 | 2026-01-26 | 17:29 | 00:00 HRS | 0 | 0 | Yulia: 1st TR unit ID number 요청 | MOBILIZATION | SPMT | A1000 | Mobilization of 1st set of SPMT; Asembly + Function Test
28 | 2026-01-26 | 17:29 | 2026-01-26 | 17:31 | 00:02 HRS | 0.03 | 0 | CHA: Case no 364332 | MOBILIZATION | SPMT | A1000 | Mobilization of 1st set of SPMT; Asembly + Function Test
29 | 2026-01-26 | 17:31 | 2026-01-26 | 17:32 | 00:01 HRS | 0.02 | 0 | CHA: Yoonus please arrange | MOBILIZATION | SPMT | A1000 | Mobilization of 1st set of SPMT; Asembly + Function Test
30 | 2026-01-26 | 17:32 | 2026-01-26 | 17:33 | 00:01 HRS | 0.02 | 0 | Yoonus: Tomorrow crane/forklift/gang booking request submitted | MOBILIZATION | SPMT | A1000 | Mobilization of 1st set of SPMT; Asembly + Function Test
31 | 2026-01-26 | 17:33 | 2026-01-26 | 17:34 | 00:01 HRS | 0.02 | 0 | Yoonus: RORO jetty approval 대기 | MOBILIZATION | MARINE | A1001 | Mobilization of Marine Equipment and Steelworks
32 | 2026-01-26 | 17:34 | 2026-01-26 | 17:35 | 00:01 HRS | 0.02 | 0 | Yulia: beam replacement 위해 2nd forklift 요청 | MOBILIZATION | SPMT | A1000 | Mobilization of 1st set of SPMT; Asembly + Function Test
33 | 2026-01-26 | 17:35 | 2026-01-26 | 17:49 | 00:14 HRS | 0.23 | 0.01 | Yoonus: GC ops 확인 후 업데이트 예정 | MOBILIZATION | SPMT | A1000 | Mobilization of 1st set of SPMT; Asembly + Function Test
34 |  |  | 2026-01-27 | 7:07 |  |  |  | 상욱: Pls update | OPERATIONAL | Deck Preparations | A1004 | Deck Preparations (D-ring cutting; marking, steel sets installation) - One 5t forklift and Crane required
35 | 2026-01-27 | 7:07 | 2026-01-27 | 7:38 | 00:31 HRS | 0.52 | 0.02 | Yulia: Jetty 5 currently berthed LCT Safeen Kate | OPERATIONAL | Deck Preparations | A1004 | Deck Preparations (D-ring cutting; marking, steel sets installation) - One 5t forklift and Crane required
36 | 2026-01-27 | 7:38 | 2026-01-27 | 7:38 | 00:00 HRS | 0 | 0 | Yulia: SPMT crew & Marine crew arrived, preparing | OPERATIONAL | Deck Preparations | A1004 | Deck Preparations (D-ring cutting; marking, steel sets installation) - One 5t forklift and Crane required
37 | 2026-01-27 | 7:38 | 2026-01-27 | 7:39 | 00:01 HRS | 0.02 | 0 | CHA: Noted | OPERATIONAL | Deck Preparations | A1004 | Deck Preparations (D-ring cutting; marking, steel sets installation) - One 5t forklift and Crane required
38 | 2026-01-27 | 7:39 | 2026-01-27 | 7:39 | 00:00 HRS | 0 | 0 | Yulia: transformer serial number sticker 못 찾음(위치 문의) | OPERATIONAL | Deck Preparations | A1004 | Deck Preparations (D-ring cutting; marking, steel sets installation) - One 5t forklift and Crane required
39 | 2026-01-27 | 7:39 | 2026-01-27 | 7:41 | 00:02 HRS | 0.03 | 0 | CHA: 확인 후 안내(잠시 대기 요청) | OPERATIONAL | Deck Preparations | A1004 | Deck Preparations (D-ring cutting; marking, steel sets installation) - One 5t forklift and Crane required
40 | 2026-01-27 | 7:41 | 2026-01-27 | 7:42 | 00:01 HRS | 0.02 | 0 | Yulia: crane & forklift 8am 도착 맞나? | OPERATIONAL | Deck Preparations | A1004 | Deck Preparations (D-ring cutting; marking, steel sets installation) - One 5t forklift and Crane required
41 | 2026-01-27 | 7:42 | 2026-01-27 | 7:45 | 00:03 HRS | 0.05 | 0 | CHA: S/N 2XBR62542-T Spare | OPERATIONAL | Deck Preparations | A1004 | Deck Preparations (D-ring cutting; marking, steel sets installation) - One 5t forklift and Crane required
42 | 2026-01-27 | 7:45 | 2026-01-27 | 8:33 | 00:48 HRS | 0.8 | 0.03 | Yulia: Crane and forklift arrived on time | OPERATIONAL | Deck Preparations | A1004 | Deck Preparations (D-ring cutting; marking, steel sets installation) - One 5t forklift and Crane required
43 | 2026-01-27 | 8:33 | 2026-01-27 | 8:33 | 00:00 HRS | 0 | 0 | Yulia: Bushra는 jetty 5? other jetty? | OPERATIONAL | Deck Preparations | A1004 | Deck Preparations (D-ring cutting; marking, steel sets installation) - One 5t forklift and Crane required
44 | 2026-01-27 | 8:33 | 2026-01-27 | 8:35 | 00:02 HRS | 0.03 | 0 | 상욱: Jetty #5는 29일 loadout 필요, deck prep는 타 jetty 가능 검토 요청 | OPERATIONAL | Deck Preparations | A1004 | Deck Preparations (D-ring cutting; marking, steel sets installation) - One 5t forklift and Crane required
45 | 2026-01-27 | 8:35 | 2026-01-27 | 12:56 | 04:21 HRS | 4.35 | 0.18 | Yulia: offloading 완료, crane release. SPMT assembly/beam replacement 진행. Bushra status? | OPERATIONAL | Deck Preparations | A1004 | Deck Preparations (D-ring cutting; marking, steel sets installation) - One 5t forklift and Crane required
46 | 2026-01-27 | 12:56 | 2026-01-27 | 14:20 | 01:24 HRS | 1.4 | 0.06 | Yulia: 2:30pm beam replacement 시작 예정, 2nd forklift 2:30까지 요청 + LCT ETA 요청 | OPERATIONAL | Deck Preparations | A1004 | Deck Preparations (D-ring cutting; marking, steel sets installation) - One 5t forklift and Crane required
47 | 2026-01-27 | 14:20 | 2026-01-27 | 14:26 | 00:06 HRS | 0.1 | 0 | CHA: I check | OPERATIONAL | Deck Preparations | A1004 | Deck Preparations (D-ring cutting; marking, steel sets installation) - One 5t forklift and Crane required
48 | 2026-01-27 | 14:26 | 2026-01-27 | 15:29 | 01:03 HRS | 1.05 | 0.04 | Yoonus: 2nd Forklift not available today | OPERATIONAL | Deck Preparations | A1004 | Deck Preparations (D-ring cutting; marking, steel sets installation) - One 5t forklift and Crane required
49 | 2026-01-27 | 15:29 | 2026-01-27 | 15:31 | 00:02 HRS | 0.03 | 0 | Yoonus: Land PTW pending → 승인 전 SPMT 이동 금지 | OPERATIONAL | Deck Preparations | A1004 | Deck Preparations (D-ring cutting; marking, steel sets installation) - One 5t forklift and Crane required
50 | 2026-01-27 | 15:31 | 2026-01-27 | 15:38 | 00:07 HRS | 0.12 | 0.01 | 상욱: Hot work(deck prep) start 요청(접안/확보 후) | OPERATIONAL | Deck Preparations | A1004 | Deck Preparations (D-ring cutting; marking, steel sets installation) - One 5t forklift and Crane required
51 | 2026-01-27 | 15:38 | 2026-01-27 | 15:39 | 00:01 HRS | 0.02 | 0 | Yulia: laydown area, permission 없이 SPMT 이동 안함 | OPERATIONAL | Deck Preparations | A1004 | Deck Preparations (D-ring cutting; marking, steel sets installation) - One 5t forklift and Crane required
52 | 2026-01-27 | 15:39 | 2026-01-27 | 15:42 | 00:03 HRS | 0.05 | 0 | Yulia: 내일 2 forklifts booking 요청 | OPERATIONAL | Deck Preparations | A1004 | Deck Preparations (D-ring cutting; marking, steel sets installation) - One 5t forklift and Crane required
53 | 2026-01-27 | 15:42 | 2026-01-27 | 15:54 | 00:12 HRS | 0.2 | 0.01 | Yoonus: 내일 몇 시? 2 forklifts만? (port advance notice 필요) | OPERATIONAL | Deck Preparations | A1004 | Deck Preparations (D-ring cutting; marking, steel sets installation) - One 5t forklift and Crane required
54 | 2026-01-27 | 15:54 | 2026-01-27 | 16:00 | 00:06 HRS | 0.1 | 0 | Yulia: 8am부터 3시간 2 forklifts + (Marine) forklift+crane+gang 8am 시작 | OPERATIONAL | Deck Preparations | A1004 | Deck Preparations (D-ring cutting; marking, steel sets installation) - One 5t forklift and Crane required
55 | 2026-01-27 | 16:00 | 2026-01-27 | 16:00 | 00:00 HRS | 0 | 0 | Yulia: Bushra Captain 정보—17:00 berth 예상 | OPERATIONAL | Deck Preparations | A1004 | Deck Preparations (D-ring cutting; marking, steel sets installation) - One 5t forklift and Crane required
56 | 2026-01-27 | 16:00 | 2026-01-27 | 16:05 | 00:05 HRS | 0.08 | 0 | Yulia: Marine crew shift 17:00 종료, deck prep 내일 아침 시작 | OPERATIONAL | Deck Preparations | A1004 | Deck Preparations (D-ring cutting; marking, steel sets installation) - One 5t forklift and Crane required
57 | 2026-01-27 | 16:05 | 2026-01-27 | 16:05 | 00:00 HRS | 0 | 0 | Yoonus: port 장비 가용 확인 후 업데이트 | OPERATIONAL | Deck Preparations | A1004 | Deck Preparations (D-ring cutting; marking, steel sets installation) - One 5t forklift and Crane required
58 | 2026-01-27 | 16:05 | 2026-01-27 | 17:59 | 01:54 HRS | 1.9 | 0.08 | Yulia: Bushra berthed roro jetty 17:38 | OPERATIONAL | Deck Preparations | A1004 | Deck Preparations (D-ring cutting; marking, steel sets installation) - One 5t forklift and Crane required
59 | 2026-01-27 | 17:59 | 2026-01-27 | 18:11 | 00:12 HRS | 0.2 | 0.01 | LCT Bushra: ALL FAST SECURED MINA ZAYED RORO BERTH 27.01.2026 1738 HRS | OPERATIONAL | Deck Preparations | A1004 | Deck Preparations (D-ring cutting; marking, steel sets installation) - One 5t forklift and Crane required
60 |  |  | 2026-01-28 | 10:01 |  |  |  | Yoonus: (MZ GC Ops) 작업 완료 후 Delivery Note 작성→AD Customs 제출(출항 전) | OPERATIONAL | Beam Replacement | A1003 | Beam Replacement AGI TR Unit 2 (TR Bay 3) - Two 5t forklifts required
61 | 2026-01-28 | 10:01 | 2026-01-28 | 10:52 | 00:51 HRS | 0.85 | 0.04 | Yulia: crane 3시간 연장 요청 | OPERATIONAL | Beam Replacement | A1003 | Beam Replacement AGI TR Unit 2 (TR Bay 3) - Two 5t forklifts required
62 | 2026-01-28 | 10:52 | 2026-01-28 | 10:56 | 00:04 HRS | 0.07 | 0 | Yulia: forklift 1대 off-hire 가능, 1대는 필요 | OPERATIONAL | Beam Replacement | A1003 | Beam Replacement AGI TR Unit 2 (TR Bay 3) - Two 5t forklifts required
63 | 2026-01-28 | 10:56 | 2026-01-28 | 11:02 | 00:06 HRS | 0.1 | 0 | Yoonus: port 통보 후 가용 업데이트 | OPERATIONAL | Beam Replacement | A1003 | Beam Replacement AGI TR Unit 2 (TR Bay 3) - Two 5t forklifts required
64 | 2026-01-28 | 11:02 | 2026-01-28 | 11:20 | 00:18 HRS | 0.3 | 0.01 | Yulia: 29-01-2026 07:00 crane+1 forklift booking 요청(linkspan) | OPERATIONAL | Deck Preparations | A1005 | Deck Preparations (Steel sets installation, welding) - Crane Required for steel sets installation
65 | 2026-01-28 | 11:20 | 2026-01-28 | 11:40 | 00:20 HRS | 0.33 | 0.01 | Yoonus: crane extension port confirmed | OPERATIONAL | Beam Replacement | A1003 | Beam Replacement AGI TR Unit 2 (TR Bay 3) - Two 5t forklifts required
66 | 2026-01-28 | 11:40 | 2026-01-28 | 13:19 | 01:39 HRS | 1.65 | 0.07 | Yulia: SPMT scope 완료→release, Marine crew 계속 | OPERATIONAL | Beam Replacement | A1003 | Beam Replacement AGI TR Unit 2 (TR Bay 3) - Two 5t forklifts required
67 | 2026-01-28 | 13:19 | 2026-01-28 | 14:19 | 01:00 HRS | 1 | 0.04 | Yoonus: 16t forklift + 40t crane(65t 정비) | OPERATIONAL | Beam Replacement | A1003 | Beam Replacement AGI TR Unit 2 (TR Bay 3) - Two 5t forklifts required
68 | 2026-01-28 | 14:19 | 2026-01-28 | 16:56 | 02:37 HRS | 2.62 | 0.11 | Yulia: 29/30 Jan weather forecast 요청 | OPERATIONAL | Deck Preparations | A1005 | Deck Preparations (Steel sets installation, welding) - Crane Required for steel sets installation
69 | 2026-01-28 | 16:56 | 2026-01-28 | 17:10 | 00:14 HRS | 0.23 | 0.01 | Yulia: AGI berth 3 점유/기상 리스크(최악 2-Feb까지 stay) 공유 | OPERATIONAL | Beam Replacement | A1003 | Beam Replacement AGI TR Unit 2 (TR Bay 3) - Two 5t forklifts required
70 | 2026-01-28 | 17:10 | 2026-01-28 | 17:18 | 00:08 HRS | 0.13 | 0.01 | Haitham: 내일 HM linkspan F2F meeting, 11am, 참석자 SCT/MWS/MMT/OFCO | OPERATIONAL | Deck Preparations | A1005 | Deck Preparations (Steel sets installation, welding) - Crane Required for steel sets installation
71 | 2026-01-28 | 17:18 | 2026-01-28 | 17:20 | 00:02 HRS | 0.03 | 0 | Yulia: tide window 8–10am, 그럼 내일 load-out 안하나? | OPERATIONAL | Deck Preparations | A1005 | Deck Preparations (Steel sets installation, welding) - Crane Required for steel sets installation
72 | 2026-01-28 | 17:20 | 2026-01-28 | 17:22 | 00:02 HRS | 0.03 | 0 | 상욱: Not possible. Linkspan issue.. HM want certificate | OPERATIONAL | Deck Preparations | A1005 | Deck Preparations (Steel sets installation, welding) - Crane Required for steel sets installation
73 | 2026-01-28 | 17:22 | 2026-01-28 | 17:36 | 00:14 HRS | 0.23 | 0.01 | Yulia: crew standby, F2F 참석, office location 요청 | OPERATIONAL | Deck Preparations | A1005 | Deck Preparations (Steel sets installation, welding) - Crane Required for steel sets installation
74 | 2026-01-28 | 17:36 | 2026-01-28 | 17:38 | 00:02 HRS | 0.03 | 0 | OFCO: Land PTW 승인 아직(초기 승인 HM) | OPERATIONAL | Beam Replacement | A1003 | Beam Replacement AGI TR Unit 2 (TR Bay 3) - Two 5t forklifts required
75 | 2026-01-29 | - | 2026-01-29 | 12:29 | - | - | - | Yoonus: 오늘 작업 없음 → crane/forklift/gang release | MOBILIZATION | JACKING EQUIPMENT, STEEL BRIDGE |  | JACKING EQUIPMENT, STEEL BRIDGE
76 | 2026-01-29 | 12:29 | 2026-01-29 | 12:31 | 00:02 HRS | 0.03 | 0 | 상욱: loadout tom 9–11am, supporting docs ASAP | MOBILIZATION | JACKING EQUIPMENT, STEEL BRIDGE |  | JACKING EQUIPMENT, STEEL BRIDGE
77 | 2026-01-29 | 12:31 | 2026-01-29 | 13:31 | 01:00 HRS | 1 | 0.04 | OFCO: linkspan certificate mandatory | MOBILIZATION | JACKING EQUIPMENT, STEEL BRIDGE |  | JACKING EQUIPMENT, STEEL BRIDGE
78 | 2026-01-29 | 13:31 | 2026-01-29 | 15:05 | 01:34 HRS | 1.57 | 0.07 | Yulia: 내일 25t crane+forklift 7am booking 요청 | MOBILIZATION | JACKING EQUIPMENT, STEEL BRIDGE |  | JACKING EQUIPMENT, STEEL BRIDGE
79 | 2026-01-29 | 15:05 | 2026-01-29 | 15:07 | 00:02 HRS | 0.03 | 0 | Yoonus: booking 진행, port confirmation 회신 예정 | MOBILIZATION | JACKING EQUIPMENT, STEEL BRIDGE |  | JACKING EQUIPMENT, STEEL BRIDGE
80 | 2026-01-29 | 15:07 | 2026-01-29 | 16:28 | 01:21 HRS | 1.35 | 0.06 | Yulia: Mammoet 팀 내일 7am port 도착 | MOBILIZATION | JACKING EQUIPMENT, STEEL BRIDGE |  | JACKING EQUIPMENT, STEEL BRIDGE
81 |  |  | 2026-01-30 | 7:26 |  |  |  | Yulia: 준비 시작(steel plates installation), PTW 또는 reschedule 대기 | MOBILIZATION | JACKING EQUIPMENT, STEEL BRIDGE | A2010 | Mobilization of Jacking Equipment and Steel bridge (prior LCT's arrival to AGI with TR 1&2!))
82 | 2026-01-30 | 7:26 | 2026-01-30 | 8:40 | 01:14 HRS | 1.23 | 0.05 | Yulia: steel plates 설치 완료, linkspan ramp adjusted | MOBILIZATION | JACKING EQUIPMENT, STEEL BRIDGE | A2010 | Mobilization of Jacking Equipment and Steel bridge (prior LCT's arrival to AGI with TR 1&2!))
83 | 2026-01-30 | 8:40 | 2026-01-30 | 8:53 | 00:13 HRS | 0.22 | 0.01 | Yulia: Tide(09:00 1.97m / 10:00 2.05m / 11:00 2.04m) | MOBILIZATION | JACKING EQUIPMENT, STEEL BRIDGE | A2010 | Mobilization of Jacking Equipment and Steel bridge (prior LCT's arrival to AGI with TR 1&2!))
84 | 2026-01-30 | 8:53 | 2026-01-30 | 10:31 | 01:38 HRS | 1.63 | 0.07 | Adnoc Ouda: welding schedule/Aries witness/MWS scope 질의 시작 | MOBILIZATION | JACKING EQUIPMENT, STEEL BRIDGE | A2010 | Mobilization of Jacking Equipment and Steel bridge (prior LCT's arrival to AGI with TR 1&2!))
85 | 2026-01-30 | 10:31 | 2026-01-30 | 10:39 | 00:08 HRS | 0.13 | 0.01 | 상욱: Aries analysis done, issue는 PTW/Linkspan | MOBILIZATION | JACKING EQUIPMENT, STEEL BRIDGE | A2010 | Mobilization of Jacking Equipment and Steel bridge (prior LCT's arrival to AGI with TR 1&2!))
86 | 2026-01-30 | 10:39 | 2026-01-30 | 10:43 | 00:04 HRS | 0.07 | 0 | Adnoc Ouda: FW discharge clearance 업데이트 요청(OFCO) | MOBILIZATION | JACKING EQUIPMENT, STEEL BRIDGE | A2010 | Mobilization of Jacking Equipment and Steel bridge (prior LCT's arrival to AGI with TR 1&2!))
87 | 2026-01-30 | 10:43 | 2026-01-30 | 11:20 | 00:37 HRS | 0.62 | 0.03 | Yulia: Port Authority가 ops 불가 → linkspan removal 시작 가능 여부 문의 | MOBILIZATION | JACKING EQUIPMENT, STEEL BRIDGE | A2010 | Mobilization of Jacking Equipment and Steel bridge (prior LCT's arrival to AGI with TR 1&2!))
88 | 2026-01-30 | 11:20 | 2026-01-30 | 11:22 | 00:02 HRS | 0.03 | 0 | Capt Igor: Please share mobile of MWS | MOBILIZATION | JACKING EQUIPMENT, STEEL BRIDGE | A2010 | Mobilization of Jacking Equipment and Steel bridge (prior LCT's arrival to AGI with TR 1&2!))
89 | 2026-01-30 | 11:22 | 2026-01-30 | 11:23 | 00:01 HRS | 0.02 | 0 | CHA: Linkspan Removal - Hold until 14:00 | MOBILIZATION | JACKING EQUIPMENT, STEEL BRIDGE | A2010 | Mobilization of Jacking Equipment and Steel bridge (prior LCT's arrival to AGI with TR 1&2!))
90 | 2026-01-30 | 11:23 | 2026-01-30 | 12:01 | 00:38 HRS | 0.63 | 0.03 | Yoonus: de-ballasting/tanker arrangements 승인 필요, proceed 확인 요청 | MOBILIZATION | JACKING EQUIPMENT, STEEL BRIDGE | A2010 | Mobilization of Jacking Equipment and Steel bridge (prior LCT's arrival to AGI with TR 1&2!))
91 | 2026-01-30 | 12:01 | 2026-01-30 | 12:01 | 00:00 HRS | 0 | 0 | Shariff: Ok confirmed...pls proceed | MOBILIZATION | JACKING EQUIPMENT, STEEL BRIDGE | A2010 | Mobilization of Jacking Equipment and Steel bridge (prior LCT's arrival to AGI with TR 1&2!))
92 | 2026-01-30 | 12:01 | 2026-01-30 | 12:12 | 00:11 HRS | 0.18 | 0.01 | LCT Bushra: fresh water transfer 계획/trim 목표 공유 | MOBILIZATION | JACKING EQUIPMENT, STEEL BRIDGE | A2010 | Mobilization of Jacking Equipment and Steel bridge (prior LCT's arrival to AGI with TR 1&2!))
93 | 2026-01-30 | 12:12 | 2026-01-30 | 14:54 | 02:42 HRS | 2.7 | 0.11 | LCT Bushra: FW transfer 후 trim 1m, plan 대비 0.15m 차이 | MOBILIZATION | JACKING EQUIPMENT, STEEL BRIDGE | A2010 | Mobilization of Jacking Equipment and Steel bridge (prior LCT's arrival to AGI with TR 1&2!))
94 | 2026-01-30 | 14:54 | 2026-01-30 | 15:55 | 01:01 HRS | 1.02 | 0.04 | Yoonus: port에 장비/gang release 요청 | MOBILIZATION | JACKING EQUIPMENT, STEEL BRIDGE | A2010 | Mobilization of Jacking Equipment and Steel bridge (prior LCT's arrival to AGI with TR 1&2!))
95 | 2026-01-30 | 15:55 | 2026-01-30 | 16:00 | 00:05 HRS | 0.08 | 0 | Yulia: load out 승인 시 내일 crane+forklift 필요(11–12pm 이후) | MOBILIZATION | JACKING EQUIPMENT, STEEL BRIDGE | A2010 | Mobilization of Jacking Equipment and Steel bridge (prior LCT's arrival to AGI with TR 1&2!))
96 | 2026-01-30 | 16:00 | 2026-01-30 | 22:10 | 06:10 HRS | 6.17 | 0.26 | Yoonus: HM/HSE/MZ Ops 승인(01st trip load), 출항 전 MWS COA 제출 조건 | OPERATIONAL | AGI TR Unit 1 | A1060 | Load-out of AGL TR Unit 1; stool down (8am-10am)
97 | 2026-01-30 | 22:10 | 2026-01-30 | 22:11 | 00:01 HRS | 0.02 | 0 | Adnoc Ouda: loading 전 MWS confirmation(Aries bow strength arrangement 정합) 필수 | MOBILIZATION | JACKING EQUIPMENT, STEEL BRIDGE | A2010 | Mobilization of Jacking Equipment and Steel bridge (prior LCT's arrival to AGI with TR 1&2!))
98 | 2026-01-30 | 22:11 | 2026-01-30 | 22:13 | 00:02 HRS | 0.03 | 0 | 상욱: loadout tomorrow morning( tide 9–11 ), MMT standby 7am | MOBILIZATION | JACKING EQUIPMENT, STEEL BRIDGE | A2010 | Mobilization of Jacking Equipment and Steel bridge (prior LCT's arrival to AGI with TR 1&2!))
99 |  |  | 2026-01-31 | 6:16 |  |  |  | CHA: MWS 08:50 Mina Port 도착 예정 | OPERATIONAL | AGI TR Unit 1 | A1060 | Load-out of AGL TR Unit 1; stool down (8am-10am)
100 | 2026-01-31 | 6:16 | 2026-01-31 | 7:21 | 01:05 HRS | 1.08 | 0.05 | Yulia: Please share PTW | OPERATIONAL | AGI TR Unit 1 | A1060 | Load-out of AGL TR Unit 1; stool down (8am-10am)
101 | 2026-01-31 | 7:21 | 2026-01-31 | 7:32 | 00:11 HRS | 0.18 | 0.01 | Yulia: HM이 MWS COA 기다림, 발급되나? | OPERATIONAL | AGI TR Unit 1 | A1060 | Load-out of AGL TR Unit 1; stool down (8am-10am)
102 | 2026-01-31 | 7:32 | 2026-01-31 | 7:46 | 00:14 HRS | 0.23 | 0.01 | Haitham: MWS before 9am, COA 발급 | OPERATIONAL | AGI TR Unit 1 | A1060 | Load-out of AGL TR Unit 1; stool down (8am-10am)
103 | 2026-01-31 | 7:46 | 2026-01-31 | 9:49 | 02:03 HRS | 2.05 | 0.09 | Yulia: mats 이동 위해 forklift 요청 | OPERATIONAL | AGI TR Unit 1 | A1060 | Load-out of AGL TR Unit 1; stool down (8am-10am)
104 | 2026-01-31 | 9:49 | 2026-01-31 | 9:50 | 00:01 HRS | 0.02 | 0 | Yoonus: noted, MZ GC ops에 요청 | OPERATIONAL | AGI TR Unit 1 | A1060 | Load-out of AGL TR Unit 1; stool down (8am-10am)
105 | 2026-01-31 | 9:50 | 2026-01-31 | 10:25 | 00:35 HRS | 0.58 | 0.02 | Yulia: HM 승인 받아 load out 시작, toolbox talk 완료 | OPERATIONAL | AGI TR Unit 1 | A1060 | Load-out of AGL TR Unit 1; stool down (8am-10am)
106 | 2026-01-31 | 10:25 | 2026-01-31 | 10:29 | 00:04 HRS | 0.07 | 0 | Yulia: Load out started | OPERATIONAL | AGI TR Unit 1 | A1060 | Load-out of AGL TR Unit 1; stool down (8am-10am)
107 | 2026-01-31 | 10:29 | 2026-01-31 | 10:53 | 00:24 HRS | 0.4 | 0.02 | Yulia: TR Unit 1 on LCT | OPERATIONAL | AGI TR Unit 1 | A1070 | RoRo ramp removal; Seafastening AGL TR Unit 1 - Crane required
108 | 2026-01-31 | 10:53 | 2026-01-31 | 10:54 | 00:01 HRS | 0.02 | 0 | Yulia: linkspan ramp removal/적재 위해 crane 요청 | OPERATIONAL | AGI TR Unit 1 | A1070 | RoRo ramp removal; Seafastening AGL TR Unit 1 - Crane required
109 | 2026-01-31 | 10:54 | 2026-01-31 | 10:58 | 00:04 HRS | 0.07 | 0 | Yoonus: crane confirmed | OPERATIONAL | AGI TR Unit 1 | A1070 | RoRo ramp removal; Seafastening AGL TR Unit 1 - Crane required
110 | 2026-01-31 | 10:58 | 2026-01-31 | 11:08 | 00:10 HRS | 0.17 | 0.01 | Adnoc Ouda: 1st unit loading 축하 | OPERATIONAL | AGI TR Unit 1 | A1070 | RoRo ramp removal; Seafastening AGL TR Unit 1 - Crane required
111 | 2026-01-31 | 11:08 | 2026-01-31 | 11:09 | 00:01 HRS | 0.02 | 0 | Adnoc Ouda: AGI offloading 전 hing beam 하부 구조/용접 재확인(MWS) | OPERATIONAL | AGI TR Unit 1 | A1070 | RoRo ramp removal; Seafastening AGL TR Unit 1 - Crane required
112 | 2026-01-31 | 11:09 | 2026-01-31 | 12:29 | 01:20 HRS | 1.33 | 0.06 | LCT Bushra: cargo manifest 요청(계산 위해) | OPERATIONAL | AGI TR Unit 1 | A1070 | RoRo ramp removal; Seafastening AGL TR Unit 1 - Crane required
113 | 2026-01-31 | 12:29 | 2026-01-31 | 13:12 | 00:43 HRS | 0.72 | 0.03 | Yoonus: (GC Ops) crane after lunch 제공 가능 | OPERATIONAL | AGI TR Unit 1 | A1070 | RoRo ramp removal; Seafastening AGL TR Unit 1 - Crane required
114 | 2026-01-31 | 13:12 | 2026-01-31 | 14:33 | 01:21 HRS | 1.35 | 0.06 | Adnoc Ouda: sailing time/ETA 요청 | OPERATIONAL | AGI TR Unit 1 | A1070 | RoRo ramp removal; Seafastening AGL TR Unit 1 - Crane required
115 | 2026-01-31 | 14:33 | 2026-01-31 | 14:46 | 00:13 HRS | 0.22 | 0.01 | 상욱: ETA AGI 2-Feb 계획 언급 | OPERATIONAL | AGI TR Unit 1 | A1070 | RoRo ramp removal; Seafastening AGL TR Unit 1 - Crane required
116 | 2026-01-31 | 14:46 | 2026-01-31 | 15:15 | 00:29 HRS | 0.48 | 0.02 | OFCO: Bushra ETD 요청(다른 landing crafts 대기) | OPERATIONAL | AGI TR Unit 1 | A1070 | RoRo ramp removal; Seafastening AGL TR Unit 1 - Crane required
117 | 2026-01-31 | 15:15 | 2026-01-31 | 16:38 | 01:23 HRS | 1.38 | 0.06 | Yulia: sea fastening done, inspection ongoing | OPERATIONAL | AGI TR Unit 1 | A1070 | RoRo ramp removal; Seafastening AGL TR Unit 1 - Crane required
118 | 2026-01-31 | 16:38 | 2026-01-31 | 17:58 | 01:20 HRS | 1.33 | 0.06 | 상욱: manifest/COA 대기, ETD 1-Feb / ETA 2-Feb 추정 | OPERATIONAL | AGI TR Unit 1 | A1070 | RoRo ramp removal; Seafastening AGL TR Unit 1 - Crane required
119 | 2026-01-31 | 17:58 | 2026-01-31 | 19:18 | 01:20 HRS | 1.33 | 0.06 | LCT Bushra: packing list vs draft/loaded weight match 언급 | OPERATIONAL | AGI TR Unit 1 | A1070 | RoRo ramp removal; Seafastening AGL TR Unit 1 - Crane required
120 | 2026-01-31 | 19:18 | 2026-01-31 | 19:28 | 00:10 HRS | 0.17 | 0.01 | LCT Bushra: manifest 645t이면 draft 2.9m 예상 vs 실제 2.5m(차이 0.4m) | OPERATIONAL | AGI TR Unit 1 | A1070 | RoRo ramp removal; Seafastening AGL TR Unit 1 - Crane required
121 | 2026-01-31 | 19:28 | 2026-01-31 | 19:47 | 00:19 HRS | 0.32 | 0.01 | 상욱: revised manifest 공유(Shipping follow-up) | OPERATIONAL | AGI TR Unit 1 | A1070 | RoRo ramp removal; Seafastening AGL TR Unit 1 - Crane required
122 | 2026-01-31 | 19:47 | 2026-01-31 | 20:52 | 01:05 HRS | 1.08 | 0.05 | Yoonus: Vessel Bushra cast off from Mina Zayed | OPERATIONAL | AGI TR Unit 1 | A1070 | RoRo ramp removal; Seafastening AGL TR Unit 1 - Crane required
123 | 2026-01-31 | 20:52 | 2026-01-31 | 20:53 | 00:01 HRS | 0.02 | 0 | LCT Bushra: 31/01/2026 2036 cast off, ETA AGI 01/02/2026 0700 | OPERATIONAL | AGI TR Unit 1 | A1070 | RoRo ramp removal; Seafastening AGL TR Unit 1 - Crane required
124 | 2026-01-31 | 20:53 | 2026-01-31 | 21:18 | 00:25 HRS | 0.42 | 0.02 | Yulia: crew는 CICPA renewal로 3-Feb 이전 이동 불가 | OPERATIONAL | AGI TR Unit 1 | A1070 | RoRo ramp removal; Seafastening AGL TR Unit 1 - Crane required
125 |  |  | 2026-02-01 | 7:42 |  |  |  | Khemlal: AGI에서는 Linkspan 외 lifting 불가(ALS LOP 범위), forklift ops 불가 | OPERATIONAL | AGI TR Unit 1 | A1081 | MWS; MPI; Sail-away - Marine Transportation by LCT to Al Ghallan Island
126 | 2026-02-01 | 7:42 | 2026-02-01 | 7:49 | 00:07 HRS | 0.12 | 0.01 | Khemlal: ADNOC approved TPC 없으면 lift 불가 | OPERATIONAL | AGI TR Unit 1 | A1081 | MWS; MPI; Sail-away - Marine Transportation by LCT to Al Ghallan Island
127 | 2026-02-01 | 7:49 | 2026-02-01 | 8:01 | 00:12 HRS | 0.2 | 0.01 | LCT Bushra: AGI anchorage 0600, waiting berthing schedule | OPERATIONAL | AGI TR Unit 1 | A1081 | MWS; MPI; Sail-away - Marine Transportation by LCT to Al Ghallan Island
128 |  |  | 2026-02-02 | 9:12 |  |  |  | 상욱: Erwin booking 확인 요청(3-Feb AM) | OPERATIONAL | AGI TR Unit 1 | A1090 | MMT Crew Mob to AGI; Site Induction; Meeting with Client
129 | 2026-02-02 | 9:12 | 2026-02-02 | 9:13 | 00:01 HRS | 0.02 | 0 | Yulia: 3rd travel 가능, CICPA pending 공유 예정 | OPERATIONAL | AGI TR Unit 1 | A1090 | MMT Crew Mob to AGI; Site Induction; Meeting with Client
130 | 2026-02-02 | 9:13 | 2026-02-02 | 9:15 | 00:02 HRS | 0.03 | 0 | 상욱: Wardeh ETA AGI today | OPERATIONAL | AGI TR Unit 1 | A1090 | MMT Crew Mob to AGI; Site Induction; Meeting with Client
131 | 2026-02-02 | 9:15 | 2026-02-02 | 9:16 | 00:01 HRS | 0.02 | 0 | 상욱: JPT62 ETA AGI 3-Feb(부분 적재) | OPERATIONAL | AGI TR Unit 1 | A1090 | MMT Crew Mob to AGI; Site Induction; Meeting with Client
132 | 2026-02-02 | 9:16 | 2026-02-02 | 9:56 | 00:40 HRS | 0.67 | 0.03 | PTR 담당: passengers booked 후 PTR 발송 | OPERATIONAL | AGI TR Unit 1 | A1090 | MMT Crew Mob to AGI; Site Induction; Meeting with Client
133 | 2026-02-02 | 9:56 | 2026-02-02 | 10:16 | 00:20 HRS | 0.33 | 0.01 | Yulia: Lifting clamps loaded onto LCT JPT62 | OPERATIONAL | AGI TR Unit 1 | A1090 | MMT Crew Mob to AGI; Site Induction; Meeting with Client
134 | 2026-02-02 | 10:16 | 2026-02-02 | 10:17 | 00:01 HRS | 0.02 | 0 | 상욱: ETA MZP 5 or 6, 내일 업데이트 | OPERATIONAL | AGI TR Unit 1 | A1090 | MMT Crew Mob to AGI; Site Induction; Meeting with Client
135 | 2026-02-02 | 10:17 | 2026-02-02 | 10:18 | 00:01 HRS | 0.02 | 0 | OFCO: Linkspan certificate very important | OPERATIONAL | AGI TR Unit 1 | A1090 | MMT Crew Mob to AGI; Site Induction; Meeting with Client
136 | 2026-02-02 | 10:18 | 2026-02-02 | 10:18 | 00:00 HRS | 0 | 0 | Yulia: 2 beams load test today and tomorrow | OPERATIONAL | AGI TR Unit 1 | A1090 | MMT Crew Mob to AGI; Site Induction; Meeting with Client
137 |  |  | 2026-02-04 | 12:22 |  |  |  | 상욱: MUS.0521 | OPERATIONAL | AGI TR Unit 1 | A1121 | LCT Sails back to MZP to collect TR Unit 1
138 | 2026-02-04 | 12:22 | 2026-02-04 | 17:35 | 05:13 HRS | 5.22 | 0.22 | Yulia: Wardeh ETA AGI 문의 | OPERATIONAL | AGI TR Unit 1 | A1121 | LCT Sails back to MZP to collect TR Unit 1
139 | 2026-02-04 | 17:35 | 2026-02-04 | 17:35 | 00:00 HRS | 0 | 0 | 상욱: Onsite.yesterday | OPERATIONAL | AGI TR Unit 1 | A1121 | LCT Sails back to MZP to collect TR Unit 1
140 | 2026-02-04 | 17:35 | 2026-02-04 | 17:36 | 00:01 HRS | 0.02 | 0 | 상욱: JPT62 ETA 20:30 today, onsite tomorrow morning | OPERATIONAL | AGI TR Unit 1 | A1121 | LCT Sails back to MZP to collect TR Unit 1
141 | 2026-02-04 | 17:36 | 2026-02-04 | 19:56 | 02:20 HRS | 2.33 | 0.1 | LCT Bushra: AGI West RORO berth 3 alongside 1606 | OPERATIONAL | AGI TR Unit 1 | A1091 | LCT Arrival; Berthing at AGL RoRo Jetty
142 |  |  | 2026-02-05 | 7:59 |  |  |  | LCT Bushra: AGI port meeting onboard 요청(아침) | OPERATIONAL | AGI TR Unit 1 | A1141 | Turning of AGI TR Unit 1 (TR Bay 4) - 10t Forklift required
143 | 2026-02-05 | 7:59 | 2026-02-05 | 8:00 | 00:01 HRS | 0.02 | 0 | Khemlal: Any specific time? | OPERATIONAL | AGI TR Unit 1 | A1141 | Turning of AGI TR Unit 1 (TR Bay 4) - 10t Forklift required
144 | 2026-02-05 | 8:00 | 2026-02-05 | 8:05 | 00:05 HRS | 0.08 | 0 | Khemlal: Electrical/MMT 08:30 참석 | OPERATIONAL | AGI TR Unit 1 | A1141 | Turning of AGI TR Unit 1 (TR Bay 4) - 10t Forklift required
145 | 2026-02-05 | 8:05 | 2026-02-05 | 12:52 | 04:47 HRS | 4.78 | 0.2 | Adnoc Ouda: TR1 offloading 시작/ETD back/2nd TR loading 일정 질의 | OPERATIONAL | AGI TR Unit 1 | A1141 | Turning of AGI TR Unit 1 (TR Bay 4) - 10t Forklift required
146 | 2026-02-05 | 12:52 | 2026-02-05 | 13:07 | 00:15 HRS | 0.25 | 0.01 | 상욱: Loadin plan tomorrow, ETD 6/ETA 7, TR2 loadout 8~9 Feb(계획) | OPERATIONAL | AGI TR Unit 1 | A1141 | Turning of AGI TR Unit 1 (TR Bay 4) - 10t Forklift required
147 | 2026-02-05 | 13:07 | 2026-02-05 | 13:11 | 00:04 HRS | 0.07 | 0 | Yoonus: 다음 TR 문서(Ramp cert/Hotwork/Overwater 등) 미수령 | OPERATIONAL | AGI TR Unit 1 | A1141 | Turning of AGI TR Unit 1 (TR Bay 4) - 10t Forklift required
148 | 2026-02-05 | 13:11 | 2026-02-05 | 13:12 | 00:01 HRS | 0.02 | 0 | Yulia: 날짜만 변경해서 재제출 가능? | OPERATIONAL | AGI TR Unit 1 | A1141 | Turning of AGI TR Unit 1 (TR Bay 4) - 10t Forklift required
149 | 2026-02-05 | 13:12 | 2026-02-05 | 13:13 | 00:01 HRS | 0.02 | 0 | Yoonus: 가능, permit duration(며칠) 필요 | OPERATIONAL | AGI TR Unit 1 | A1141 | Turning of AGI TR Unit 1 (TR Bay 4) - 10t Forklift required
150 | 2026-02-05 | 13:13 | 2026-02-05 | 13:14 | 00:01 HRS | 0.02 | 0 | Yulia: safe side 1 week permit | OPERATIONAL | AGI TR Unit 1 | A1141 | Turning of AGI TR Unit 1 (TR Bay 4) - 10t Forklift required
151 | 2026-02-05 | 13:14 | 2026-02-05 | 13:14 | 00:00 HRS | 0 | 0 | Yulia: linkspan certificate 제출 예정(Inspector 공유 대기) | OPERATIONAL | AGI TR Unit 1 | A1141 | Turning of AGI TR Unit 1 (TR Bay 4) - 10t Forklift required
152 | 2026-02-05 | 13:14 | 2026-02-05 | 16:47 | 03:33 HRS | 3.55 | 0.15 | Yoonus: pre-ops meeting scheduled(06-Feb 15:00) | OPERATIONAL | AGI TR Unit 1 | A1141 | Turning of AGI TR Unit 1 (TR Bay 4) - 10t Forklift required
153 | 2026-02-05 | 16:47 | 2026-02-05 | 16:59 | 00:12 HRS | 0.2 | 0.01 | Yoonus: updated MOS/RA + tide window 요청 | OPERATIONAL | AGI TR Unit 1 | A1141 | Turning of AGI TR Unit 1 (TR Bay 4) - 10t Forklift required
154 | 2026-02-05 | 16:59 | 2026-02-05 | 17:32 | 00:33 HRS | 0.55 | 0.02 | Yulia: 내일 아침 MOS/RA 전달 예정 | OPERATIONAL | AGI TR Unit 1 | A1141 | Turning of AGI TR Unit 1 (TR Bay 4) - 10t Forklift required
155 | 2026-02-05 | 17:32 | 2026-02-05 | 17:33 | 00:01 HRS | 0.02 | 0 | Yulia: ADNOC office Fri–Sun off, approval 지연 우려 | OPERATIONAL | AGI TR Unit 1 | A1141 | Turning of AGI TR Unit 1 (TR Bay 4) - 10t Forklift required
156 |  |  | 2026-02-06 | 9:00 |  |  |  | 상욱: Pls send email.. | OPERATIONAL | AGI TR Unit 1 | A1141 | Turning of AGI TR Unit 1 (TR Bay 4) - 10t Forklift required
157 | 2026-02-06 | 9:00 | 2026-02-06 | 9:07 | 00:07 HRS | 0.12 | 0.01 | Yulia: done | OPERATIONAL | AGI TR Unit 1 | A1141 | Turning of AGI TR Unit 1 (TR Bay 4) - 10t Forklift required
158 | 2026-02-06 | 9:07 | 2026-02-06 | 9:37 | 00:30 HRS | 0.5 | 0.02 | LCT Bushra: offloading plan today? high tide 15:00–16:00 | OPERATIONAL | AGI TR Unit 1 | A1141 | Turning of AGI TR Unit 1 (TR Bay 4) - 10t Forklift required
159 | 2026-02-06 | 9:37 | 2026-02-06 | 10:29 | 00:52 HRS | 0.87 | 0.04 | Yoonus: 2nd TR cargo manifest forward 요청 | OPERATIONAL | AGI TR Unit 1 | A1141 | Turning of AGI TR Unit 1 (TR Bay 4) - 10t Forklift required
160 | 2026-02-06 | 10:29 | 2026-02-06 | 14:44 | 04:15 HRS | 4.25 | 0.18 | Yoonus: 2nd TR BOE copy 요청 | OPERATIONAL | AGI TR Unit 1 | A1141 | Turning of AGI TR Unit 1 (TR Bay 4) - 10t Forklift required
161 | 2026-02-06 | 14:44 | 2026-02-06 | 14:46 | 00:02 HRS | 0.03 | 0 | Yoonus: Bushra updated ETA MZP? | OPERATIONAL | AGI TR Unit 1 | A1141 | Turning of AGI TR Unit 1 (TR Bay 4) - 10t Forklift required
162 | 2026-02-06 | 14:46 | 2026-02-06 | 14:52 | 00:06 HRS | 0.1 | 0 | 상욱: tentative ETA 8 or 9 Feb | OPERATIONAL | AGI TR Unit 1 | A1141 | Turning of AGI TR Unit 1 (TR Bay 4) - 10t Forklift required
163 | 2026-02-06 | 14:52 | 2026-02-06 | 14:52 | 00:00 HRS | 0 | 0 | LCT Bushra: TR2 ramp door damage risk 언급(step 4&5) | OPERATIONAL | AGI TR Unit 1 | A1141 | Turning of AGI TR Unit 1 (TR Bay 4) - 10t Forklift required
164 | 2026-02-06 | 14:52 | 2026-02-06 | 14:54 | 00:02 HRS | 0.03 | 0 | Yulia: Engineer Sayeed Ahmed와 논의 요청(+971 58 680 5307) | OPERATIONAL | AGI TR Unit 1 | A1141 | Turning of AGI TR Unit 1 (TR Bay 4) - 10t Forklift required
165 | 2026-02-06 | 14:54 | 2026-02-06 | 14:59 | 00:05 HRS | 0.08 | 0 | LCT Bushra: Ok will try to contact | OPERATIONAL | AGI TR Unit 1 | A1141 | Turning of AGI TR Unit 1 (TR Bay 4) - 10t Forklift required
166 | 2026-02-06 | 14:59 | 2026-02-06 | 15:32 | 00:33 HRS | 0.55 | 0.02 | Yoonus: meeting rescheduled to 09-Feb 11:00 | OPERATIONAL | AGI TR Unit 1 | A1141 | Turning of AGI TR Unit 1 (TR Bay 4) - 10t Forklift required
167 |  |  | 2026-02-07 | 8:47 |  |  |  | 상욱: AGI 1st TR loading commenced. MZP 2nd loadout plan 10-Feb | OPERATIONAL | AGI TR Unit 1 | A1141 | Turning of AGI TR Unit 1 (TR Bay 4) - 10t Forklift required
168 |  |  | 2026-02-08 | 11:00 |  |  |  | 상욱: AGI 1st TR offloading completed. cast off around 2pm | OPERATIONAL | AGI TR Unit 1 | A1150 | Jacking down of AGI TR Unit 1 (TR Bay 4) on temporary support - Forklift required
169 | 2026-02-08 | 11:00 | 2026-02-08 | 11:04 | 00:04 HRS | 0.07 | 0 | 상욱: TR2 loadout plan(MZP) 09-Feb FRA/PTW, 10-Feb loadout/sea fastening/MWS | OPERATIONAL | AGI TR Unit 1 | A1150 | Jacking down of AGI TR Unit 1 (TR Bay 4) on temporary support - Forklift required
170 | 2026-02-08 | 11:04 | 2026-02-08 | 12:46 | 01:42 HRS | 1.7 | 0.07 | Shariff: ETD 1600 today, ETA MZP 0300 09-Feb | OPERATIONAL | AGI TR Unit 1 | A1150 | Jacking down of AGI TR Unit 1 (TR Bay 4) on temporary support - Forklift required
171 | 2026-02-08 | 12:46 | 2026-02-08 | 12:49 | 00:03 HRS | 0.05 | 0 | 상욱: Berth request 09–11 Feb pls | OPERATIONAL | AGI TR Unit 1 | A1150 | Jacking down of AGI TR Unit 1 (TR Bay 4) on temporary support - Forklift required
172 | 2026-02-08 | 12:49 | 2026-02-08 | 13:38 | 00:49 HRS | 0.82 | 0.03 | +971 56 898 7173: AGI transformer offloading completed, FRA 승인 기반 운송 예정 | OPERATIONAL | AGI TR Unit 1 | A1150 | Jacking down of AGI TR Unit 1 (TR Bay 4) on temporary support - Forklift required
173 | 2026-02-08 | 13:38 | 2026-02-08 | 15:05 | 01:27 HRS | 1.45 | 0.06 | 상욱: ATD 1500, ETA MZP 0100 | OPERATIONAL | AGI TR Unit 1 | A1150 | Jacking down of AGI TR Unit 1 (TR Bay 4) on temporary support - Forklift required
174 | 2026-02-08 | 15:05 | 2026-02-08 | 16:17 | 01:12 HRS | 1.2 | 0.05 | Yulia: 내일 90t crane+forklift+gang booking 요청(11am/2pm) | OPERATIONAL | AGI TR Unit 1 | A1150 | Jacking down of AGI TR Unit 1 (TR Bay 4) on temporary support - Forklift required
175 | 2026-02-08 | 16:17 | 2026-02-08 | 16:25 | 00:08 HRS | 0.13 | 0.01 | Yoonus: 투입 구역(yard/berth5) + forklift capacity 확인 요청 | OPERATIONAL | AGI TR Unit 1 | A1150 | Jacking down of AGI TR Unit 1 (TR Bay 4) on temporary support - Forklift required
176 | 2026-02-08 | 16:25 | 2026-02-08 | 16:29 | 00:04 HRS | 0.07 | 0 | Yoonus: yard or berth #5? | OPERATIONAL | AGI TR Unit 1 | A1150 | Jacking down of AGI TR Unit 1 (TR Bay 4) on temporary support - Forklift required
177 | 2026-02-08 | 16:29 | 2026-02-08 | 16:41 | 00:12 HRS | 0.2 | 0.01 | Yulia: SPMT는 laydown, marine eq는 상황 따라 berth5/laydown, 10t forklift 충분 | OPERATIONAL | AGI TR Unit 1 | A1150 | Jacking down of AGI TR Unit 1 (TR Bay 4) on temporary support - Forklift required
178 | 2026-02-08 | 16:41 | 2026-02-08 | 17:32 | 00:51 HRS | 0.85 | 0.04 | Yoonus: MZP Berth #5 내일 저녁 가용 | OPERATIONAL | AGI TR Unit 1 | A1150 | Jacking down of AGI TR Unit 1 (TR Bay 4) on temporary support - Forklift required
179 | 2026-02-08 | 17:32 | 2026-02-08 | 18:36 | 01:04 HRS | 1.07 | 0.04 | LCT Bushra: Bushra plan? other berth or drop anchor? (provision/water 부족) | OPERATIONAL | AGI TR Unit 1 | A1150 | Jacking down of AGI TR Unit 1 (TR Bay 4) on temporary support - Forklift required
180 | 2026-02-08 | 18:36 | 2026-02-08 | 18:38 | 00:02 HRS | 0.03 | 0 | LCT Bushra: CAST OFF AGI 1438, ETA MZP 09-Feb 0100 | OPERATIONAL | AGI TR Unit 1 | A1121 | LCT Sails back to MZP to collect TR Unit 1
181 | 2026-02-08 | 18:38 | 2026-02-08 | 18:42 | 00:04 HRS | 0.07 | 0 | 상욱: ETA 0100, provision/drinking water 위해 가능한 jetty 문의 | OPERATIONAL | AGI TR Unit 1 | A1121 | LCT Sails back to MZP to collect TR Unit 1
182 | 2026-02-08 | 18:42 | 2026-02-08 | 20:28 | 01:46 HRS | 1.77 | 0.07 | Yoonus: 대안 jetty 없음, port authorities와 follow-up | OPERATIONAL | AGI TR Unit 1 | A1121 | LCT Sails back to MZP to collect TR Unit 1
183 | 2026-02-08 | 20:28 | 2026-02-08 | 23:09 | 02:41 HRS | 2.68 | 0.11 | LCT Bushra: drop anchor at MZP anchorage 2242hrs | OPERATIONAL | AGI TR Unit 1 | A1121 | LCT Sails back to MZP to collect TR Unit 1