## wa_group_events
event_id | activity_id | level1 | level2 | event_type | occurred_date | occurred_time | occurred_at_end | timezone | planned_start | planned_finish | description | activity_name | source_message | evidence_message_nos | duration_hrs | remarks
E001 | A1001 | MOBILIZATION | MARINE | milestone | 2026-01-25 | 08:54 |  | GST | 2026-01-26 | 2026-01-26 | Bushra Musaffah drop anchor 25/01/2026 0854 hrs | Mobilization of Marine Equipment and Steelworks | LCT Bushra: Musaffah short stay drop anchor 25/01/2026 0854 hrs | 2
E015 | A1004 | OPERATIONAL | Deck Preparations | milestone | 2026-01-27 | 07:38 |  | GST | 2026-01-27 | 2026-01-27 | SPMT crew and Marine crew arrived preparing | Deck Preparations (D-ring cutting; marking | steel sets installation) - One 5t forklift and Crane required | Yulia: SPMT crew & Marine crew arrived, preparing | 36
E014 | A1001 | MOBILIZATION | MARINE | report | 2026-01-27 | 08:00 |  | GST | 2026-01-26 | 2026-01-26 | Bushra planned arrival 27 Jan 08:00 AM | Mobilization of Marine Equipment and Steelworks | CHA: 2026-01-27 08:00 AM | 7
E003 | A1004 | OPERATIONAL | Deck Preparations | milestone | 2026-01-27 | 08:33 |  | GST | 2026-01-27 | 2026-01-27 | Crane and forklift arrived on time 27 Jan | Deck Preparations (D-ring cutting; marking | steel sets installation) - One 5t forklift and Crane required | Yulia: Crane and forklift arrived on time | 42
E004 | A1004 | OPERATIONAL | Deck Preparations | report | 2026-01-27 | 12:56 |  | GST | 2026-01-27 | 2026-01-27 | Offloading 완료 crane release SPMT assembly/beam replacement | Deck Preparations (D-ring cutting; marking | steel sets installation) - One 5t forklift and Crane required | Yulia: offloading 완료, crane release. SPMT assembly/beam replacement 진행. Bushra status? | 45
E016 | A1004 | OPERATIONAL | Deck Preparations | report | 2026-01-27 | 14:30 |  | GST | 2026-01-27 | 2026-01-27 | Beam replacement 2:30pm 시작 예정 | Deck Preparations (D-ring cutting; marking | steel sets installation) - One 5t forklift and Crane required | Yulia: 2:30pm beam replacement 시작 예정, 2nd forklift 2:30까지 요청 + LCT ETA 요청 | 46
E017 | A1004 | OPERATIONAL | Deck Preparations | report | 2026-01-27 | 17:00 |  | GST | 2026-01-27 | 2026-01-27 | Bushra Captain 17:00 berth 예상 | Deck Preparations (D-ring cutting; marking | steel sets installation) - One 5t forklift and Crane required | Yulia: Bushra Captain 정보—17:00 berth 예상 | 55
E002 | A1004 | OPERATIONAL | Deck Preparations | milestone | 2026-01-27 | 17:38 |  | GST | 2026-01-27 | 2026-01-27 | Bushra berthed MZP RORO 27.01.2026 1738 HRS | Deck Preparations (D-ring cutting; marking | steel sets installation) - One 5t forklift and Crane required | LCT Bushra: ALL FAST SECURED MINA ZAYED RORO BERTH 27.01.2026 1738 HRS | 58;59
E027 | A1003 | OPERATIONAL | Beam Replacement | milestone | 2026-01-28 | 13:19 |  | GST | 2026-01-28 | 2026-01-28 | SPMT scope 완료 release Marine crew 계속 | Beam Replacement AGI TR Unit 2 (TR Bay 3) - Two 5t forklifts required | Yulia: SPMT scope 완료→release, Marine crew 계속 | 66
E025 | A2010 | MOBILIZATION | JACKING EQUIPMENT; STEEL BRIDGE | actual_start | 2026-01-30 | 07:26 |  | GST | 2026-01-30 | 2026-01-31 | Steel plates installation 준비 시작 (PTW/reschedule 대기) | Mobilization of Jacking Equipment and Steel bridge (prior LCT's arrival to AGI with TR 1&2!))) | Yulia: 준비 시작(steel plates installation), PTW 또는 reschedule 대기 | 81
E018 | A2010 | MOBILIZATION | JACKING EQUIPMENT; STEEL BRIDGE | milestone | 2026-01-30 | 08:40 |  | GST | 2026-01-30 | 2026-01-31 | Steel plates 설치 완료 linkspan ramp adjusted | Mobilization of Jacking Equipment and Steel bridge (prior LCT's arrival to AGI with TR 1&2!))) | Yulia: steel plates 설치 완료, linkspan ramp adjusted | 82
E020 | A1060 | OPERATIONAL | AGI TR Unit 1 | report | 2026-01-30 |  |  | GST | 2026-01-30 | 2026-01-30 | HM/HSE/MZ Ops 승인 01st trip load | Load-out of AGL TR Unit 1; stool down (8am-10am) | Yoonus: HM/HSE/MZ Ops 승인(01st trip load), 출항 전 MWS COA 제출 조건 | 96
E019 | A1060 | OPERATIONAL | AGI TR Unit 1 | report | 2026-01-31 | 08:50 |  | GST | 2026-01-30 | 2026-01-30 | MWS 08:50 Mina Port 도착 예정 | Load-out of AGL TR Unit 1; stool down (8am-10am) | CHA: MWS 08:50 Mina Port 도착 예정 | 99
E005 | A1060 | OPERATIONAL | AGI TR Unit 1 | actual_start | 2026-01-31 | 10:25 |  | GST | 2026-01-30 | 2026-01-30 | Load out started 31 Jan | Load-out of AGL TR Unit 1; stool down (8am-10am) | Yulia: HM 승인 받아 load out 시작, toolbox talk 완료 / Load out started | 105;106
E006 | A1070 | OPERATIONAL | AGI TR Unit 1 | milestone | 2026-01-31 | 10:53 |  | GST | 2026-01-30 | 2026-01-31 | TR Unit 1 on LCT 31 Jan | RoRo ramp removal; Seafastening AGL TR Unit 1 - Crane required | Yulia: TR Unit 1 on LCT | 107
E007 | A1070 | OPERATIONAL | AGI TR Unit 1 | milestone | 2026-01-31 | 16:38 |  | GST | 2026-01-30 | 2026-01-31 | Sea fastening done inspection ongoing | RoRo ramp removal; Seafastening AGL TR Unit 1 - Crane required | Yulia: sea fastening done, inspection ongoing | 117
E008 | A1070 | OPERATIONAL | AGI TR Unit 1 | milestone | 2026-01-31 | 20:36 |  | GST | 2026-01-30 | 2026-01-31 | Bushra cast off Mina Zayed 31/01/2026 2036 ETA AGI 01/02/2026 0700 | RoRo ramp removal; Seafastening AGL TR Unit 1 - Crane required | LCT Bushra: 31/01/2026 2036 cast off, ETA AGI 01/02/2026 0700 | 122;123
E009 | A1081 | OPERATIONAL | AGI TR Unit 1 | milestone | 2026-02-01 | 06:00 |  | GST | 2026-02-01 | 2026-02-01 | Bushra AGI anchorage 0600 waiting berthing schedule | MWS; MPI; Sail-away - Marine Transportation by LCT to Al Ghallan Island | LCT Bushra: AGI anchorage 0600, waiting berthing schedule | 127
E010 | A1091 | OPERATIONAL | AGI TR Unit 1 | milestone | 2026-02-04 | 16:06 |  | GST | 2026-02-02 | 2026-02-02 | LCT Bushra AGI West RORO berth 3 alongside 1606 | LCT Arrival; Berthing at AGL RoRo Jetty | LCT Bushra: AGI West RORO berth 3 alongside 1606 | 141
E026 | A1141 | OPERATIONAL | AGI TR Unit 1 | report | 2026-02-06 | 15:00 |  | GST | 2026-02-05 | 2026-02-07 | Pre-ops meeting scheduled 06-Feb 15:00 | Turning of AGI TR Unit 1 (TR Bay 4) - 10t Forklift required | Yoonus: pre-ops meeting scheduled(06-Feb 15:00) | 152
E021 | A1141 | OPERATIONAL | AGI TR Unit 1 | milestone | 2026-02-07 |  |  | GST | 2026-02-05 | 2026-02-07 | AGI 1st TR loading commenced | Turning of AGI TR Unit 1 (TR Bay 4) - 10t Forklift required | 상욱: AGI 1st TR loading commenced. MZP 2nd loadout plan 10-Feb | 167
E011 | A1150 | OPERATIONAL | AGI TR Unit 1 | actual_end | 2026-02-08 | 14:00 |  | GST | 2026-02-08 | 2026-02-08 | AGI 1st TR offloading completed cast off around 2pm | Jacking down of AGI TR Unit 1 (TR Bay 4) on temporary support - Forklift required | 상욱: AGI 1st TR offloading completed. cast off around 2pm | 168
E012 | A1121 | OPERATIONAL | AGI TR Unit 1 | milestone | 2026-02-08 | 14:38 |  | GST | 2026-02-04 | 2026-02-04 | CAST OFF AGI 1438 ETA MZP 09-Feb 0100 | LCT Sails back to MZP to collect TR Unit 1 | LCT Bushra: CAST OFF AGI 1438, ETA MZP 09-Feb 0100 | 180
E024 | A1150 | OPERATIONAL | AGI TR Unit 1 | milestone | 2026-02-08 | 15:00 |  | GST | 2026-02-08 | 2026-02-08 | ATD 1500 ETA MZP 0100 09-Feb | Jacking down of AGI TR Unit 1 (TR Bay 4) on temporary support - Forklift required | 상욱: ATD 1500, ETA MZP 0100 | 173
E022 | A1150 | OPERATIONAL | AGI TR Unit 1 | milestone | 2026-02-08 | 16:00 |  | GST | 2026-02-08 | 2026-02-08 | ETD 1600 today ETA MZP 0300 09-Feb | Jacking down of AGI TR Unit 1 (TR Bay 4) on temporary support - Forklift required | Shariff: ETD 1600 today, ETA MZP 0300 09-Feb | 170
E023 | A1150 | OPERATIONAL | AGI TR Unit 1 | milestone | 2026-02-08 |  |  | GST | 2026-02-08 | 2026-02-08 | AGI transformer offloading completed | Jacking down of AGI TR Unit 1 (TR Bay 4) on temporary support - Forklift required | +971 56 898 7173: AGI transformer offloading completed, FRA 승인 기반 운송 예정 | 172